## Dashboard
ORDER-TO-DELIVERY OPERATIONS CONTROL TOWER
Executive view ¦ 420 synthetic orders ¦ PO dates Jan 2025-Aug 2026 ¦ deliveries through 10 Aug 2026 ¦ As of 11 Aug 2026
TOTAL ORDER VALUE | GROSS PROFIT |  | GROSS MARGIN | ON-TIME DELIVERY
9328187 | 2438378 |  | 26.14% | 69.35%
DELAYED ORDER VALUE | OUTSTANDING RECEIVABLES |  | AVERAGE LEAD TIME | AVERAGE COLLECTION
2706711 | 1853258 |  | 45.1477 | 71.7286
MANAGEMENT FOCUS |  | PORTFOLIO STORY
1. Supplier lead time drives 45.7% of delayed value ($1.24m), the largest root cause. |  | A complete analyst case study: validated synthetic data, formula-driven Excel KPIs, SQL and DAX logic, a priority action queue, data-quality controls, requirements traceability, UAT design, and management recommendations. No confidential data or production-system claim is used.
2. Olive Gardens carries the highest delayed exposure ($314.9k); Meridian Campus follows ($276.0k).
3. On-time delivery is 69.4%; Alpine Illumination is the lowest-performing supplier at 59.3%.
4. Outstanding receivables are $1.85m, including $1.29m already overdue.
5. 25 delayed orders ($540.5k; 20.0% of delayed value) have no classified blocker and need ownership.
6. Open Action Center first: P1 exceptions combine overdue cash, high value, or delays of 15+ days.
Note on M6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On-time delivery excludes orders that are still open because they do not yet have an actual delivery date.

## Orders
Order_ID | Project_ID | Project | Project_Segment | Supplier_ID | Supplier | Supplier_Country | Category_ID | Product_Category | Quote_Date | Approval_Date | PO_Date | Promised_Delivery | Actual_Delivery | Order_Value_USD | Cost_USD | Invoice_Date | Payment_Date | Payment_Terms_Days | Primary_Blocker | Manager_Action | Gross_Profit_USD | Gross_Margin | Lead_Time_Days | Delivery_Status | Delay_Days | Delayed_Value_USD | Collection_Days | Payment_Status | Outstanding_USD | PO_Month | Risk_Priority
ORD-0311 | PRJ-004 | District Retail | Residential | SUP-12 | Atlas Outdoor | Spain | CAT-05 | Architectural Fixtures | 2025-01-03 17:53 | 2025-01-08 17:53 | 2025-01-08 17:53 | 2025-03-05 17:53 | 2025-03-10 17:53 | 16233 | 10982 | 2025-03-16 17:53 | 2025-04-07 17:53 | 30 | Shipping / customs | Review freight milestone and customs documents | 5251 | 32.35% | 61 | Late | 5 | 16233 | 22 | Paid | 0 | 2025-01 | P3
ORD-0099 | PRJ-007 | Garden Villas | Commercial | SUP-11 | Orient Emergency Systems | Malaysia | CAT-06 | Electrical Accessories | 2025-01-06 22:35 | 2025-01-10 22:35 | 2025-01-10 22:35 | 2025-03-23 22:35 | 2025-03-23 22:35 | 19367 | 13218 | 2025-03-24 22:35 | 2025-04-25 22:35 | 30 | None | Monitor to plan | 6149 | 31.75% | 72 | On Time | 0 | 0 | 32 | Paid | 0 | 2025-01 | Monitor
ORD-0231 | PRJ-005 | Elm Hospital | Public Sector | SUP-04 | Anatolia Lighting | Turkey | CAT-05 | Architectural Fixtures | 2025-01-05 22:34 | 2025-01-08 22:34 | 2025-01-11 22:34 | 2025-02-26 22:34 | 2025-02-23 22:34 | 57723 | 45401 | 2025-02-24 22:34 | 2025-04-16 22:34 | 45 | None | Monitor to plan | 12322 | 21.35% | 43 | On Time | 0 | 0 | 51 | Paid | 0 | 2025-01 | Monitor
ORD-0201 | PRJ-007 | Garden Villas | Commercial | SUP-07 | Nordic Beam | Germany | CAT-04 | Emergency Lighting | 2025-01-08 03:40 | 2025-01-13 03:40 | 2025-01-13 03:40 | 2025-03-08 03:40 | 2025-03-07 03:40 | 30458 | 21602 | 2025-03-12 03:40 | 2025-04-09 03:40 | 30 | None | Monitor to plan | 8856 | 29.08% | 53 | On Time | 0 | 0 | 28 | Paid | 0 | 2025-01 | Monitor
ORD-0286 | PRJ-005 | Elm Hospital | Public Sector | SUP-11 | Orient Emergency Systems | Malaysia | CAT-03 | Lighting Controls | 2025-01-08 07:46 | 2025-01-09 07:46 | 2025-01-13 07:46 | 2025-03-17 07:46 | 2025-04-02 07:46 | 5067 | 3617 | 2025-04-05 07:46 | 2025-06-07 07:46 | 60 | None | Monitor to plan | 1450 | 28.62% | 79 | Late | 16 | 5067 | 63 | Paid | 0 | 2025-01 | P1
ORD-0047 | PRJ-009 | Iris Resort | Residential | SUP-01 | Cedar Components | Lebanon | CAT-02 | Outdoor Lighting | 2025-01-08 00:41 | 2025-01-14 00:41 | 2025-01-14 00:41 | 2025-02-10 00:41 | 2025-02-03 00:41 | 24128 | 18944 | 2025-02-03 00:41 | 2025-03-19 00:41 | 45 | None | Monitor to plan | 5184 | 21.49% | 20 | On Time | 0 | 0 | 44 | Paid | 0 | 2025-01 | Monitor
ORD-0229 | PRJ-001 | Atlas Hotel | Hospitality | SUP-08 | Gulf Smart Controls | UAE | CAT-02 | Outdoor Lighting | 2025-01-11 01:54 | 2025-01-17 01:54 | 2025-01-18 01:54 | 2025-02-19 01:54 | 2025-02-13 01:54 | 50018 | 37986 | 2025-02-14 01:54 |  | 30 | None | Monitor to plan | 12032 | 24.06% | 26 | On Time | 0 | 0 | 542.9206 | Overdue | 50018 | 2025-01 | P1
ORD-0250 | PRJ-003 | Cedar Residence | Retail | SUP-05 | Aegean Systems | Greece | CAT-06 | Electrical Accessories | 2025-01-12 05:45 | 2025-01-16 05:45 | 2025-01-18 05:45 | 2025-03-10 05:45 | 2025-03-13 05:45 | 17201 | 13835 | 2025-03-16 05:45 | 2025-04-13 05:45 | 30 | None | Monitor to plan | 3366 | 19.57% | 54 | Late | 3 | 17201 | 28 | Paid | 0 | 2025-01 | P3
ORD-0017 | PRJ-013 | Meridian Campus | Retail | SUP-06 | Alpine Illumination | Italy | CAT-06 | Electrical Accessories | 2025-01-14 01:52 | 2025-01-18 01:52 | 2025-01-21 01:52 | 2025-03-08 01:52 | 2025-03-07 01:52 | 10810 | 8810 | 2025-03-08 01:52 | 2025-04-20 01:52 | 45 | None | Monitor to plan | 2000 | 18.5% | 45 | On Time | 0 | 0 | 43 | Paid | 0 | 2025-01 | Monitor
ORD-0249 | PRJ-007 | Garden Villas | Commercial | SUP-04 | Anatolia Lighting | Turkey | CAT-06 | Electrical Accessories | 2025-01-19 05:06 | 2025-01-22 05:06 | 2025-01-24 05:06 | 2025-03-09 05:06 | 2025-03-07 05:06 | 16447 | 12322 | 2025-03-13 05:06 | 2025-05-03 05:06 | 45 | None | Monitor to plan | 4125 | 25.08% | 42 | On Time | 0 | 0 | 51 | Paid | 0 | 2025-01 | Monitor
ORD-0127 | PRJ-006 | Forum Center | Hospitality | SUP-04 | Anatolia Lighting | Turkey | CAT-05 | Architectural Fixtures | 2025-01-18 15:02 | 2025-01-22 15:02 | 2025-01-24 15:02 | 2025-03-08 15:02 | 2025-03-02 15:02 | 52853 | 36486 | 2025-03-08 15:02 | 2025-04-15 15:02 | 45 | None | Monitor to plan | 16367 | 30.97% | 37 | On Time | 0 | 0 | 38 | Paid | 0 | 2025-01 | Monitor
ORD-0396 | PRJ-011 | Keystone Residence | Hospitality | SUP-09 | Pearl LED Works | China | CAT-04 | Emergency Lighting | 2025-01-17 15:13 | 2025-01-22 15:13 | 2025-01-24 15:13 | 2025-04-13 15:13 | 2025-04-21 15:13 | 15375 | 11084 | 2025-04-24 15:13 |  | 45 | Payment blocker | Coordinate payment release with finance | 4291 | 27.91% | 87 | Late | 8 | 15375 | 473.3662 | Overdue | 15375 | 2025-01 | P1
ORD-0412 | PRJ-013 | Meridian Campus | Retail | SUP-01 | Cedar Components | Lebanon | CAT-05 | Architectural Fixtures | 2025-01-19 14:24 | 2025-01-22 14:24 | 2025-01-25 14:24 | 2025-02-08 14:24 | 2025-02-15 14:24 | 54053 | 37081 | 2025-02-18 14:24 | 2025-05-02 14:24 | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 16972 | 31.4% | 21 | Late | 7 | 54053 | 73 | Paid | 0 | 2025-01 | P1
ORD-0321 | PRJ-002 | Beacon Offices | Commercial | SUP-04 | Anatolia Lighting | Turkey | CAT-05 | Architectural Fixtures | 2025-01-23 03:46 | 2025-01-24 03:46 | 2025-01-27 03:46 | 2025-03-03 03:46 | 2025-02-23 03:46 | 19861 | 14496 | 2025-02-27 03:46 | 2025-04-21 03:46 | 60 | None | Monitor to plan | 5365 | 27.01% | 27 | On Time | 0 | 0 | 53 | Paid | 0 | 2025-01 | Monitor
ORD-0341 | PRJ-002 | Beacon Offices | Commercial | SUP-09 | Pearl LED Works | China | CAT-06 | Electrical Accessories | 2025-01-19 04:49 | 2025-01-25 04:49 | 2025-01-27 04:49 | 2025-04-09 04:49 | 2025-04-18 04:49 | 18810 | 14138 | 2025-04-21 04:49 |  | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 4672 | 24.84% | 81 | Late | 9 | 18810 | 476.7996 | Overdue | 18810 | 2025-01 | P1
ORD-0119 | PRJ-009 | Iris Resort | Residential | SUP-02 | Levant Controls | Lebanon | CAT-06 | Electrical Accessories | 2025-01-09 14:32 | 2025-01-25 14:32 | 2025-01-28 14:32 | 2025-02-19 14:32 | 2025-02-21 14:32 | 17713 | 12786 | 2025-02-22 14:32 | 2025-05-04 14:32 | 60 | Client approval | Confirm decision owner and approval deadline | 4927 | 27.82% | 24 | Late | 2 | 17713 | 71 | Paid | 0 | 2025-01 | P3
ORD-0398 | PRJ-014 | Northgate Complex | Residential | SUP-12 | Atlas Outdoor | Spain | CAT-05 | Architectural Fixtures | 2025-01-19 23:54 | 2025-01-24 23:54 | 2025-01-28 23:54 | 2025-03-21 23:54 | 2025-03-17 23:54 | 33714 | 24759 | 2025-03-22 23:54 | 2025-05-07 23:54 | 45 | Documentation | Complete missing document and revalidate order | 8955 | 26.56% | 48 | On Time | 0 | 0 | 46 | Paid | 0 | 2025-01 | Monitor
ORD-0392 | PRJ-008 | Harbor Offices | Retail | SUP-05 | Aegean Systems | Greece | CAT-04 | Emergency Lighting | 2025-01-20 01:53 | 2025-01-25 01:53 | 2025-01-29 01:53 | 2025-03-21 01:53 | 2025-03-15 01:53 | 22517 | 16290 | 2025-03-21 01:53 | 2025-04-16 01:53 | 30 | None | Monitor to plan | 6227 | 27.65% | 45 | On Time | 0 | 0 | 26 | Paid | 0 | 2025-01 | Monitor
ORD-0292 | PRJ-007 | Garden Villas | Commercial | SUP-12 | Atlas Outdoor | Spain | CAT-05 | Architectural Fixtures | 2025-01-18 03:18 | 2025-01-25 03:18 | 2025-01-29 03:18 | 2025-03-17 03:18 | 2025-03-29 03:18 | 16913 | 13727 | 2025-04-02 03:18 | 2025-05-13 03:18 | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 3186 | 18.84% | 59 | Late | 12 | 16913 | 41 | Paid | 0 | 2025-01 | P2
ORD-0044 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-01 | Cedar Components | Lebanon | CAT-06 | Electrical Accessories | 2025-01-27 08:38 | 2025-01-29 08:38 | 2025-01-29 08:38 | 2025-02-22 08:38 | 2025-02-25 08:38 | 13181 | 10697 | 2025-03-03 08:38 | 2025-04-26 08:38 | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 2484 | 18.85% | 27 | Late | 3 | 13181 | 54 | Paid | 0 | 2025-01 | P3
ORD-0066 | PRJ-006 | Forum Center | Hospitality | SUP-02 | Levant Controls | Lebanon | CAT-03 | Lighting Controls | 2025-01-21 08:20 | 2025-01-27 08:20 | 2025-01-30 08:20 | 2025-02-24 08:20 | 2025-02-16 08:20 | 29051 | 22907 | 2025-02-19 08:20 | 2025-04-28 08:20 | 60 | None | Monitor to plan | 6144 | 21.15% | 17 | On Time | 0 | 0 | 68 | Paid | 0 | 2025-01 | Monitor
ORD-0116 | PRJ-003 | Cedar Residence | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-04 | Emergency Lighting | 2025-01-25 03:06 | 2025-01-30 03:06 | 2025-02-03 03:06 | 2025-03-01 03:06 | 2025-03-01 03:06 | 5397 | 3959 | 2025-03-04 03:06 | 2025-04-07 03:06 | 30 | None | Monitor to plan | 1438 | 26.64% | 26 | On Time | 0 | 0 | 34 | Paid | 0 | 2025-02 | Monitor
ORD-0093 | PRJ-002 | Beacon Offices | Commercial | SUP-09 | Pearl LED Works | China | CAT-04 | Emergency Lighting | 2025-01-31 06:15 | 2025-02-02 06:15 | 2025-02-06 06:15 | 2025-04-18 06:15 | 2025-04-11 06:15 | 5884 | 4054 | 2025-04-17 06:15 | 2025-05-26 06:15 | 30 | None | Monitor to plan | 1830 | 31.1% | 64 | On Time | 0 | 0 | 39 | Paid | 0 | 2025-02 | Monitor
ORD-0399 | PRJ-009 | Iris Resort | Residential | SUP-10 | Pacific Fixtures | China | CAT-06 | Electrical Accessories | 2025-01-29 01:16 | 2025-02-05 01:16 | 2025-02-08 01:16 | 2025-05-02 01:16 | 2025-05-17 01:16 | 14701 | 11167 | 2025-05-22 01:16 | 2025-07-15 01:16 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 3534 | 24.04% | 98 | Late | 15 | 14701 | 54 | Paid | 0 | 2025-02 | P1
ORD-0293 | PRJ-004 | District Retail | Residential | SUP-10 | Pacific Fixtures | China | CAT-02 | Outdoor Lighting | 2025-01-31 04:00 | 2025-02-06 04:00 | 2025-02-08 04:00 | 2025-04-28 04:00 | 2025-05-09 04:00 | 8561 | 5580 | 2025-05-13 04:00 | 2025-06-23 04:00 | 45 | None | Monitor to plan | 2981 | 34.82% | 90 | Late | 11 | 8561 | 41 | Paid | 0 | 2025-02 | P2
ORD-0406 | PRJ-014 | Northgate Complex | Residential | SUP-01 | Cedar Components | Lebanon | CAT-02 | Outdoor Lighting | 2025-02-04 06:23 | 2025-02-08 06:23 | 2025-02-09 06:23 | 2025-03-06 06:23 | 2025-03-23 06:23 | 37867 | 27341 | 2025-03-29 06:23 | 2025-04-23 06:23 | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 10526 | 27.8% | 42 | Late | 17 | 37867 | 25 | Paid | 0 | 2025-02 | P1
ORD-0159 | PRJ-007 | Garden Villas | Commercial | SUP-03 | Phoenicia Electrical | Lebanon | CAT-05 | Architectural Fixtures | 2025-02-09 10:31 | 2025-02-15 10:31 | 2025-02-15 10:31 | 2025-03-05 10:31 | 2025-02-25 10:31 | 44608 | 31335 | 2025-03-01 10:31 | 2025-04-14 10:31 | 45 | None | Monitor to plan | 13273 | 29.75% | 10 | On Time | 0 | 0 | 44 | Paid | 0 | 2025-02 | Monitor
ORD-0074 | PRJ-011 | Keystone Residence | Hospitality | SUP-02 | Levant Controls | Lebanon | CAT-05 | Architectural Fixtures | 2025-02-10 14:57 | 2025-02-15 14:57 | 2025-02-15 14:57 | 2025-03-19 14:57 | 2025-03-18 14:57 | 19175 | 15473 | 2025-03-19 14:57 | 2025-05-20 14:57 | 60 | None | Monitor to plan | 3702 | 19.31% | 31 | On Time | 0 | 0 | 62 | Paid | 0 | 2025-02 | Monitor
ORD-0320 | PRJ-007 | Garden Villas | Commercial | SUP-12 | Atlas Outdoor | Spain | CAT-06 | Electrical Accessories | 2025-02-10 01:18 | 2025-02-15 01:18 | 2025-02-19 01:18 | 2025-04-12 01:18 | 2025-04-04 01:18 | 18643 | 15146 | 2025-04-04 01:18 | 2025-05-25 01:18 | 45 | None | Monitor to plan | 3497 | 18.76% | 44 | On Time | 0 | 0 | 51 | Paid | 0 | 2025-02 | Monitor
ORD-0235 | PRJ-013 | Meridian Campus | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-03 | Lighting Controls | 2025-02-12 11:26 | 2025-02-15 11:26 | 2025-02-19 11:26 | 2025-03-20 11:26 | 2025-03-18 11:26 | 27658 | 19926 | 2025-03-20 11:26 | 2025-05-24 11:26 | 60 | None | Monitor to plan | 7732 | 27.96% | 27 | On Time | 0 | 0 | 65 | Paid | 0 | 2025-02 | Monitor
ORD-0161 | PRJ-003 | Cedar Residence | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-04 | Emergency Lighting | 2025-02-11 18:09 | 2025-02-15 18:09 | 2025-02-19 18:09 | 2025-03-14 18:09 | 2025-03-14 18:09 | 15873 | 11442 | 2025-03-18 18:09 | 2025-05-01 18:09 | 45 | Payment blocker | Coordinate payment release with finance | 4431 | 27.92% | 23 | On Time | 0 | 0 | 44 | Paid | 0 | 2025-02 | Monitor
ORD-0213 | PRJ-006 | Forum Center | Hospitality | SUP-08 | Gulf Smart Controls | UAE | CAT-06 | Electrical Accessories | 2025-02-14 13:52 | 2025-02-20 13:52 | 2025-02-20 13:52 | 2025-03-28 13:52 | 2025-03-25 13:52 | 13156 | 9426 | 2025-03-26 13:52 | 2025-05-15 13:52 | 45 | None | Monitor to plan | 3730 | 28.35% | 33 | On Time | 0 | 0 | 50 | Paid | 0 | 2025-02 | Monitor
ORD-0004 | PRJ-010 | Juniper Mall | Public Sector | SUP-12 | Atlas Outdoor | Spain | CAT-02 | Outdoor Lighting | 2025-02-04 15:11 | 2025-02-17 15:11 | 2025-02-20 15:11 | 2025-04-11 15:11 | 2025-04-10 15:11 | 22841 | 17320 | 2025-04-16 15:11 | 2025-06-08 15:11 | 60 | Client approval | Confirm decision owner and approval deadline | 5521 | 24.17% | 49 | On Time | 0 | 0 | 53 | Paid | 0 | 2025-02 | Monitor
ORD-0043 | PRJ-008 | Harbor Offices | Retail | SUP-02 | Levant Controls | Lebanon | CAT-02 | Outdoor Lighting | 2025-02-13 03:02 | 2025-02-18 03:02 | 2025-02-22 03:02 | 2025-03-15 03:02 | 2025-03-30 03:02 | 10576 | 7122 | 2025-04-03 03:02 | 2025-04-24 03:02 | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 3454 | 32.66% | 36 | Late | 15 | 10576 | 21 | Paid | 0 | 2025-02 | P1
ORD-0326 | PRJ-002 | Beacon Offices | Commercial | SUP-07 | Nordic Beam | Germany | CAT-05 | Architectural Fixtures | 2025-02-20 03:38 | 2025-02-24 03:38 | 2025-02-26 03:38 | 2025-04-25 03:38 | 2025-04-19 03:38 | 6315 | 4163 | 2025-04-20 03:38 | 2025-05-29 03:38 | 30 | None | Monitor to plan | 2152 | 34.08% | 52 | On Time | 0 | 0 | 39 | Paid | 0 | 2025-02 | Monitor
ORD-0062 | PRJ-006 | Forum Center | Hospitality | SUP-02 | Levant Controls | Lebanon | CAT-04 | Emergency Lighting | 2025-02-21 12:04 | 2025-02-22 12:04 | 2025-02-26 12:04 | 2025-03-20 12:04 | 2025-03-16 12:04 | 20294 | 13649 | 2025-03-19 12:04 | 2025-05-17 12:04 | 45 | None | Monitor to plan | 6645 | 32.74% | 18 | On Time | 0 | 0 | 59 | Paid | 0 | 2025-02 | Monitor
ORD-0196 | PRJ-001 | Atlas Hotel | Hospitality | SUP-04 | Anatolia Lighting | Turkey | CAT-05 | Architectural Fixtures | 2025-02-19 19:16 | 2025-02-24 19:16 | 2025-02-27 19:16 | 2025-04-02 19:16 | 2025-04-11 19:16 | 30391 | 23484 | 2025-04-14 19:16 | 2025-05-22 19:16 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 6907 | 22.73% | 43 | Late | 9 | 30391 | 38 | Paid | 0 | 2025-02 | P2
ORD-0188 | PRJ-015 | Olive Gardens | Public Sector | SUP-01 | Cedar Components | Lebanon | CAT-04 | Emergency Lighting | 2025-02-27 13:56 | 2025-03-01 13:56 | 2025-03-01 13:56 | 2025-03-15 13:56 | 2025-03-11 13:56 | 22063 | 17422 | 2025-03-13 13:56 | 2025-05-03 13:56 | 60 | None | Monitor to plan | 4641 | 21.04% | 10 | On Time | 0 | 0 | 51 | Paid | 0 | 2025-03 | Monitor
ORD-0211 | PRJ-010 | Juniper Mall | Public Sector | SUP-11 | Orient Emergency Systems | Malaysia | CAT-03 | Lighting Controls | 2025-02-21 17:24 | 2025-02-26 17:24 | 2025-03-02 17:24 | 2025-05-10 17:24 | 2025-05-18 17:24 | 14533 | 11445 | 2025-05-19 17:24 | 2025-07-20 17:24 | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 3088 | 21.25% | 77 | Late | 8 | 14533 | 62 | Paid | 0 | 2025-03 | P2
ORD-0329 | PRJ-006 | Forum Center | Hospitality | SUP-06 | Alpine Illumination | Italy | CAT-03 | Lighting Controls | 2025-02-28 05:24 | 2025-03-02 05:24 | 2025-03-03 05:24 | 2025-04-28 05:24 | 2025-04-20 05:24 | 21485 | 15490 | 2025-04-24 05:24 | 2025-05-17 05:24 | 30 | None | Monitor to plan | 5995 | 27.9% | 48 | On Time | 0 | 0 | 23 | Paid | 0 | 2025-03 | Monitor
ORD-0200 | PRJ-015 | Olive Gardens | Public Sector | SUP-10 | Pacific Fixtures | China | CAT-05 | Architectural Fixtures | 2025-02-25 20:40 | 2025-02-28 20:40 | 2025-03-04 20:40 | 2025-05-28 20:40 | 2025-05-28 20:40 | 19117 | 13856 | 2025-05-28 20:40 | 2025-08-02 20:40 | 60 | None | Monitor to plan | 5261 | 27.52% | 85 | On Time | 0 | 0 | 66 | Paid | 0 | 2025-03 | Monitor
ORD-0204 | PRJ-015 | Olive Gardens | Public Sector | SUP-11 | Orient Emergency Systems | Malaysia | CAT-05 | Architectural Fixtures | 2025-02-28 02:35 | 2025-03-04 02:35 | 2025-03-05 02:35 | 2025-05-18 02:35 | 2025-05-14 02:35 | 21245 | 15478 | 2025-05-14 02:35 | 2025-07-12 02:35 | 45 | None | Monitor to plan | 5767 | 27.15% | 70 | On Time | 0 | 0 | 59 | Paid | 0 | 2025-03 | Monitor
ORD-0280 | PRJ-013 | Meridian Campus | Retail | SUP-10 | Pacific Fixtures | China | CAT-05 | Architectural Fixtures | 2025-03-03 05:45 | 2025-03-04 05:45 | 2025-03-08 05:45 | 2025-05-25 05:45 | 2025-05-23 05:45 | 28488 | 22954 | 2025-05-24 05:45 |  | 60 | None | Monitor to plan | 5534 | 19.43% | 76 | On Time | 0 | 0 | 443.7602 | Overdue | 28488 | 2025-03 | P1
ORD-0173 | PRJ-003 | Cedar Residence | Retail | SUP-04 | Anatolia Lighting | Turkey | CAT-03 | Lighting Controls | 2025-03-10 16:50 | 2025-03-11 16:50 | 2025-03-12 16:50 | 2025-04-21 16:50 | 2025-04-23 16:50 | 24006 | 16317 | 2025-04-27 16:50 |  | 30 | None | Monitor to plan | 7689 | 32.03% | 42 | Late | 2 | 24006 | 470.2984 | Overdue | 24006 | 2025-03 | P1
ORD-0040 | PRJ-002 | Beacon Offices | Commercial | SUP-03 | Phoenicia Electrical | Lebanon | CAT-03 | Lighting Controls | 2025-03-05 17:24 | 2025-03-11 17:24 | 2025-03-13 17:24 | 2025-04-07 17:24 | 2025-04-01 17:24 | 10450 | 8487 | 2025-04-01 17:24 | 2025-05-07 17:24 | 30 | None | Monitor to plan | 1963 | 18.78% | 19 | On Time | 0 | 0 | 36 | Paid | 0 | 2025-03 | Monitor
ORD-0190 | PRJ-008 | Harbor Offices | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-03 | Lighting Controls | 2025-02-24 19:16 | 2025-03-14 19:16 | 2025-03-15 19:16 | 2025-04-06 19:16 | 2025-04-09 19:16 | 26552 | 20358 | 2025-04-15 19:16 | 2025-05-28 19:16 | 45 | Client approval | Confirm decision owner and approval deadline | 6194 | 23.33% | 25 | Late | 3 | 26552 | 43 | Paid | 0 | 2025-03 | P2
ORD-0375 | PRJ-001 | Atlas Hotel | Hospitality | SUP-10 | Pacific Fixtures | China | CAT-06 | Electrical Accessories | 2025-03-11 05:42 | 2025-03-16 05:42 | 2025-03-16 05:42 | 2025-06-08 05:42 | 2025-06-08 05:42 | 8107 | 6478 | 2025-06-08 05:42 | 2025-07-14 05:42 | 30 | None | Monitor to plan | 1629 | 20.09% | 84 | On Time | 0 | 0 | 36 | Paid | 0 | 2025-03 | Monitor
ORD-0401 | PRJ-002 | Beacon Offices | Commercial | SUP-08 | Gulf Smart Controls | UAE | CAT-06 | Electrical Accessories | 2025-03-08 07:33 | 2025-03-13 07:33 | 2025-03-16 07:33 | 2025-04-22 07:33 | 2025-04-14 07:33 | 15824 | 10400 | 2025-04-15 07:33 | 2025-05-30 07:33 | 45 | None | Monitor to plan | 5424 | 34.28% | 29 | On Time | 0 | 0 | 45 | Paid | 0 | 2025-03 | Monitor
ORD-0125 | PRJ-014 | Northgate Complex | Residential | SUP-07 | Nordic Beam | Germany | CAT-03 | Lighting Controls | 2025-03-07 10:57 | 2025-03-14 10:57 | 2025-03-16 10:57 | 2025-05-09 10:57 | 2025-05-16 10:57 | 12942 | 8573 | 2025-05-21 10:57 | 2025-06-26 10:57 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 4369 | 33.76% | 61 | Late | 7 | 12942 | 36 | Paid | 0 | 2025-03 | P2
ORD-0364 | PRJ-006 | Forum Center | Hospitality | SUP-05 | Aegean Systems | Greece | CAT-04 | Emergency Lighting | 2025-03-12 02:27 | 2025-03-17 02:27 | 2025-03-17 02:27 | 2025-04-28 02:27 | 2025-05-07 02:27 | 24673 | 16568 | 2025-05-10 02:27 | 2025-07-04 02:27 | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 8105 | 32.85% | 51 | Late | 9 | 24673 | 55 | Paid | 0 | 2025-03 | P2
ORD-0420 | PRJ-009 | Iris Resort | Residential | SUP-12 | Atlas Outdoor | Spain | CAT-02 | Outdoor Lighting | 2025-03-14 17:53 | 2025-03-16 17:53 | 2025-03-17 17:53 | 2025-05-16 17:53 | 2025-05-14 17:53 | 11002 | 8479 | 2025-05-18 17:53 | 2025-07-14 17:53 | 45 | None | Monitor to plan | 2523 | 22.93% | 58 | On Time | 0 | 0 | 57 | Paid | 0 | 2025-03 | Monitor
ORD-0416 | PRJ-010 | Juniper Mall | Public Sector | SUP-03 | Phoenicia Electrical | Lebanon | CAT-03 | Lighting Controls | 2025-03-16 15:47 | 2025-03-18 15:47 | 2025-03-18 15:47 | 2025-04-13 15:47 | 2025-04-16 15:47 | 11594 | 8972 | 2025-04-17 15:47 | 2025-05-28 15:47 | 30 | Shipping / customs | Review freight milestone and customs documents | 2622 | 22.62% | 29 | Late | 3 | 11594 | 41 | Paid | 0 | 2025-03 | P3
ORD-0371 | PRJ-006 | Forum Center | Hospitality | SUP-04 | Anatolia Lighting | Turkey | CAT-02 | Outdoor Lighting | 2025-03-18 17:45 | 2025-03-20 17:45 | 2025-03-20 17:45 | 2025-05-01 17:45 | 2025-05-06 17:45 | 13841 | 10890 | 2025-05-11 17:45 | 2025-07-23 17:45 | 60 | None | Monitor to plan | 2951 | 21.32% | 47 | Late | 5 | 13841 | 73 | Paid | 0 | 2025-03 | P3
ORD-0152 | PRJ-013 | Meridian Campus | Retail | SUP-01 | Cedar Components | Lebanon | CAT-02 | Outdoor Lighting | 2025-03-10 09:51 | 2025-03-17 09:51 | 2025-03-21 09:51 | 2025-04-16 09:51 | 2025-04-10 09:51 | 14642 | 10333 | 2025-04-14 09:51 |  | 60 | None | Monitor to plan | 4309 | 29.43% | 20 | On Time | 0 | 0 | 483.5898 | Overdue | 14642 | 2025-03 | P1
ORD-0138 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-03 | Phoenicia Electrical | Lebanon | CAT-06 | Electrical Accessories | 2025-03-19 14:00 | 2025-03-21 14:00 | 2025-03-21 14:00 | 2025-04-14 14:00 | 2025-04-10 14:00 | 18534 | 13531 | 2025-04-12 14:00 | 2025-05-16 14:00 | 30 | None | Monitor to plan | 5003 | 26.99% | 20 | On Time | 0 | 0 | 34 | Paid | 0 | 2025-03 | Monitor
ORD-0080 | PRJ-015 | Olive Gardens | Public Sector | SUP-11 | Orient Emergency Systems | Malaysia | CAT-03 | Lighting Controls | 2025-03-21 16:40 | 2025-03-24 16:40 | 2025-03-25 16:40 | 2025-05-29 16:40 | 2025-06-18 16:40 | 24882 | 19620 | 2025-06-21 16:40 |  | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 5262 | 21.15% | 85 | Late | 20 | 24882 | 415.3059 | Overdue | 24882 | 2025-03 | P1
ORD-0247 | PRJ-014 | Northgate Complex | Residential | SUP-12 | Atlas Outdoor | Spain | CAT-01 | Indoor Lighting | 2025-03-19 16:45 | 2025-03-26 16:45 | 2025-03-26 16:45 | 2025-05-22 16:45 | 2025-05-15 16:45 | 27084 | 18995 | 2025-05-16 16:45 | 2025-07-12 16:45 | 60 | None | Monitor to plan | 8089 | 29.87% | 50 | On Time | 0 | 0 | 57 | Paid | 0 | 2025-03 | Monitor
ORD-0246 | PRJ-010 | Juniper Mall | Public Sector | SUP-05 | Aegean Systems | Greece | CAT-04 | Emergency Lighting | 2025-03-20 09:39 | 2025-03-26 09:39 | 2025-03-28 09:39 | 2025-05-14 09:39 | 2025-05-11 09:39 | 23005 | 17025 | 2025-05-13 09:39 | 2025-07-08 09:39 | 60 | None | Monitor to plan | 5980 | 25.99% | 44 | On Time | 0 | 0 | 56 | Paid | 0 | 2025-03 | Monitor
ORD-0236 | PRJ-014 | Northgate Complex | Residential | SUP-10 | Pacific Fixtures | China | CAT-06 | Electrical Accessories | 2025-03-25 06:10 | 2025-03-29 06:10 | 2025-03-29 06:10 | 2025-06-10 06:10 | 2025-06-09 06:10 | 12311 | 9613 | 2025-06-15 06:10 | 2025-08-08 06:10 | 45 | None | Monitor to plan | 2698 | 21.92% | 72 | On Time | 0 | 0 | 54 | Paid | 0 | 2025-03 | Monitor
ORD-0373 | PRJ-008 | Harbor Offices | Retail | SUP-12 | Atlas Outdoor | Spain | CAT-01 | Indoor Lighting | 2025-03-19 13:57 | 2025-03-26 13:57 | 2025-03-30 13:57 | 2025-05-30 13:57 | 2025-05-22 13:57 | 24251 | 19864 | 2025-05-24 13:57 | 2025-07-14 13:57 | 60 | None | Monitor to plan | 4387 | 18.09% | 53 | On Time | 0 | 0 | 51 | Paid | 0 | 2025-03 | Monitor
ORD-0199 | PRJ-005 | Elm Hospital | Public Sector | SUP-05 | Aegean Systems | Greece | CAT-01 | Indoor Lighting | 2025-03-26 10:18 | 2025-03-29 10:18 | 2025-04-01 10:18 | 2025-05-11 10:18 | 2025-05-14 10:18 | 41366 | 32580 | 2025-05-19 10:18 | 2025-07-29 10:18 | 60 | Payment blocker | Coordinate payment release with finance | 8786 | 21.24% | 43 | Late | 3 | 41366 | 71 | Paid | 0 | 2025-04 | P1
ORD-0234 | PRJ-013 | Meridian Campus | Retail | SUP-02 | Levant Controls | Lebanon | CAT-02 | Outdoor Lighting | 2025-03-31 02:27 | 2025-04-03 02:27 | 2025-04-04 02:27 | 2025-05-05 02:27 | 2025-05-20 02:27 | 13403 | 9522 | 2025-05-26 02:27 | 2025-07-05 02:27 | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 3881 | 28.96% | 46 | Late | 15 | 13403 | 40 | Paid | 0 | 2025-04 | P1
ORD-0306 | PRJ-006 | Forum Center | Hospitality | SUP-08 | Gulf Smart Controls | UAE | CAT-01 | Indoor Lighting | 2025-03-31 04:22 | 2025-04-02 04:22 | 2025-04-05 04:22 | 2025-05-12 04:22 | 2025-05-06 04:22 | 3624 | 2742 | 2025-05-08 04:22 | 2025-07-11 04:22 | 60 | None | Monitor to plan | 882 | 24.34% | 31 | On Time | 0 | 0 | 64 | Paid | 0 | 2025-04 | Monitor
ORD-0056 | PRJ-008 | Harbor Offices | Retail | SUP-01 | Cedar Components | Lebanon | CAT-02 | Outdoor Lighting | 2025-03-18 20:08 | 2025-04-05 20:08 | 2025-04-05 20:08 | 2025-05-01 20:08 | 2025-04-26 20:08 | 40325 | 29594 | 2025-04-29 20:08 |  | 45 | Client approval | Confirm decision owner and approval deadline | 10731 | 26.61% | 21 | On Time | 0 | 0 | 468.1614 | Overdue | 40325 | 2025-04 | P1
ORD-0185 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-02 | Levant Controls | Lebanon | CAT-04 | Emergency Lighting | 2025-04-01 22:01 | 2025-04-08 22:01 | 2025-04-08 22:01 | 2025-04-30 22:01 | 2025-04-30 22:01 | 7749 | 6159 | 2025-05-02 22:01 | 2025-05-26 22:01 | 30 | None | Monitor to plan | 1590 | 20.52% | 22 | On Time | 0 | 0 | 24 | Paid | 0 | 2025-04 | Monitor
ORD-0176 | PRJ-003 | Cedar Residence | Retail | SUP-12 | Atlas Outdoor | Spain | CAT-05 | Architectural Fixtures | 2025-04-02 09:21 | 2025-04-08 09:21 | 2025-04-10 09:21 | 2025-05-28 09:21 | 2025-06-01 09:21 | 15464 | 12642 | 2025-06-05 09:21 | 2025-07-14 09:21 | 45 | Payment blocker | Coordinate payment release with finance | 2822 | 18.25% | 52 | Late | 4 | 15464 | 39 | Paid | 0 | 2025-04 | P3
ORD-0356 | PRJ-002 | Beacon Offices | Commercial | SUP-11 | Orient Emergency Systems | Malaysia | CAT-02 | Outdoor Lighting | 2025-04-03 16:18 | 2025-04-10 16:18 | 2025-04-10 16:18 | 2025-06-15 16:18 | 2025-06-15 16:18 | 27640 | 21896 | 2025-06-16 16:18 | 2025-07-17 16:18 | 30 | None | Monitor to plan | 5744 | 20.78% | 66 | On Time | 0 | 0 | 31 | Paid | 0 | 2025-04 | Monitor
ORD-0380 | PRJ-015 | Olive Gardens | Public Sector | SUP-03 | Phoenicia Electrical | Lebanon | CAT-01 | Indoor Lighting | 2025-04-02 16:29 | 2025-04-07 16:29 | 2025-04-10 16:29 | 2025-05-06 16:29 | 2025-05-03 16:29 | 32102 | 24958 | 2025-05-08 16:29 |  | 45 | Payment blocker | Coordinate payment release with finance | 7144 | 22.25% | 23 | On Time | 0 | 0 | 459.3132 | Overdue | 32102 | 2025-04 | P1
ORD-0118 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-09 | Pearl LED Works | China | CAT-06 | Electrical Accessories | 2025-04-05 21:01 | 2025-04-12 21:01 | 2025-04-13 21:01 | 2025-06-27 21:01 | 2025-06-27 21:01 | 13901 | 9924 | 2025-07-03 21:01 |  | 60 | None | Monitor to plan | 3977 | 28.61% | 75 | On Time | 0 | 0 | 403.1244 | Overdue | 13901 | 2025-04 | P1
ORD-0265 | PRJ-007 | Garden Villas | Commercial | SUP-10 | Pacific Fixtures | China | CAT-05 | Architectural Fixtures | 2025-03-29 18:02 | 2025-04-12 18:02 | 2025-04-15 18:02 | 2025-06-30 18:02 | 2025-06-29 18:02 | 22559 | 18187 | 2025-07-05 18:02 | 2025-08-14 18:02 | 45 | Client approval | Confirm decision owner and approval deadline | 4372 | 19.38% | 75 | On Time | 0 | 0 | 40 | Paid | 0 | 2025-04 | Monitor
ORD-0048 | PRJ-002 | Beacon Offices | Commercial | SUP-10 | Pacific Fixtures | China | CAT-01 | Indoor Lighting | 2025-03-28 22:40 | 2025-04-16 22:40 | 2025-04-17 22:40 | 2025-07-08 22:40 | 2025-07-01 22:40 | 5150 | 3806 | 2025-07-07 22:40 | 2025-08-13 22:40 | 30 | Client approval | Confirm decision owner and approval deadline | 1344 | 26.1% | 75 | On Time | 0 | 0 | 37 | Paid | 0 | 2025-04 | Monitor
ORD-0258 | PRJ-003 | Cedar Residence | Retail | SUP-02 | Levant Controls | Lebanon | CAT-03 | Lighting Controls | 2025-04-08 05:44 | 2025-04-14 05:44 | 2025-04-18 05:44 | 2025-05-08 05:44 | 2025-05-11 05:44 | 13021 | 8966 | 2025-05-16 05:44 | 2025-06-15 05:44 | 30 | Documentation | Complete missing document and revalidate order | 4055 | 31.14% | 23 | Late | 3 | 13021 | 30 | Paid | 0 | 2025-04 | P3
ORD-0133 | PRJ-013 | Meridian Campus | Retail | SUP-11 | Orient Emergency Systems | Malaysia | CAT-03 | Lighting Controls | 2025-04-08 12:49 | 2025-04-15 12:49 | 2025-04-18 12:49 | 2025-06-30 12:49 | 2025-06-23 12:49 | 15621 | 10781 | 2025-06-27 12:49 | 2025-08-07 12:49 | 45 | None | Monitor to plan | 4840 | 30.98% | 66 | On Time | 0 | 0 | 41 | Paid | 0 | 2025-04 | Monitor
ORD-0183 | PRJ-007 | Garden Villas | Commercial | SUP-02 | Levant Controls | Lebanon | CAT-05 | Architectural Fixtures | 2025-04-14 03:01 | 2025-04-19 03:01 | 2025-04-19 03:01 | 2025-05-13 03:01 | 2025-05-08 03:01 | 59930 | 41283 | 2025-05-14 03:01 | 2025-07-23 03:01 | 60 | None | Monitor to plan | 18647 | 31.11% | 19 | On Time | 0 | 0 | 70 | Paid | 0 | 2025-04 | Monitor
ORD-0034 | PRJ-001 | Atlas Hotel | Hospitality | SUP-12 | Atlas Outdoor | Spain | CAT-04 | Emergency Lighting | 2025-04-14 17:28 | 2025-04-17 17:28 | 2025-04-21 17:28 | 2025-06-16 17:28 | 2025-06-09 17:28 | 16517 | 11922 | 2025-06-15 17:28 | 2025-07-10 17:28 | 30 | None | Monitor to plan | 4595 | 27.82% | 49 | On Time | 0 | 0 | 25 | Paid | 0 | 2025-04 | Monitor
ORD-0112 | PRJ-005 | Elm Hospital | Public Sector | SUP-09 | Pearl LED Works | China | CAT-05 | Architectural Fixtures | 2025-04-15 14:22 | 2025-04-18 14:22 | 2025-04-22 14:22 | 2025-07-02 14:22 | 2025-07-09 14:22 | 11694 | 9574 | 2025-07-11 14:22 | 2025-08-25 14:22 | 45 | Documentation | Complete missing document and revalidate order | 2120 | 18.13% | 78 | Late | 7 | 11694 | 45 | Paid | 0 | 2025-04 | P2
ORD-0298 | PRJ-010 | Juniper Mall | Public Sector | SUP-09 | Pearl LED Works | China | CAT-03 | Lighting Controls | 2025-04-19 07:29 | 2025-04-21 07:29 | 2025-04-25 07:29 | 2025-07-09 07:29 | 2025-07-07 07:29 | 33394 | 23732 | 2025-07-09 07:29 | 2025-08-18 07:29 | 30 | None | Monitor to plan | 9662 | 28.93% | 73 | On Time | 0 | 0 | 40 | Paid | 0 | 2025-04 | Monitor
ORD-0372 | PRJ-002 | Beacon Offices | Commercial | SUP-09 | Pearl LED Works | China | CAT-06 | Electrical Accessories | 2025-04-18 12:07 | 2025-04-22 12:07 | 2025-04-26 12:07 | 2025-07-04 12:07 | 2025-06-27 12:07 | 21635 | 14722 | 2025-07-02 12:07 |  | 30 | None | Monitor to plan | 6913 | 31.95% | 62 | On Time | 0 | 0 | 404.4949 | Overdue | 21635 | 2025-04 | P1
ORD-0408 | PRJ-014 | Northgate Complex | Residential | SUP-07 | Nordic Beam | Germany | CAT-02 | Outdoor Lighting | 2025-04-19 14:43 | 2025-04-26 14:43 | 2025-04-26 14:43 | 2025-06-24 14:43 | 2025-06-19 14:43 | 7032 | 5701 | 2025-06-21 14:43 |  | 30 | None | Monitor to plan | 1331 | 18.93% | 54 | On Time | 0 | 0 | 415.387 | Overdue | 7032 | 2025-04 | P1
ORD-0179 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-07 | Nordic Beam | Germany | CAT-03 | Lighting Controls | 2025-04-20 21:12 | 2025-04-27 21:12 | 2025-04-28 21:12 | 2025-06-17 21:12 | 2025-06-20 21:12 | 10224 | 6679 | 2025-06-24 21:12 |  | 30 | Payment blocker | Coordinate payment release with finance | 3545 | 34.67% | 53 | Late | 3 | 10224 | 412.1167 | Overdue | 10224 | 2025-04 | P1
ORD-0151 | PRJ-013 | Meridian Campus | Retail | SUP-01 | Cedar Components | Lebanon | CAT-01 | Indoor Lighting | 2025-04-25 05:21 | 2025-04-29 05:21 | 2025-04-30 05:21 | 2025-05-18 05:21 | 2025-05-21 05:21 | 7303 | 5290 | 2025-05-21 05:21 | 2025-06-21 05:21 | 30 | Shipping / customs | Review freight milestone and customs documents | 2013 | 27.56% | 21 | Late | 3 | 7303 | 31 | Paid | 0 | 2025-04 | P3
ORD-0089 | PRJ-013 | Meridian Campus | Retail | SUP-09 | Pearl LED Works | China | CAT-02 | Outdoor Lighting | 2025-04-25 19:32 | 2025-04-30 19:32 | 2025-04-30 19:32 | 2025-07-14 19:32 | 2025-07-15 19:32 | 44095 | 31024 | 2025-07-17 19:32 |  | 30 | Payment blocker | Coordinate payment release with finance | 13071 | 29.64% | 76 | Late | 1 | 44095 | 389.1864 | Overdue | 44095 | 2025-04 | P1
ORD-0092 | PRJ-004 | District Retail | Residential | SUP-09 | Pearl LED Works | China | CAT-02 | Outdoor Lighting | 2025-04-27 09:28 | 2025-05-01 09:28 | 2025-05-01 09:28 | 2025-07-12 09:28 | 2025-07-04 09:28 | 38227 | 28952 | 2025-07-08 09:28 | 2025-08-17 09:28 | 45 | None | Monitor to plan | 9275 | 24.26% | 64 | On Time | 0 | 0 | 40 | Paid | 0 | 2025-05 | Monitor
ORD-0052 | PRJ-005 | Elm Hospital | Public Sector | SUP-03 | Phoenicia Electrical | Lebanon | CAT-03 | Lighting Controls | 2025-04-29 10:56 | 2025-05-04 10:56 | 2025-05-05 10:56 | 2025-05-24 10:56 | 2025-05-18 10:56 | 9132 | 6366 | 2025-05-19 10:56 | 2025-07-24 10:56 | 60 | None | Monitor to plan | 2766 | 30.29% | 13 | On Time | 0 | 0 | 66 | Paid | 0 | 2025-05 | Monitor
ORD-0175 | PRJ-009 | Iris Resort | Residential | SUP-04 | Anatolia Lighting | Turkey | CAT-02 | Outdoor Lighting | 2025-05-02 20:22 | 2025-05-06 20:22 | 2025-05-07 20:22 | 2025-06-11 20:22 | 2025-06-09 20:22 | 28097 | 20320 | 2025-06-09 20:22 | 2025-07-31 20:22 | 45 | None | Monitor to plan | 7777 | 27.68% | 33 | On Time | 0 | 0 | 52 | Paid | 0 | 2025-05 | Monitor
ORD-0140 | PRJ-008 | Harbor Offices | Retail | SUP-10 | Pacific Fixtures | China | CAT-06 | Electrical Accessories | 2025-04-29 18:31 | 2025-05-06 18:31 | 2025-05-08 18:31 | 2025-08-01 18:31 | 2025-07-25 18:31 | 13230 | 10188 | 2025-07-26 18:31 |  | 30 | None | Monitor to plan | 3042 | 22.99% | 78 | On Time | 0 | 0 | 380.2286 | Overdue | 13230 | 2025-05 | P1
ORD-0005 | PRJ-003 | Cedar Residence | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-04 | Emergency Lighting | 2025-04-20 12:29 | 2025-05-07 12:29 | 2025-05-10 12:29 | 2025-06-04 12:29 | 2025-05-27 12:29 | 5753 | 4032 | 2025-05-31 12:29 | 2025-06-29 12:29 | 30 | Client approval | Confirm decision owner and approval deadline | 1721 | 29.91% | 17 | On Time | 0 | 0 | 29 | Paid | 0 | 2025-05 | Monitor
ORD-0325 | PRJ-003 | Cedar Residence | Retail | SUP-10 | Pacific Fixtures | China | CAT-02 | Outdoor Lighting | 2025-04-30 21:40 | 2025-05-06 21:40 | 2025-05-10 21:40 | 2025-07-29 21:40 | 2025-07-23 21:40 | 13093 | 9828 | 2025-07-28 21:40 | 2025-09-20 21:40 | 45 | None | Monitor to plan | 3265 | 24.94% | 74 | On Time | 0 | 0 | 54 | Paid | 0 | 2025-05 | Monitor
ORD-0269 | PRJ-009 | Iris Resort | Residential | SUP-10 | Pacific Fixtures | China | CAT-03 | Lighting Controls | 2025-05-07 07:41 | 2025-05-10 07:41 | 2025-05-11 07:41 | 2025-07-24 07:41 | 2025-07-18 07:41 | 13592 | 10507 | 2025-07-19 07:41 | 2025-09-03 07:41 | 45 | None | Monitor to plan | 3085 | 22.7% | 68 | On Time | 0 | 0 | 46 | Paid | 0 | 2025-05 | Monitor
ORD-0091 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-03 | Phoenicia Electrical | Lebanon | CAT-04 | Emergency Lighting | 2025-05-07 14:49 | 2025-05-09 14:49 | 2025-05-12 14:49 | 2025-06-04 14:49 | 2025-06-04 14:49 | 5671 | 4524 | 2025-06-06 14:49 | 2025-08-01 14:49 | 45 | Payment blocker | Coordinate payment release with finance | 1147 | 20.23% | 23 | On Time | 0 | 0 | 56 | Paid | 0 | 2025-05 | Monitor
ORD-0067 | PRJ-008 | Harbor Offices | Retail | SUP-05 | Aegean Systems | Greece | CAT-05 | Architectural Fixtures | 2025-05-10 19:01 | 2025-05-11 19:01 | 2025-05-13 19:01 | 2025-06-21 19:01 | 2025-06-20 19:01 | 57680 | 44112 | 2025-06-21 19:01 | 2025-07-24 19:01 | 30 | None | Monitor to plan | 13568 | 23.52% | 38 | On Time | 0 | 0 | 33 | Paid | 0 | 2025-05 | Monitor
ORD-0158 | PRJ-010 | Juniper Mall | Public Sector | SUP-02 | Levant Controls | Lebanon | CAT-06 | Electrical Accessories | 2025-05-15 06:50 | 2025-05-16 06:50 | 2025-05-17 06:50 | 2025-06-06 06:50 | 2025-06-04 06:50 | 22462 | 16762 | 2025-06-06 06:50 | 2025-07-05 06:50 | 30 | None | Monitor to plan | 5700 | 25.38% | 18 | On Time | 0 | 0 | 29 | Paid | 0 | 2025-05 | Monitor
ORD-0344 | PRJ-004 | District Retail | Residential | SUP-02 | Levant Controls | Lebanon | CAT-06 | Electrical Accessories | 2025-05-12 14:27 | 2025-05-13 14:27 | 2025-05-17 14:27 | 2025-06-05 14:27 | 2025-06-05 14:27 | 21090 | 13749 | 2025-06-11 14:27 | 2025-07-24 14:27 | 45 | None | Monitor to plan | 7341 | 34.81% | 19 | On Time | 0 | 0 | 43 | Paid | 0 | 2025-05 | Monitor
ORD-0313 | PRJ-009 | Iris Resort | Residential | SUP-11 | Orient Emergency Systems | Malaysia | CAT-04 | Emergency Lighting | 2025-05-08 18:04 | 2025-05-15 18:04 | 2025-05-17 18:04 | 2025-07-18 18:04 | 2025-08-01 18:04 | 28648 | 20163 | 2025-08-03 18:04 | 2025-09-13 18:04 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 8485 | 29.62% | 76 | Late | 14 | 28648 | 41 | Paid | 0 | 2025-05 | P2
ORD-0365 | PRJ-006 | Forum Center | Hospitality | SUP-06 | Alpine Illumination | Italy | CAT-03 | Lighting Controls | 2025-05-10 18:20 | 2025-05-16 18:20 | 2025-05-20 18:20 | 2025-07-03 18:20 | 2025-06-27 18:20 | 8287 | 6276 | 2025-07-03 18:20 | 2025-08-03 18:20 | 30 | None | Monitor to plan | 2011 | 24.27% | 38 | On Time | 0 | 0 | 31 | Paid | 0 | 2025-05 | Monitor
ORD-0226 | PRJ-004 | District Retail | Residential | SUP-05 | Aegean Systems | Greece | CAT-02 | Outdoor Lighting | 2025-05-16 03:18 | 2025-05-20 03:18 | 2025-05-21 03:18 | 2025-06-29 03:18 | 2025-06-24 03:18 | 12839 | 10081 | 2025-06-28 03:18 | 2025-07-31 03:18 | 30 | None | Monitor to plan | 2758 | 21.48% | 34 | On Time | 0 | 0 | 33 | Paid | 0 | 2025-05 | Monitor
ORD-0290 | PRJ-014 | Northgate Complex | Residential | SUP-09 | Pearl LED Works | China | CAT-06 | Electrical Accessories | 2025-05-11 09:03 | 2025-05-17 09:03 | 2025-05-21 09:03 | 2025-07-26 09:03 | 2025-07-20 09:03 | 3378 | 2280 | 2025-07-26 09:03 | 2025-09-02 09:03 | 45 | None | Monitor to plan | 1098 | 32.5% | 60 | On Time | 0 | 0 | 38 | Paid | 0 | 2025-05 | Monitor
ORD-0039 | PRJ-011 | Keystone Residence | Hospitality | SUP-01 | Cedar Components | Lebanon | CAT-06 | Electrical Accessories | 2025-05-15 13:30 | 2025-05-20 13:30 | 2025-05-21 13:30 | 2025-06-08 13:30 | 2025-06-07 13:30 | 22361 | 17698 | 2025-06-09 13:30 | 2025-07-21 13:30 | 30 | None | Monitor to plan | 4663 | 20.85% | 17 | On Time | 0 | 0 | 42 | Paid | 0 | 2025-05 | Monitor
ORD-0013 | PRJ-005 | Elm Hospital | Public Sector | SUP-05 | Aegean Systems | Greece | CAT-05 | Architectural Fixtures | 2025-05-19 15:33 | 2025-05-21 15:33 | 2025-05-22 15:33 | 2025-07-06 15:33 | 2025-07-06 15:33 | 41173 | 32819 | 2025-07-12 15:33 | 2025-09-02 15:33 | 45 | None | Monitor to plan | 8354 | 20.29% | 45 | On Time | 0 | 0 | 52 | Paid | 0 | 2025-05 | Monitor
ORD-0064 | PRJ-005 | Elm Hospital | Public Sector | SUP-05 | Aegean Systems | Greece | CAT-05 | Architectural Fixtures | 2025-05-16 05:18 | 2025-05-23 05:18 | 2025-05-24 05:18 | 2025-07-14 05:18 | 2025-07-07 05:18 | 5610 | 4170 | 2025-07-08 05:18 | 2025-09-02 05:18 | 45 | None | Monitor to plan | 1440 | 25.67% | 44 | On Time | 0 | 0 | 56 | Paid | 0 | 2025-05 | Monitor
ORD-0390 | PRJ-007 | Garden Villas | Commercial | SUP-05 | Aegean Systems | Greece | CAT-05 | Architectural Fixtures | 2025-05-16 08:36 | 2025-05-23 08:36 | 2025-05-24 08:36 | 2025-07-08 08:36 | 2025-07-06 08:36 | 16937 | 11751 | 2025-07-08 08:36 | 2025-08-08 08:36 | 30 | None | Monitor to plan | 5186 | 30.62% | 43 | On Time | 0 | 0 | 31 | Paid | 0 | 2025-05 | Monitor
ORD-0012 | PRJ-004 | District Retail | Residential | SUP-05 | Aegean Systems | Greece | CAT-04 | Emergency Lighting | 2025-05-19 09:05 | 2025-05-23 09:05 | 2025-05-25 09:05 | 2025-07-12 09:05 | 2025-07-08 09:05 | 3945 | 2741 | 2025-07-08 09:05 | 2025-08-26 09:05 | 45 | None | Monitor to plan | 1204 | 30.52% | 44 | On Time | 0 | 0 | 49 | Paid | 0 | 2025-05 | Monitor
ORD-0347 | PRJ-009 | Iris Resort | Residential | SUP-08 | Gulf Smart Controls | UAE | CAT-02 | Outdoor Lighting | 2025-05-20 04:03 | 2025-05-25 04:03 | 2025-05-26 04:03 | 2025-06-27 04:03 | 2025-06-21 04:03 | 33109 | 22175 | 2025-06-27 04:03 | 2025-08-02 04:03 | 30 | None | Monitor to plan | 10934 | 33.02% | 26 | On Time | 0 | 0 | 36 | Paid | 0 | 2025-05 | Monitor
ORD-0065 | PRJ-005 | Elm Hospital | Public Sector | SUP-02 | Levant Controls | Lebanon | CAT-03 | Lighting Controls | 2025-05-18 22:51 | 2025-05-23 22:51 | 2025-05-26 22:51 | 2025-06-23 22:51 | 2025-06-21 22:51 | 32043 | 22321 | 2025-06-27 22:51 | 2025-08-11 22:51 | 45 | None | Monitor to plan | 9722 | 30.34% | 26 | On Time | 0 | 0 | 45 | Paid | 0 | 2025-05 | Monitor
ORD-0394 | PRJ-005 | Elm Hospital | Public Sector | SUP-04 | Anatolia Lighting | Turkey | CAT-02 | Outdoor Lighting | 2025-05-22 07:00 | 2025-05-25 07:00 | 2025-05-27 07:00 | 2025-07-02 07:00 | 2025-06-24 07:00 | 16855 | 13014 | 2025-06-25 07:00 | 2025-08-05 07:00 | 45 | None | Monitor to plan | 3841 | 22.79% | 28 | On Time | 0 | 0 | 41 | Paid | 0 | 2025-05 | Monitor
ORD-0122 | PRJ-008 | Harbor Offices | Retail | SUP-04 | Anatolia Lighting | Turkey | CAT-02 | Outdoor Lighting | 2025-05-23 02:48 | 2025-05-27 02:48 | 2025-05-30 02:48 | 2025-07-10 02:48 | 2025-07-15 02:48 | 6630 | 5109 | 2025-07-18 02:48 | 2025-08-23 02:48 | 30 | None | Monitor to plan | 1521 | 22.94% | 46 | Late | 5 | 6630 | 36 | Paid | 0 | 2025-05 | P3
ORD-0345 | PRJ-004 | District Retail | Residential | SUP-11 | Orient Emergency Systems | Malaysia | CAT-01 | Indoor Lighting | 2025-05-11 15:33 | 2025-05-28 15:33 | 2025-05-31 15:33 | 2025-08-07 15:33 | 2025-08-03 15:33 | 35956 | 28717 | 2025-08-06 15:33 | 2025-09-17 15:33 | 45 | Client approval | Confirm decision owner and approval deadline | 7239 | 20.13% | 64 | On Time | 0 | 0 | 42 | Paid | 0 | 2025-05 | Monitor
ORD-0209 | PRJ-001 | Atlas Hotel | Hospitality | SUP-08 | Gulf Smart Controls | UAE | CAT-01 | Indoor Lighting | 2025-05-29 10:46 | 2025-05-30 10:46 | 2025-06-01 10:46 | 2025-07-04 10:46 | 2025-06-28 10:46 | 35526 | 27344 | 2025-07-01 10:46 | 2025-07-31 10:46 | 30 | None | Monitor to plan | 8182 | 23.03% | 27 | On Time | 0 | 0 | 30 | Paid | 0 | 2025-06 | Monitor
ORD-0098 | PRJ-008 | Harbor Offices | Retail | SUP-09 | Pearl LED Works | China | CAT-04 | Emergency Lighting | 2025-05-16 14:25 | 2025-06-05 14:25 | 2025-06-05 14:25 | 2025-08-14 14:25 | 2025-08-13 14:25 | 24527 | 19945 | 2025-08-13 14:25 | 2025-09-18 14:25 | 30 | Client approval | Confirm decision owner and approval deadline | 4582 | 18.68% | 69 | On Time | 0 | 0 | 36 | Paid | 0 | 2025-06 | Monitor
ORD-0359 | PRJ-004 | District Retail | Residential | SUP-02 | Levant Controls | Lebanon | CAT-05 | Architectural Fixtures | 2025-05-22 23:41 | 2025-06-04 23:41 | 2025-06-05 23:41 | 2025-07-06 23:41 | 2025-07-01 23:41 | 24717 | 17206 | 2025-07-07 23:41 | 2025-09-06 23:41 | 60 | Client approval | Confirm decision owner and approval deadline | 7511 | 30.39% | 26 | On Time | 0 | 0 | 61 | Paid | 0 | 2025-06 | Monitor
ORD-0180 | PRJ-005 | Elm Hospital | Public Sector | SUP-05 | Aegean Systems | Greece | CAT-06 | Electrical Accessories | 2025-05-30 16:56 | 2025-06-04 16:56 | 2025-06-07 16:56 | 2025-07-28 16:56 | 2025-07-20 16:56 | 2537 | 1967 | 2025-07-22 16:56 | 2025-08-22 16:56 | 30 | None | Monitor to plan | 570 | 22.47% | 43 | On Time | 0 | 0 | 31 | Paid | 0 | 2025-06 | Monitor
ORD-0336 | PRJ-005 | Elm Hospital | Public Sector | SUP-09 | Pearl LED Works | China | CAT-04 | Emergency Lighting | 2025-06-05 06:56 | 2025-06-10 06:56 | 2025-06-10 06:56 | 2025-08-24 06:56 | 2025-08-19 06:56 | 30956 | 23759 | 2025-08-23 06:56 | 2025-10-18 06:56 | 45 | None | Monitor to plan | 7197 | 23.25% | 70 | On Time | 0 | 0 | 56 | Paid | 0 | 2025-06 | Monitor
ORD-0037 | PRJ-008 | Harbor Offices | Retail | SUP-11 | Orient Emergency Systems | Malaysia | CAT-06 | Electrical Accessories | 2025-06-01 17:54 | 2025-06-07 17:54 | 2025-06-11 17:54 | 2025-08-23 17:54 | 2025-08-19 17:54 | 4182 | 3417 | 2025-08-25 17:54 | 2025-10-30 17:54 | 60 | Payment blocker | Coordinate payment release with finance | 765 | 18.29% | 69 | On Time | 0 | 0 | 66 | Paid | 0 | 2025-06 | Monitor
ORD-0282 | PRJ-010 | Juniper Mall | Public Sector | SUP-08 | Gulf Smart Controls | UAE | CAT-06 | Electrical Accessories | 2025-06-09 04:31 | 2025-06-13 04:31 | 2025-06-14 04:31 | 2025-07-14 04:31 | 2025-07-09 04:31 | 9028 | 6428 | 2025-07-10 04:31 | 2025-08-16 04:31 | 30 | None | Monitor to plan | 2600 | 28.8% | 25 | On Time | 0 | 0 | 37 | Paid | 0 | 2025-06 | Monitor
ORD-0248 | PRJ-003 | Cedar Residence | Retail | SUP-10 | Pacific Fixtures | China | CAT-06 | Electrical Accessories | 2025-06-10 04:00 | 2025-06-15 04:00 | 2025-06-15 04:00 | 2025-09-08 04:00 | 2025-09-11 04:00 | 14979 | 10426 | 2025-09-11 04:00 | 2025-10-30 04:00 | 45 | None | Monitor to plan | 4553 | 30.4% | 88 | Late | 3 | 14979 | 49 | Paid | 0 | 2025-06 | P3
ORD-0393 | PRJ-002 | Beacon Offices | Commercial | SUP-06 | Alpine Illumination | Italy | CAT-05 | Architectural Fixtures | 2025-06-07 16:39 | 2025-06-14 16:39 | 2025-06-17 16:39 | 2025-08-01 16:39 | 2025-08-13 16:39 | 7054 | 5586 | 2025-08-19 16:39 | 2025-10-21 16:39 | 60 | None | Monitor to plan | 1468 | 20.81% | 57 | Late | 12 | 7054 | 63 | Paid | 0 | 2025-06 | P2
ORD-0036 | PRJ-006 | Forum Center | Hospitality | SUP-12 | Atlas Outdoor | Spain | CAT-06 | Electrical Accessories | 2025-06-16 06:05 | 2025-06-18 06:05 | 2025-06-19 06:05 | 2025-08-08 06:05 | 2025-08-07 06:05 | 19091 | 12510 | 2025-08-11 06:05 | 2025-09-10 06:05 | 30 | Documentation | Complete missing document and revalidate order | 6581 | 34.47% | 49 | On Time | 0 | 0 | 30 | Paid | 0 | 2025-06 | Monitor
ORD-0397 | PRJ-005 | Elm Hospital | Public Sector | SUP-05 | Aegean Systems | Greece | CAT-02 | Outdoor Lighting | 2025-06-14 07:35 | 2025-06-17 07:35 | 2025-06-19 07:35 | 2025-08-06 07:35 | 2025-08-05 07:35 | 21019 | 16842 | 2025-08-08 07:35 | 2025-09-22 07:35 | 45 | None | Monitor to plan | 4177 | 19.87% | 47 | On Time | 0 | 0 | 45 | Paid | 0 | 2025-06 | Monitor
ORD-0351 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-11 | Orient Emergency Systems | Malaysia | CAT-03 | Lighting Controls | 2025-06-14 04:46 | 2025-06-17 04:46 | 2025-06-20 04:46 | 2025-08-22 04:46 | 2025-09-14 04:46 | 27826 | 20753 | 2025-09-16 04:46 | 2025-10-18 04:46 | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 7073 | 25.42% | 86 | Late | 23 | 27826 | 32 | Paid | 0 | 2025-06 | P1
ORD-0024 | PRJ-010 | Juniper Mall | Public Sector | SUP-08 | Gulf Smart Controls | UAE | CAT-04 | Emergency Lighting | 2025-06-16 04:50 | 2025-06-20 04:50 | 2025-06-23 04:50 | 2025-07-28 04:50 | 2025-07-23 04:50 | 13996 | 10198 | 2025-07-27 04:50 |  | 30 | None | Monitor to plan | 3798 | 27.14% | 30 | On Time | 0 | 0 | 379.7985 | Overdue | 13996 | 2025-06 | P1
ORD-0297 | PRJ-006 | Forum Center | Hospitality | SUP-04 | Anatolia Lighting | Turkey | CAT-04 | Emergency Lighting | 2025-06-16 13:17 | 2025-06-21 13:17 | 2025-06-23 13:17 | 2025-07-31 13:17 | 2025-07-28 13:17 | 15680 | 11255 | 2025-08-02 13:17 | 2025-09-25 13:17 | 45 | None | Monitor to plan | 4425 | 28.22% | 35 | On Time | 0 | 0 | 54 | Paid | 0 | 2025-06 | Monitor
ORD-0227 | PRJ-006 | Forum Center | Hospitality | SUP-03 | Phoenicia Electrical | Lebanon | CAT-05 | Architectural Fixtures | 2025-06-09 15:51 | 2025-06-23 15:51 | 2025-06-25 15:51 | 2025-07-12 15:51 | 2025-07-04 15:51 | 54202 | 36879 | 2025-07-06 15:51 | 2025-07-26 15:51 | 30 | Client approval | Confirm decision owner and approval deadline | 17323 | 31.96% | 9 | On Time | 0 | 0 | 20 | Paid | 0 | 2025-06 | Monitor
ORD-0042 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-10 | Pacific Fixtures | China | CAT-05 | Architectural Fixtures | 2025-06-21 07:18 | 2025-06-23 07:18 | 2025-06-26 07:18 | 2025-09-16 07:18 | 2025-09-19 07:18 | 23422 | 18042 | 2025-09-19 07:18 | 2025-10-31 07:18 | 45 | Documentation | Complete missing document and revalidate order | 5380 | 22.97% | 85 | Late | 3 | 23422 | 42 | Paid | 0 | 2025-06 | P2
ORD-0181 | PRJ-013 | Meridian Campus | Retail | SUP-02 | Levant Controls | Lebanon | CAT-05 | Architectural Fixtures | 2025-06-25 12:55 | 2025-06-26 12:55 | 2025-06-27 12:55 | 2025-07-28 12:55 | 2025-07-23 12:55 | 11803 | 9377 | 2025-07-28 12:55 | 2025-09-06 12:55 | 45 | None | Monitor to plan | 2426 | 20.55% | 26 | On Time | 0 | 0 | 40 | Paid | 0 | 2025-06 | Monitor
ORD-0304 | PRJ-013 | Meridian Campus | Retail | SUP-04 | Anatolia Lighting | Turkey | CAT-05 | Architectural Fixtures | 2025-06-26 04:25 | 2025-06-28 04:25 | 2025-07-01 04:25 | 2025-08-10 04:25 | 2025-08-10 04:25 | 27322 | 22217 | 2025-08-13 04:25 | 2025-09-17 04:25 | 45 | Documentation | Complete missing document and revalidate order | 5105 | 18.68% | 40 | On Time | 0 | 0 | 35 | Paid | 0 | 2025-07 | Monitor
ORD-0105 | PRJ-006 | Forum Center | Hospitality | SUP-02 | Levant Controls | Lebanon | CAT-05 | Architectural Fixtures | 2025-06-24 13:47 | 2025-06-29 13:47 | 2025-07-03 13:47 | 2025-07-31 13:47 | 2025-08-18 13:47 | 22349 | 16666 | 2025-08-21 13:47 | 2025-10-31 13:47 | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 5683 | 25.43% | 46 | Late | 18 | 22349 | 71 | Paid | 0 | 2025-07 | P1
ORD-0177 | PRJ-005 | Elm Hospital | Public Sector | SUP-02 | Levant Controls | Lebanon | CAT-06 | Electrical Accessories | 2025-06-28 18:48 | 2025-07-03 18:48 | 2025-07-03 18:48 | 2025-07-21 18:48 | 2025-07-21 18:48 | 12016 | 9827 | 2025-07-26 18:48 | 2025-10-08 18:48 | 60 | None | Monitor to plan | 2189 | 18.22% | 18 | On Time | 0 | 0 | 74 | Paid | 0 | 2025-07 | Monitor
ORD-0225 | PRJ-001 | Atlas Hotel | Hospitality | SUP-06 | Alpine Illumination | Italy | CAT-04 | Emergency Lighting | 2025-06-20 08:40 | 2025-07-02 08:40 | 2025-07-04 08:40 | 2025-08-28 08:40 | 2025-08-27 08:40 | 29895 | 20255 | 2025-08-28 08:40 | 2025-10-25 08:40 | 45 | Client approval | Confirm decision owner and approval deadline | 9640 | 32.25% | 54 | On Time | 0 | 0 | 58 | Paid | 0 | 2025-07 | Monitor
ORD-0294 | PRJ-005 | Elm Hospital | Public Sector | SUP-05 | Aegean Systems | Greece | CAT-05 | Architectural Fixtures | 2025-06-23 09:28 | 2025-06-30 09:28 | 2025-07-04 09:28 | 2025-08-11 09:28 | 2025-08-17 09:28 | 40970 | 33261 | 2025-08-23 09:28 |  | 45 | None | Monitor to plan | 7709 | 18.82% | 44 | Late | 6 | 40970 | 352.6055 | Overdue | 40970 | 2025-07 | P1
ORD-0413 | PRJ-010 | Juniper Mall | Public Sector | SUP-08 | Gulf Smart Controls | UAE | CAT-02 | Outdoor Lighting | 2025-06-30 23:22 | 2025-07-03 23:22 | 2025-07-04 23:22 | 2025-08-12 23:22 | 2025-08-10 23:22 | 21029 | 16449 | 2025-08-15 23:22 |  | 45 | None | Monitor to plan | 4580 | 21.78% | 37 | On Time | 0 | 0 | 360.0266 | Overdue | 21029 | 2025-07 | P1
ORD-0009 | PRJ-002 | Beacon Offices | Commercial | SUP-04 | Anatolia Lighting | Turkey | CAT-03 | Lighting Controls | 2025-07-01 12:24 | 2025-07-06 12:24 | 2025-07-07 12:24 | 2025-08-20 12:24 | 2025-08-12 12:24 | 30681 | 20750 | 2025-08-17 12:24 | 2025-10-02 12:24 | 45 | None | Monitor to plan | 9931 | 32.37% | 36 | On Time | 0 | 0 | 46 | Paid | 0 | 2025-07 | Monitor
ORD-0245 | PRJ-006 | Forum Center | Hospitality | SUP-05 | Aegean Systems | Greece | CAT-02 | Outdoor Lighting | 2025-07-05 00:25 | 2025-07-09 00:25 | 2025-07-09 00:25 | 2025-08-26 00:25 | 2025-08-26 00:25 | 11929 | 8203 | 2025-08-29 00:25 | 2025-10-29 00:25 | 60 | None | Monitor to plan | 3726 | 31.23% | 48 | On Time | 0 | 0 | 61 | Paid | 0 | 2025-07 | Monitor
ORD-0189 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-05 | Aegean Systems | Greece | CAT-01 | Indoor Lighting | 2025-07-06 00:53 | 2025-07-12 00:53 | 2025-07-12 00:53 | 2025-08-23 00:53 | 2025-08-21 00:53 | 35336 | 25949 | 2025-08-27 00:53 | 2025-11-06 00:53 | 60 | Documentation | Complete missing document and revalidate order | 9387 | 26.56% | 40 | On Time | 0 | 0 | 71 | Paid | 0 | 2025-07 | Monitor
ORD-0405 | PRJ-015 | Olive Gardens | Public Sector | SUP-06 | Alpine Illumination | Italy | CAT-04 | Emergency Lighting | 2025-07-06 17:33 | 2025-07-13 17:33 | 2025-07-13 17:33 | 2025-09-02 17:33 | 2025-08-25 17:33 | 30287 | 22493 | 2025-08-29 17:33 | 2025-09-26 17:33 | 30 | None | Monitor to plan | 7794 | 25.73% | 43 | On Time | 0 | 0 | 28 | Paid | 0 | 2025-07 | Monitor
ORD-0337 | PRJ-006 | Forum Center | Hospitality | SUP-09 | Pearl LED Works | China | CAT-04 | Emergency Lighting | 2025-07-04 04:35 | 2025-07-10 04:35 | 2025-07-14 04:35 | 2025-09-26 04:35 | 2025-09-26 04:35 | 26406 | 20281 | 2025-09-28 04:35 | 2025-11-06 04:35 | 45 | Documentation | Complete missing document and revalidate order | 6125 | 23.2% | 74 | On Time | 0 | 0 | 39 | Paid | 0 | 2025-07 | Monitor
ORD-0166 | PRJ-002 | Beacon Offices | Commercial | SUP-01 | Cedar Components | Lebanon | CAT-04 | Emergency Lighting | 2025-07-08 14:55 | 2025-07-11 14:55 | 2025-07-14 14:55 | 2025-08-02 14:55 | 2025-07-25 14:55 | 28972 | 23707 | 2025-07-27 14:55 | 2025-08-20 14:55 | 30 | None | Monitor to plan | 5265 | 18.17% | 11 | On Time | 0 | 0 | 24 | Paid | 0 | 2025-07 | Monitor
ORD-0046 | PRJ-009 | Iris Resort | Residential | SUP-04 | Anatolia Lighting | Turkey | CAT-04 | Emergency Lighting | 2025-07-13 11:36 | 2025-07-20 11:36 | 2025-07-22 11:36 | 2025-08-23 11:36 | 2025-08-18 11:36 | 24684 | 17373 | 2025-08-22 11:36 | 2025-09-12 11:36 | 30 | None | Monitor to plan | 7311 | 29.62% | 27 | On Time | 0 | 0 | 21 | Paid | 0 | 2025-07 | Monitor
ORD-0143 | PRJ-006 | Forum Center | Hospitality | SUP-04 | Anatolia Lighting | Turkey | CAT-01 | Indoor Lighting | 2025-07-19 05:16 | 2025-07-20 05:16 | 2025-07-23 05:16 | 2025-08-25 05:16 | 2025-08-19 05:16 | 35935 | 25362 | 2025-08-19 05:16 | 2025-10-01 05:16 | 30 | None | Monitor to plan | 10573 | 29.42% | 27 | On Time | 0 | 0 | 43 | Paid | 0 | 2025-07 | Monitor
ORD-0002 | PRJ-004 | District Retail | Residential | SUP-04 | Anatolia Lighting | Turkey | CAT-01 | Indoor Lighting | 2025-07-18 06:45 | 2025-07-21 06:45 | 2025-07-24 06:45 | 2025-08-27 06:45 | 2025-09-02 06:45 | 8618 | 6704 | 2025-09-05 06:45 | 2025-11-08 06:45 | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 1914 | 22.21% | 40 | Late | 6 | 8618 | 64 | Paid | 0 | 2025-07 | P3
ORD-0203 | PRJ-003 | Cedar Residence | Retail | SUP-12 | Atlas Outdoor | Spain | CAT-05 | Architectural Fixtures | 2025-07-21 09:59 | 2025-07-23 09:59 | 2025-07-24 09:59 | 2025-09-12 09:59 | 2025-09-06 09:59 | 31681 | 21080 | 2025-09-11 09:59 | 2025-11-07 09:59 | 45 | None | Monitor to plan | 10601 | 33.46% | 44 | On Time | 0 | 0 | 57 | Paid | 0 | 2025-07 | Monitor
ORD-0193 | PRJ-003 | Cedar Residence | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-05 | Architectural Fixtures | 2025-07-22 21:46 | 2025-07-24 21:46 | 2025-07-25 21:46 | 2025-08-21 21:46 | 2025-08-17 21:46 | 30853 | 21929 | 2025-08-17 21:46 | 2025-09-29 21:46 | 45 | None | Monitor to plan | 8924 | 28.92% | 23 | On Time | 0 | 0 | 43 | Paid | 0 | 2025-07 | Monitor
ORD-0102 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-02 | Levant Controls | Lebanon | CAT-06 | Electrical Accessories | 2025-07-20 05:44 | 2025-07-22 05:44 | 2025-07-26 05:44 | 2025-08-19 05:44 | 2025-08-26 05:44 | 7861 | 5184 | 2025-09-01 05:44 | 2025-10-07 05:44 | 30 | None | Monitor to plan | 2677 | 34.05% | 31 | Late | 7 | 7861 | 36 | Paid | 0 | 2025-07 | P2
ORD-0240 | PRJ-013 | Meridian Campus | Retail | SUP-08 | Gulf Smart Controls | UAE | CAT-04 | Emergency Lighting | 2025-07-19 18:00 | 2025-07-23 18:00 | 2025-07-26 18:00 | 2025-08-21 18:00 | 2025-08-16 18:00 | 16031 | 12609 | 2025-08-16 18:00 | 2025-09-24 18:00 | 45 | None | Monitor to plan | 3422 | 21.35% | 21 | On Time | 0 | 0 | 39 | Paid | 0 | 2025-07 | Monitor
ORD-0020 | PRJ-008 | Harbor Offices | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-06 | Electrical Accessories | 2025-07-19 17:55 | 2025-07-24 17:55 | 2025-07-27 17:55 | 2025-08-19 17:55 | 2025-09-04 17:55 | 19108 | 13817 | 2025-09-09 17:55 | 2025-11-06 17:55 | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 5291 | 27.69% | 39 | Late | 16 | 19108 | 58 | Paid | 0 | 2025-07 | P1
ORD-0357 | PRJ-005 | Elm Hospital | Public Sector | SUP-08 | Gulf Smart Controls | UAE | CAT-01 | Indoor Lighting | 2025-07-20 00:41 | 2025-07-27 00:41 | 2025-07-28 00:41 | 2025-08-29 00:41 | 2025-08-29 00:41 | 34738 | 24372 | 2025-09-03 00:41 | 2025-11-01 00:41 | 60 | None | Monitor to plan | 10366 | 29.84% | 32 | On Time | 0 | 0 | 59 | Paid | 0 | 2025-07 | Monitor
ORD-0384 | PRJ-006 | Forum Center | Hospitality | SUP-09 | Pearl LED Works | China | CAT-05 | Architectural Fixtures | 2025-07-22 03:48 | 2025-07-28 03:48 | 2025-07-29 03:48 | 2025-10-08 03:48 | 2025-10-06 03:48 | 38637 | 31255 | 2025-10-07 03:48 | 2025-10-27 03:48 | 30 | None | Monitor to plan | 7382 | 19.11% | 69 | On Time | 0 | 0 | 20 | Paid | 0 | 2025-07 | Monitor
ORD-0134 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-08 | Gulf Smart Controls | UAE | CAT-03 | Lighting Controls | 2025-07-23 17:53 | 2025-07-29 17:53 | 2025-07-29 17:53 | 2025-08-24 17:53 | 2025-08-29 17:53 | 33575 | 23683 | 2025-09-02 17:53 | 2025-11-01 17:53 | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 9892 | 29.46% | 31 | Late | 5 | 33575 | 60 | Paid | 0 | 2025-07 | P2
ORD-0117 | PRJ-002 | Beacon Offices | Commercial | SUP-07 | Nordic Beam | Germany | CAT-06 | Electrical Accessories | 2025-07-30 09:35 | 2025-07-31 09:35 | 2025-08-02 09:35 | 2025-09-29 09:35 | 2025-09-30 09:35 | 16281 | 13015 | 2025-10-06 09:35 | 2025-11-02 09:35 | 30 | Payment blocker | Coordinate payment release with finance | 3266 | 20.06% | 59 | Late | 1 | 16281 | 27 | Paid | 0 | 2025-08 | P3
ORD-0088 | PRJ-002 | Beacon Offices | Commercial | SUP-02 | Levant Controls | Lebanon | CAT-04 | Emergency Lighting | 2025-07-28 02:51 | 2025-08-03 02:51 | 2025-08-03 02:51 | 2025-09-04 02:51 | 2025-09-26 02:51 | 8126 | 6243 | 2025-10-01 02:51 | 2025-11-28 02:51 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 1883 | 23.17% | 54 | Late | 22 | 8126 | 58 | Paid | 0 | 2025-08 | P1
ORD-0281 | PRJ-011 | Keystone Residence | Hospitality | SUP-10 | Pacific Fixtures | China | CAT-06 | Electrical Accessories | 2025-08-01 17:57 | 2025-08-02 17:57 | 2025-08-03 17:57 | 2025-10-20 17:57 | 2025-11-07 17:57 | 3377 | 2637 | 2025-11-08 17:57 |  | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 740 | 21.91% | 96 | Late | 18 | 3377 | 275.2518 | Overdue | 3377 | 2025-08 | P1
ORD-0121 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-01 | Cedar Components | Lebanon | CAT-02 | Outdoor Lighting | 2025-07-28 13:31 | 2025-08-03 13:31 | 2025-08-04 13:31 | 2025-08-25 13:31 | 2025-08-21 13:31 | 27964 | 19029 | 2025-08-23 13:31 | 2025-10-02 13:31 | 30 | None | Monitor to plan | 8935 | 31.95% | 17 | On Time | 0 | 0 | 40 | Paid | 0 | 2025-08 | Monitor
ORD-0083 | PRJ-002 | Beacon Offices | Commercial | SUP-04 | Anatolia Lighting | Turkey | CAT-05 | Architectural Fixtures | 2025-07-30 23:04 | 2025-08-03 23:04 | 2025-08-04 23:04 | 2025-09-07 23:04 | 2025-09-07 23:04 | 7024 | 5338 | 2025-09-08 23:04 | 2025-10-15 23:04 | 45 | Shipping / customs | Review freight milestone and customs documents | 1686 | 24% | 34 | On Time | 0 | 0 | 37 | Paid | 0 | 2025-08 | Monitor
ORD-0146 | PRJ-014 | Northgate Complex | Residential | SUP-10 | Pacific Fixtures | China | CAT-04 | Emergency Lighting | 2025-07-27 08:21 | 2025-08-03 08:21 | 2025-08-06 08:21 | 2025-10-23 08:21 | 2025-10-18 08:21 | 26065 | 19417 | 2025-10-20 08:21 | 2025-12-04 08:21 | 45 | None | Monitor to plan | 6648 | 25.51% | 73 | On Time | 0 | 0 | 45 | Paid | 0 | 2025-08 | Monitor
ORD-0355 | PRJ-013 | Meridian Campus | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-02 | Outdoor Lighting | 2025-07-28 09:57 | 2025-08-04 09:57 | 2025-08-06 09:57 | 2025-08-24 09:57 | 2025-08-16 09:57 | 15407 | 11506 | 2025-08-16 09:57 | 2025-09-28 09:57 | 30 | None | Monitor to plan | 3901 | 25.32% | 10 | On Time | 0 | 0 | 43 | Paid | 0 | 2025-08 | Monitor
ORD-0001 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-04 | Anatolia Lighting | Turkey | CAT-06 | Electrical Accessories | 2025-08-02 14:38 | 2025-08-05 14:38 | 2025-08-06 14:38 | 2025-09-11 14:38 | 2025-09-12 14:38 | 24398 | 16661 | 2025-09-16 14:38 | 2025-11-25 14:38 | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 7737 | 31.71% | 37 | Late | 1 | 24398 | 70 | Paid | 0 | 2025-08 | P2
ORD-0123 | PRJ-010 | Juniper Mall | Public Sector | SUP-03 | Phoenicia Electrical | Lebanon | CAT-03 | Lighting Controls | 2025-07-14 15:46 | 2025-08-04 15:46 | 2025-08-08 15:46 | 2025-08-24 15:46 | 2025-08-18 15:46 | 21803 | 16177 | 2025-08-20 15:46 | 2025-10-05 15:46 | 45 | Client approval | Confirm decision owner and approval deadline | 5626 | 25.8% | 10 | On Time | 0 | 0 | 46 | Paid | 0 | 2025-08 | Monitor
ORD-0129 | PRJ-011 | Keystone Residence | Hospitality | SUP-11 | Orient Emergency Systems | Malaysia | CAT-06 | Electrical Accessories | 2025-08-07 18:04 | 2025-08-08 18:04 | 2025-08-08 18:04 | 2025-10-12 18:04 | 2025-10-05 18:04 | 19354 | 15816 | 2025-10-11 18:04 | 2025-11-27 18:04 | 45 | None | Monitor to plan | 3538 | 18.28% | 58 | On Time | 0 | 0 | 47 | Paid | 0 | 2025-08 | Monitor
ORD-0053 | PRJ-010 | Juniper Mall | Public Sector | SUP-08 | Gulf Smart Controls | UAE | CAT-04 | Emergency Lighting | 2025-08-02 15:11 | 2025-08-05 15:11 | 2025-08-09 15:11 | 2025-09-04 15:11 | 2025-09-12 15:11 | 19346 | 14671 | 2025-09-16 15:11 | 2025-11-04 15:11 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 4675 | 24.17% | 34 | Late | 8 | 19346 | 49 | Paid | 0 | 2025-08 | P2
ORD-0331 | PRJ-003 | Cedar Residence | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-05 | Architectural Fixtures | 2025-07-27 17:19 | 2025-08-11 17:19 | 2025-08-12 17:19 | 2025-08-28 17:19 | 2025-08-25 17:19 | 56739 | 45315 | 2025-08-30 17:19 |  | 45 | Client approval | Confirm decision owner and approval deadline | 11424 | 20.13% | 13 | On Time | 0 | 0 | 345.2785 | Overdue | 56739 | 2025-08 | P1
ORD-0379 | PRJ-006 | Forum Center | Hospitality | SUP-10 | Pacific Fixtures | China | CAT-04 | Emergency Lighting | 2025-08-08 01:15 | 2025-08-14 01:15 | 2025-08-14 01:15 | 2025-10-26 01:15 | 2025-10-26 01:15 | 28457 | 20694 | 2025-11-01 01:15 |  | 45 | Payment blocker | Coordinate payment release with finance | 7763 | 27.28% | 73 | On Time | 0 | 0 | 282.948 | Overdue | 28457 | 2025-08 | P1
ORD-0078 | PRJ-010 | Juniper Mall | Public Sector | SUP-06 | Alpine Illumination | Italy | CAT-04 | Emergency Lighting | 2025-08-07 05:36 | 2025-08-13 05:36 | 2025-08-15 05:36 | 2025-10-03 05:36 | 2025-09-25 05:36 | 14076 | 10985 | 2025-09-26 05:36 | 2025-10-28 05:36 | 30 | None | Monitor to plan | 3091 | 21.96% | 41 | On Time | 0 | 0 | 32 | Paid | 0 | 2025-08 | Monitor
ORD-0058 | PRJ-009 | Iris Resort | Residential | SUP-08 | Gulf Smart Controls | UAE | CAT-02 | Outdoor Lighting | 2025-08-09 02:38 | 2025-08-16 02:38 | 2025-08-18 02:38 | 2025-09-20 02:38 | 2025-09-16 02:38 | 9026 | 6731 | 2025-09-20 02:38 | 2025-10-25 02:38 | 45 | None | Monitor to plan | 2295 | 25.43% | 29 | On Time | 0 | 0 | 35 | Paid | 0 | 2025-08 | Monitor
ORD-0208 | PRJ-005 | Elm Hospital | Public Sector | SUP-03 | Phoenicia Electrical | Lebanon | CAT-03 | Lighting Controls | 2025-08-11 03:37 | 2025-08-16 03:37 | 2025-08-18 03:37 | 2025-09-14 03:37 | 2025-09-07 03:37 | 24549 | 19393 | 2025-09-08 03:37 | 2025-10-22 03:37 | 45 | None | Monitor to plan | 5156 | 21% | 20 | On Time | 0 | 0 | 44 | Paid | 0 | 2025-08 | Monitor
ORD-0305 | PRJ-005 | Elm Hospital | Public Sector | SUP-04 | Anatolia Lighting | Turkey | CAT-01 | Indoor Lighting | 2025-08-14 08:59 | 2025-08-18 08:59 | 2025-08-19 08:59 | 2025-09-25 08:59 | 2025-10-11 08:59 | 25885 | 20881 | 2025-10-13 08:59 | 2025-12-03 08:59 | 60 | Shipping / customs | Review freight milestone and customs documents | 5004 | 19.33% | 53 | Late | 16 | 25885 | 51 | Paid | 0 | 2025-08 | P1
ORD-0287 | PRJ-015 | Olive Gardens | Public Sector | SUP-05 | Aegean Systems | Greece | CAT-02 | Outdoor Lighting | 2025-08-13 13:57 | 2025-08-16 13:57 | 2025-08-20 13:57 | 2025-09-30 13:57 | 2025-10-18 13:57 | 44466 | 31280 | 2025-10-23 13:57 | 2025-12-29 13:57 | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 13186 | 29.65% | 59 | Late | 18 | 44466 | 67 | Paid | 0 | 2025-08 | P1
ORD-0071 | PRJ-006 | Forum Center | Hospitality | SUP-08 | Gulf Smart Controls | UAE | CAT-03 | Lighting Controls | 2025-08-02 08:16 | 2025-08-20 08:16 | 2025-08-21 08:16 | 2025-09-18 08:16 | 2025-09-10 08:16 | 7353 | 4787 | 2025-09-15 08:16 | 2025-11-02 08:16 | 45 | Client approval | Confirm decision owner and approval deadline | 2566 | 34.9% | 20 | On Time | 0 | 0 | 48 | Paid | 0 | 2025-08 | Monitor
ORD-0069 | PRJ-002 | Beacon Offices | Commercial | SUP-12 | Atlas Outdoor | Spain | CAT-01 | Indoor Lighting | 2025-08-17 10:46 | 2025-08-18 10:46 | 2025-08-22 10:46 | 2025-10-17 10:46 | 2025-10-09 10:46 | 26038 | 18245 | 2025-10-12 10:46 | 2025-12-19 10:46 | 60 | None | Monitor to plan | 7793 | 29.93% | 48 | On Time | 0 | 0 | 68 | Paid | 0 | 2025-08 | Monitor
ORD-0312 | PRJ-014 | Northgate Complex | Residential | SUP-10 | Pacific Fixtures | China | CAT-05 | Architectural Fixtures | 2025-08-11 09:04 | 2025-08-21 09:04 | 2025-08-25 09:04 | 2025-11-08 09:04 | 2025-11-17 09:04 | 29344 | 23103 | 2025-11-17 09:04 | 2026-01-05 09:04 | 45 | Client approval | Confirm decision owner and approval deadline | 6241 | 21.27% | 84 | Late | 9 | 29344 | 49 | Paid | 0 | 2025-08 | P2
ORD-0271 | PRJ-008 | Harbor Offices | Retail | SUP-01 | Cedar Components | Lebanon | CAT-02 | Outdoor Lighting | 2025-08-19 07:56 | 2025-08-24 07:56 | 2025-08-27 07:56 | 2025-09-16 07:56 | 2025-09-14 07:56 | 35788 | 27164 | 2025-09-19 07:56 | 2025-11-13 07:56 | 60 | None | Monitor to plan | 8624 | 24.1% | 18 | On Time | 0 | 0 | 55 | Paid | 0 | 2025-08 | Monitor
ORD-0342 | PRJ-008 | Harbor Offices | Retail | SUP-06 | Alpine Illumination | Italy | CAT-02 | Outdoor Lighting | 2025-08-20 22:18 | 2025-08-24 22:18 | 2025-08-27 22:18 | 2025-10-23 22:18 | 2025-11-05 22:18 | 23426 | 15500 | 2025-11-10 22:18 | 2026-01-16 22:18 | 60 | Shipping / customs | Review freight milestone and customs documents | 7926 | 33.83% | 70 | Late | 13 | 23426 | 67 | Paid | 0 | 2025-08 | P2
ORD-0090 | PRJ-007 | Garden Villas | Commercial | SUP-12 | Atlas Outdoor | Spain | CAT-05 | Architectural Fixtures | 2025-08-21 15:16 | 2025-08-28 15:16 | 2025-08-28 15:16 | 2025-10-21 15:16 | 2025-11-10 15:16 | 44725 | 35815 | 2025-11-12 15:16 | 2026-01-10 15:16 | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 8910 | 19.92% | 74 | Late | 20 | 44725 | 59 | Paid | 0 | 2025-08 | P1
ORD-0148 | PRJ-005 | Elm Hospital | Public Sector | SUP-06 | Alpine Illumination | Italy | CAT-05 | Architectural Fixtures | 2025-08-21 17:00 | 2025-08-28 17:00 | 2025-08-29 17:00 | 2025-10-16 17:00 | 2025-10-09 17:00 | 17207 | 12687 | 2025-10-12 17:00 | 2025-12-11 17:00 | 60 | None | Monitor to plan | 4520 | 26.27% | 41 | On Time | 0 | 0 | 60 | Paid | 0 | 2025-08 | Monitor
ORD-0097 | PRJ-008 | Harbor Offices | Retail | SUP-05 | Aegean Systems | Greece | CAT-05 | Architectural Fixtures | 2025-08-22 06:50 | 2025-08-27 06:50 | 2025-08-31 06:50 | 2025-10-16 06:50 | 2025-10-15 06:50 | 29165 | 19322 | 2025-10-20 06:50 | 2025-12-21 06:50 | 60 | None | Monitor to plan | 9843 | 33.75% | 45 | On Time | 0 | 0 | 62 | Paid | 0 | 2025-08 | Monitor
ORD-0338 | PRJ-011 | Keystone Residence | Hospitality | SUP-06 | Alpine Illumination | Italy | CAT-04 | Emergency Lighting | 2025-08-30 08:47 | 2025-09-04 08:47 | 2025-09-04 08:47 | 2025-10-30 08:47 | 2025-10-24 08:47 | 16116 | 10638 | 2025-10-27 08:47 |  | 60 | None | Monitor to plan | 5478 | 33.99% | 50 | On Time | 0 | 0 | 287.634 | Overdue | 16116 | 2025-09 | P1
ORD-0206 | PRJ-002 | Beacon Offices | Commercial | SUP-12 | Atlas Outdoor | Spain | CAT-01 | Indoor Lighting | 2025-08-30 15:12 | 2025-09-04 15:12 | 2025-09-06 15:12 | 2025-11-05 15:12 | 2025-10-28 15:12 | 20681 | 14768 | 2025-10-31 15:12 | 2025-11-23 15:12 | 30 | None | Monitor to plan | 5913 | 28.59% | 52 | On Time | 0 | 0 | 23 | Paid | 0 | 2025-09 | Monitor
ORD-0319 | PRJ-003 | Cedar Residence | Retail | SUP-07 | Nordic Beam | Germany | CAT-04 | Emergency Lighting | 2025-08-31 09:34 | 2025-09-07 09:34 | 2025-09-08 09:34 | 2025-11-04 09:34 | 2025-10-30 09:34 | 19406 | 15559 | 2025-11-02 09:34 | 2025-11-25 09:34 | 30 | None | Monitor to plan | 3847 | 19.82% | 52 | On Time | 0 | 0 | 23 | Paid | 0 | 2025-09 | Monitor
ORD-0400 | PRJ-007 | Garden Villas | Commercial | SUP-12 | Atlas Outdoor | Spain | CAT-04 | Emergency Lighting | 2025-09-03 13:10 | 2025-09-08 13:10 | 2025-09-09 13:10 | 2025-11-05 13:10 | 2025-11-21 13:10 | 23930 | 17700 | 2025-11-22 13:10 | 2025-12-31 13:10 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 6230 | 26.03% | 73 | Late | 16 | 23930 | 39 | Paid | 0 | 2025-09 | P1
ORD-0407 | PRJ-011 | Keystone Residence | Hospitality | SUP-05 | Aegean Systems | Greece | CAT-03 | Lighting Controls | 2025-09-06 01:24 | 2025-09-10 01:24 | 2025-09-12 01:24 | 2025-10-29 01:24 | 2025-10-25 01:24 | 33915 | 26681 | 2025-10-31 01:24 | 2025-12-07 01:24 | 30 | None | Monitor to plan | 7234 | 21.33% | 43 | On Time | 0 | 0 | 37 | Paid | 0 | 2025-09 | Monitor
ORD-0008 | PRJ-011 | Keystone Residence | Hospitality | SUP-11 | Orient Emergency Systems | Malaysia | CAT-02 | Outdoor Lighting | 2025-08-22 10:45 | 2025-09-09 10:45 | 2025-09-13 10:45 | 2025-11-23 10:45 | 2025-11-16 10:45 | 26682 | 19024 | 2025-11-21 10:45 | 2025-12-24 10:45 | 30 | Client approval | Confirm decision owner and approval deadline | 7658 | 28.7% | 64 | On Time | 0 | 0 | 33 | Paid | 0 | 2025-09 | Monitor
ORD-0025 | PRJ-013 | Meridian Campus | Retail | SUP-06 | Alpine Illumination | Italy | CAT-06 | Electrical Accessories | 2025-09-08 20:49 | 2025-09-09 20:49 | 2025-09-13 20:49 | 2025-11-08 20:49 | 2025-11-03 20:49 | 16784 | 13072 | 2025-11-08 20:49 | 2026-01-02 20:49 | 45 | None | Monitor to plan | 3712 | 22.12% | 51 | On Time | 0 | 0 | 55 | Paid | 0 | 2025-09 | Monitor
ORD-0168 | PRJ-008 | Harbor Offices | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-04 | Emergency Lighting | 2025-09-07 02:30 | 2025-09-11 02:30 | 2025-09-14 02:30 | 2025-10-13 02:30 | 2025-10-12 02:30 | 7707 | 6044 | 2025-10-16 02:30 |  | 45 | None | Monitor to plan | 1663 | 21.58% | 28 | On Time | 0 | 0 | 298.8955 | Overdue | 7707 | 2025-09 | P1
ORD-0057 | PRJ-001 | Atlas Hotel | Hospitality | SUP-04 | Anatolia Lighting | Turkey | CAT-06 | Electrical Accessories | 2025-09-08 17:21 | 2025-09-13 17:21 | 2025-09-14 17:21 | 2025-10-18 17:21 | 2025-10-30 17:21 | 19128 | 14684 | 2025-11-03 17:21 | 2025-12-08 17:21 | 45 | None | Monitor to plan | 4444 | 23.23% | 46 | Late | 12 | 19128 | 35 | Paid | 0 | 2025-09 | P2
ORD-0343 | PRJ-010 | Juniper Mall | Public Sector | SUP-06 | Alpine Illumination | Italy | CAT-02 | Outdoor Lighting | 2025-09-08 06:24 | 2025-09-11 06:24 | 2025-09-15 06:24 | 2025-10-30 06:24 | 2025-10-26 06:24 | 25219 | 17250 | 2025-10-28 06:24 | 2025-12-04 06:24 | 45 | None | Monitor to plan | 7969 | 31.6% | 41 | On Time | 0 | 0 | 37 | Paid | 0 | 2025-09 | Monitor
ORD-0383 | PRJ-007 | Garden Villas | Commercial | SUP-10 | Pacific Fixtures | China | CAT-02 | Outdoor Lighting | 2025-09-12 17:12 | 2025-09-13 17:12 | 2025-09-15 17:12 | 2025-12-06 17:12 | 2025-12-02 17:12 | 24790 | 17635 | 2025-12-03 17:12 | 2026-01-08 17:12 | 30 | None | Monitor to plan | 7155 | 28.86% | 78 | On Time | 0 | 0 | 36 | Paid | 0 | 2025-09 | Monitor
ORD-0218 | PRJ-015 | Olive Gardens | Public Sector | SUP-10 | Pacific Fixtures | China | CAT-05 | Architectural Fixtures | 2025-09-13 12:17 | 2025-09-15 12:17 | 2025-09-16 12:17 | 2025-12-04 12:17 | 2025-12-20 12:17 | 35209 | 23278 | 2025-12-22 12:17 | 2026-02-22 12:17 | 60 | None | Monitor to plan | 11931 | 33.89% | 95 | Late | 16 | 35209 | 62 | Paid | 0 | 2025-09 | P1
ORD-0307 | PRJ-009 | Iris Resort | Residential | SUP-07 | Nordic Beam | Germany | CAT-01 | Indoor Lighting | 2025-09-15 03:28 | 2025-09-17 03:28 | 2025-09-18 03:28 | 2025-11-10 03:28 | 2025-11-06 03:28 | 29943 | 22140 | 2025-11-08 03:28 | 2025-12-16 03:28 | 45 | None | Monitor to plan | 7803 | 26.06% | 49 | On Time | 0 | 0 | 38 | Paid | 0 | 2025-09 | Monitor
ORD-0381 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-11 | Orient Emergency Systems | Malaysia | CAT-02 | Outdoor Lighting | 2025-09-11 07:42 | 2025-09-18 07:42 | 2025-09-19 07:42 | 2025-12-01 07:42 | 2025-11-30 07:42 | 37624 | 28736 | 2025-12-05 07:42 | 2026-01-10 07:42 | 30 | None | Monitor to plan | 8888 | 23.62% | 72 | On Time | 0 | 0 | 36 | Paid | 0 | 2025-09 | Monitor
ORD-0073 | PRJ-014 | Northgate Complex | Residential | SUP-07 | Nordic Beam | Germany | CAT-03 | Lighting Controls | 2025-09-18 08:41 | 2025-09-19 08:41 | 2025-09-19 08:41 | 2025-11-17 08:41 | 2025-11-16 08:41 | 35352 | 28435 | 2025-11-18 08:41 | 2026-01-16 08:41 | 45 | None | Monitor to plan | 6917 | 19.57% | 58 | On Time | 0 | 0 | 59 | Paid | 0 | 2025-09 | Monitor
ORD-0095 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-01 | Cedar Components | Lebanon | CAT-03 | Lighting Controls | 2025-09-17 09:51 | 2025-09-24 09:51 | 2025-09-25 09:51 | 2025-10-08 09:51 | 2025-10-05 09:51 | 5086 | 4015 | 2025-10-05 09:51 |  | 30 | None | Monitor to plan | 1071 | 21.06% | 10 | On Time | 0 | 0 | 309.5898 | Overdue | 5086 | 2025-09 | P1
ORD-0316 | PRJ-001 | Atlas Hotel | Hospitality | SUP-02 | Levant Controls | Lebanon | CAT-03 | Lighting Controls | 2025-09-17 00:46 | 2025-09-22 00:46 | 2025-09-26 00:46 | 2025-10-27 00:46 | 2025-10-23 00:46 | 7432 | 4991 | 2025-10-27 00:46 | 2025-12-03 00:46 | 45 | None | Monitor to plan | 2441 | 32.84% | 27 | On Time | 0 | 0 | 37 | Paid | 0 | 2025-09 | Monitor
ORD-0268 | PRJ-014 | Northgate Complex | Residential | SUP-07 | Nordic Beam | Germany | CAT-05 | Architectural Fixtures | 2025-09-25 15:34 | 2025-09-26 15:34 | 2025-09-27 15:34 | 2025-11-19 15:34 | 2025-11-19 15:34 | 24901 | 20047 | 2025-11-25 15:34 | 2026-01-20 15:34 | 60 | None | Monitor to plan | 4854 | 19.49% | 53 | On Time | 0 | 0 | 56 | Paid | 0 | 2025-09 | Monitor
ORD-0155 | PRJ-007 | Garden Villas | Commercial | SUP-05 | Aegean Systems | Greece | CAT-03 | Lighting Controls | 2025-09-24 16:15 | 2025-09-30 16:15 | 2025-09-30 16:15 | 2025-11-08 16:15 | 2025-11-08 16:15 | 23438 | 17571 | 2025-11-11 16:15 | 2025-12-06 16:15 | 30 | None | Monitor to plan | 5867 | 25.03% | 39 | On Time | 0 | 0 | 25 | Paid | 0 | 2025-09 | Monitor
ORD-0035 | PRJ-014 | Northgate Complex | Residential | SUP-04 | Anatolia Lighting | Turkey | CAT-04 | Emergency Lighting | 2025-09-27 04:24 | 2025-09-29 04:24 | 2025-10-01 04:24 | 2025-11-06 04:24 | 2025-11-15 04:24 | 20237 | 14581 | 2025-11-15 04:24 | 2026-01-05 04:24 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 5656 | 27.95% | 45 | Late | 9 | 20237 | 51 | Paid | 0 | 2025-10 | P2
ORD-0386 | PRJ-002 | Beacon Offices | Commercial | SUP-02 | Levant Controls | Lebanon | CAT-04 | Emergency Lighting | 2025-09-22 15:31 | 2025-09-29 15:31 | 2025-10-03 15:31 | 2025-11-02 15:31 | 2025-10-30 15:31 | 13173 | 8636 | 2025-11-01 15:31 | 2025-12-08 15:31 | 45 | None | Monitor to plan | 4537 | 34.44% | 27 | On Time | 0 | 0 | 37 | Paid | 0 | 2025-10 | Monitor
ORD-0094 | PRJ-010 | Juniper Mall | Public Sector | SUP-05 | Aegean Systems | Greece | CAT-06 | Electrical Accessories | 2025-09-29 13:07 | 2025-10-06 13:07 | 2025-10-07 13:07 | 2025-11-21 13:07 | 2025-11-19 13:07 | 12171 | 8472 | 2025-11-19 13:07 | 2025-12-17 13:07 | 30 | None | Monitor to plan | 3699 | 30.39% | 43 | On Time | 0 | 0 | 28 | Paid | 0 | 2025-10 | Monitor
ORD-0264 | PRJ-011 | Keystone Residence | Hospitality | SUP-07 | Nordic Beam | Germany | CAT-05 | Architectural Fixtures | 2025-09-15 21:36 | 2025-10-09 21:36 | 2025-10-11 21:36 | 2025-12-12 21:36 | 2025-12-07 21:36 | 40920 | 29438 | 2025-12-13 21:36 | 2026-01-29 21:36 | 45 | Client approval | Confirm decision owner and approval deadline | 11482 | 28.06% | 57 | On Time | 0 | 0 | 47 | Paid | 0 | 2025-10 | Monitor
ORD-0079 | PRJ-003 | Cedar Residence | Retail | SUP-06 | Alpine Illumination | Italy | CAT-06 | Electrical Accessories | 2025-10-12 06:40 | 2025-10-13 06:40 | 2025-10-15 06:40 | 2025-12-01 06:40 | 2025-12-14 06:40 | 15278 | 10369 | 2025-12-18 06:40 | 2026-02-24 06:40 | 60 | Shipping / customs | Review freight milestone and customs documents | 4909 | 32.13% | 60 | Late | 13 | 15278 | 68 | Paid | 0 | 2025-10 | P2
ORD-0417 | PRJ-015 | Olive Gardens | Public Sector | SUP-10 | Pacific Fixtures | China | CAT-03 | Lighting Controls | 2025-10-10 13:57 | 2025-10-11 13:57 | 2025-10-15 13:57 | 2026-01-04 13:57 | 2026-01-03 13:57 | 11311 | 8217 | 2026-01-09 13:57 | 2026-03-15 13:57 | 60 | None | Monitor to plan | 3094 | 27.35% | 80 | On Time | 0 | 0 | 65 | Paid | 0 | 2025-10 | Monitor
ORD-0150 | PRJ-004 | District Retail | Residential | SUP-02 | Levant Controls | Lebanon | CAT-02 | Outdoor Lighting | 2025-10-08 17:34 | 2025-10-12 17:34 | 2025-10-15 17:34 | 2025-11-11 17:34 | 2025-11-13 17:34 | 13008 | 9873 | 2025-11-16 17:34 |  | 45 | Payment blocker | Coordinate payment release with finance | 3135 | 24.1% | 29 | Late | 2 | 13008 | 267.2681 | Overdue | 13008 | 2025-10 | P1
ORD-0007 | PRJ-004 | District Retail | Residential | SUP-08 | Gulf Smart Controls | UAE | CAT-06 | Electrical Accessories | 2025-10-13 00:48 | 2025-10-15 00:48 | 2025-10-16 00:48 | 2025-11-14 00:48 | 2025-11-10 00:48 | 5561 | 4273 | 2025-11-11 00:48 |  | 60 | Documentation | Complete missing document and revalidate order | 1288 | 23.16% | 25 | On Time | 0 | 0 | 272.9668 | Overdue | 5561 | 2025-10 | P1
ORD-0212 | PRJ-006 | Forum Center | Hospitality | SUP-12 | Atlas Outdoor | Spain | CAT-06 | Electrical Accessories | 2025-10-15 09:55 | 2025-10-17 09:55 | 2025-10-17 09:55 | 2025-12-03 09:55 | 2025-12-01 09:55 | 15259 | 11125 | 2025-12-04 09:55 | 2026-01-29 09:55 | 45 | None | Monitor to plan | 4134 | 27.09% | 45 | On Time | 0 | 0 | 56 | Paid | 0 | 2025-10 | Monitor
ORD-0366 | PRJ-015 | Olive Gardens | Public Sector | SUP-06 | Alpine Illumination | Italy | CAT-05 | Architectural Fixtures | 2025-10-10 14:18 | 2025-10-15 14:18 | 2025-10-17 14:18 | 2025-12-08 14:18 | 2025-12-29 14:18 | 34504 | 25183 | 2026-01-01 14:18 | 2026-02-05 14:18 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 9321 | 27.01% | 73 | Late | 21 | 34504 | 35 | Paid | 0 | 2025-10 | P1
ORD-0330 | PRJ-009 | Iris Resort | Residential | SUP-01 | Cedar Components | Lebanon | CAT-06 | Electrical Accessories | 2025-10-14 23:11 | 2025-10-17 23:11 | 2025-10-17 23:11 | 2025-11-05 23:11 | 2025-10-30 23:11 | 8939 | 6787 | 2025-11-03 23:11 |  | 60 | None | Monitor to plan | 2152 | 24.07% | 13 | On Time | 0 | 0 | 280.0341 | Overdue | 8939 | 2025-10 | P1
ORD-0187 | PRJ-004 | District Retail | Residential | SUP-11 | Orient Emergency Systems | Malaysia | CAT-03 | Lighting Controls | 2025-10-09 15:20 | 2025-10-16 15:20 | 2025-10-18 15:20 | 2025-12-21 15:20 | 2025-12-20 15:20 | 13121 | 9071 | 2025-12-26 15:20 | 2026-02-03 15:20 | 45 | None | Monitor to plan | 4050 | 30.87% | 63 | On Time | 0 | 0 | 39 | Paid | 0 | 2025-10 | Monitor
ORD-0010 | PRJ-010 | Juniper Mall | Public Sector | SUP-04 | Anatolia Lighting | Turkey | CAT-04 | Emergency Lighting | 2025-10-10 07:51 | 2025-10-17 07:51 | 2025-10-21 07:51 | 2025-12-05 07:51 | 2025-12-30 07:51 | 18669 | 13217 | 2026-01-05 07:51 | 2026-01-30 07:51 | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 5452 | 29.2% | 70 | Late | 25 | 18669 | 25 | Paid | 0 | 2025-10 | P1
ORD-0327 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-08 | Gulf Smart Controls | UAE | CAT-03 | Lighting Controls | 2025-10-15 12:21 | 2025-10-20 12:21 | 2025-10-23 12:21 | 2025-12-02 12:21 | 2025-12-05 12:21 | 24753 | 16176 | 2025-12-06 12:21 | 2026-01-13 12:21 | 30 | Payment blocker | Coordinate payment release with finance | 8577 | 34.65% | 43 | Late | 3 | 24753 | 38 | Paid | 0 | 2025-10 | P2
ORD-0239 | PRJ-004 | District Retail | Residential | SUP-04 | Anatolia Lighting | Turkey | CAT-05 | Architectural Fixtures | 2025-10-20 04:24 | 2025-10-22 04:24 | 2025-10-24 04:24 | 2025-12-08 04:24 | 2025-12-08 04:24 | 17209 | 11672 | 2025-12-11 04:24 |  | 30 | None | Monitor to plan | 5537 | 32.18% | 45 | On Time | 0 | 0 | 242.8168 | Overdue | 17209 | 2025-10 | P1
ORD-0156 | PRJ-013 | Meridian Campus | Retail | SUP-10 | Pacific Fixtures | China | CAT-01 | Indoor Lighting | 2025-10-23 12:45 | 2025-10-24 12:45 | 2025-10-24 12:45 | 2026-01-15 12:45 | 2026-02-01 12:45 | 24217 | 19491 | 2026-02-05 12:45 | 2026-03-07 12:45 | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 4726 | 19.52% | 100 | Late | 17 | 24217 | 30 | Paid | 0 | 2025-10 | P1
ORD-0303 | PRJ-002 | Beacon Offices | Commercial | SUP-12 | Atlas Outdoor | Spain | CAT-01 | Indoor Lighting | 2025-10-20 15:16 | 2025-10-24 15:16 | 2025-10-26 15:16 | 2025-12-18 15:16 | 2025-12-18 15:16 | 36594 | 26090 | 2025-12-23 15:16 | 2026-02-21 15:16 | 60 | None | Monitor to plan | 10504 | 28.7% | 53 | On Time | 0 | 0 | 60 | Paid | 0 | 2025-10 | Monitor
ORD-0378 | PRJ-001 | Atlas Hotel | Hospitality | SUP-06 | Alpine Illumination | Italy | CAT-05 | Architectural Fixtures | 2025-10-21 10:38 | 2025-10-28 10:38 | 2025-10-28 10:38 | 2025-12-21 10:38 | 2025-12-17 10:38 | 11552 | 9186 | 2025-12-17 10:38 | 2026-01-30 10:38 | 45 | None | Monitor to plan | 2366 | 20.48% | 50 | On Time | 0 | 0 | 44 | Paid | 0 | 2025-10 | Monitor
ORD-0147 | PRJ-013 | Meridian Campus | Retail | SUP-06 | Alpine Illumination | Italy | CAT-02 | Outdoor Lighting | 2025-10-21 18:54 | 2025-10-27 18:54 | 2025-10-29 18:54 | 2025-12-25 18:54 | 2025-12-18 18:54 | 30062 | 21736 | 2025-12-23 18:54 | 2026-01-22 18:54 | 30 | None | Monitor to plan | 8326 | 27.7% | 50 | On Time | 0 | 0 | 30 | Paid | 0 | 2025-10 | Monitor
ORD-0222 | PRJ-014 | Northgate Complex | Residential | SUP-05 | Aegean Systems | Greece | CAT-04 | Emergency Lighting | 2025-10-23 02:00 | 2025-10-27 02:00 | 2025-10-30 02:00 | 2025-12-10 02:00 | 2025-12-02 02:00 | 31050 | 23708 | 2025-12-04 02:00 |  | 45 | None | Monitor to plan | 7342 | 23.65% | 33 | On Time | 0 | 0 | 249.9165 | Overdue | 31050 | 2025-10 | P1
ORD-0141 | PRJ-010 | Juniper Mall | Public Sector | SUP-11 | Orient Emergency Systems | Malaysia | CAT-04 | Emergency Lighting | 2025-10-25 21:14 | 2025-10-29 21:14 | 2025-10-31 21:14 | 2026-01-04 21:14 | 2026-01-16 21:14 | 24271 | 18916 | 2026-01-19 21:14 | 2026-02-25 21:14 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 5355 | 22.06% | 77 | Late | 12 | 24271 | 37 | Paid | 0 | 2025-10 | P2
ORD-0411 | PRJ-006 | Forum Center | Hospitality | SUP-03 | Phoenicia Electrical | Lebanon | CAT-01 | Indoor Lighting | 2025-10-09 00:13 | 2025-11-01 00:13 | 2025-11-01 00:13 | 2025-11-25 00:13 | 2025-11-20 00:13 | 15113 | 11897 | 2025-11-23 00:13 | 2026-01-05 00:13 | 30 | Client approval | Confirm decision owner and approval deadline | 3216 | 21.28% | 19 | On Time | 0 | 0 | 43 | Paid | 0 | 2025-11 | Monitor
ORD-0270 | PRJ-015 | Olive Gardens | Public Sector | SUP-03 | Phoenicia Electrical | Lebanon | CAT-01 | Indoor Lighting | 2025-10-28 19:02 | 2025-10-30 19:02 | 2025-11-03 19:02 | 2025-11-20 19:02 | 2025-12-06 19:02 | 40940 | 29884 | 2025-12-07 19:02 | 2026-01-30 19:02 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 11056 | 27.01% | 33 | Late | 16 | 40940 | 54 | Paid | 0 | 2025-11 | P1
ORD-0223 | PRJ-004 | District Retail | Residential | SUP-10 | Pacific Fixtures | China | CAT-05 | Architectural Fixtures | 2025-10-29 21:35 | 2025-11-01 21:35 | 2025-11-04 21:35 | 2026-01-19 21:35 | 2026-01-19 21:35 | 23658 | 17507 | 2026-01-20 21:35 | 2026-03-03 21:35 | 45 | None | Monitor to plan | 6151 | 26% | 76 | On Time | 0 | 0 | 42 | Paid | 0 | 2025-11 | Monitor
ORD-0352 | PRJ-009 | Iris Resort | Residential | SUP-01 | Cedar Components | Lebanon | CAT-06 | Electrical Accessories | 2025-10-28 23:03 | 2025-11-01 23:03 | 2025-11-04 23:03 | 2025-11-21 23:03 | 2025-11-29 23:03 | 23035 | 16804 | 2025-12-03 23:03 | 2025-12-25 23:03 | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 6231 | 27.05% | 25 | Late | 8 | 23035 | 22 | Paid | 0 | 2025-11 | P2
ORD-0202 | PRJ-011 | Keystone Residence | Hospitality | SUP-07 | Nordic Beam | Germany | CAT-01 | Indoor Lighting | 2025-10-30 09:28 | 2025-11-01 09:28 | 2025-11-05 09:28 | 2026-01-01 09:28 | 2025-12-27 09:28 | 17054 | 12903 | 2025-12-27 09:28 | 2026-02-01 09:28 | 45 | None | Monitor to plan | 4151 | 24.34% | 52 | On Time | 0 | 0 | 36 | Paid | 0 | 2025-11 | Monitor
ORD-0314 | PRJ-015 | Olive Gardens | Public Sector | SUP-03 | Phoenicia Electrical | Lebanon | CAT-03 | Lighting Controls | 2025-10-28 15:00 | 2025-11-02 15:00 | 2025-11-05 15:00 | 2025-12-05 15:00 | 2025-12-18 15:00 | 33731 | 25202 | 2025-12-22 15:00 | 2026-02-12 15:00 | 45 | Shipping / customs | Review freight milestone and customs documents | 8529 | 25.29% | 43 | Late | 13 | 33731 | 52 | Paid | 0 | 2025-11 | P2
ORD-0263 | PRJ-009 | Iris Resort | Residential | SUP-06 | Alpine Illumination | Italy | CAT-03 | Lighting Controls | 2025-10-30 09:12 | 2025-11-04 09:12 | 2025-11-08 09:12 | 2025-12-25 09:12 | 2025-12-23 09:12 | 30160 | 19899 | 2025-12-26 09:12 | 2026-01-17 09:12 | 30 | Payment blocker | Coordinate payment release with finance | 10261 | 34.02% | 45 | On Time | 0 | 0 | 22 | Paid | 0 | 2025-11 | Monitor
ORD-0139 | PRJ-010 | Juniper Mall | Public Sector | SUP-04 | Anatolia Lighting | Turkey | CAT-04 | Emergency Lighting | 2025-11-01 18:00 | 2025-11-07 18:00 | 2025-11-10 18:00 | 2025-12-24 18:00 | 2025-12-22 18:00 | 11786 | 9178 | 2025-12-23 18:00 | 2026-02-11 18:00 | 60 | None | Monitor to plan | 2608 | 22.13% | 42 | On Time | 0 | 0 | 50 | Paid | 0 | 2025-11 | Monitor
ORD-0195 | PRJ-014 | Northgate Complex | Residential | SUP-01 | Cedar Components | Lebanon | CAT-02 | Outdoor Lighting | 2025-11-06 00:19 | 2025-11-08 00:19 | 2025-11-12 00:19 | 2025-12-06 00:19 | 2025-12-04 00:19 | 15487 | 12627 | 2025-12-09 00:19 | 2026-01-18 00:19 | 45 | None | Monitor to plan | 2860 | 18.47% | 22 | On Time | 0 | 0 | 40 | Paid | 0 | 2025-11 | Monitor
ORD-0418 | PRJ-006 | Forum Center | Hospitality | SUP-05 | Aegean Systems | Greece | CAT-04 | Emergency Lighting | 2025-11-08 01:43 | 2025-11-12 01:43 | 2025-11-14 01:43 | 2026-01-03 01:43 | 2026-01-01 01:43 | 26903 | 19679 | 2026-01-03 01:43 | 2026-03-17 01:43 | 60 | None | Monitor to plan | 7224 | 26.85% | 48 | On Time | 0 | 0 | 73 | Paid | 0 | 2025-11 | Monitor
ORD-0283 | PRJ-008 | Harbor Offices | Retail | SUP-07 | Nordic Beam | Germany | CAT-02 | Outdoor Lighting | 2025-11-10 04:22 | 2025-11-15 04:22 | 2025-11-16 04:22 | 2026-01-04 04:22 | 2026-01-04 04:22 | 9073 | 6935 | 2026-01-09 04:22 |  | 45 | None | Monitor to plan | 2138 | 23.56% | 49 | On Time | 0 | 0 | 213.818 | Overdue | 9073 | 2025-11 | P1
ORD-0026 | PRJ-009 | Iris Resort | Residential | SUP-08 | Gulf Smart Controls | UAE | CAT-05 | Architectural Fixtures | 2025-11-11 07:42 | 2025-11-13 07:42 | 2025-11-16 07:42 | 2025-12-21 07:42 | 2025-12-16 07:42 | 10423 | 7238 | 2025-12-18 07:42 | 2026-01-28 07:42 | 45 | None | Monitor to plan | 3185 | 30.56% | 30 | On Time | 0 | 0 | 41 | Paid | 0 | 2025-11 | Monitor
ORD-0186 | PRJ-003 | Cedar Residence | Retail | SUP-05 | Aegean Systems | Greece | CAT-01 | Indoor Lighting | 2025-11-04 14:51 | 2025-11-15 14:51 | 2025-11-18 14:51 | 2026-01-05 14:51 | 2026-01-05 14:51 | 32031 | 23481 | 2026-01-10 14:51 | 2026-02-15 14:51 | 30 | Client approval | Confirm decision owner and approval deadline | 8550 | 26.69% | 48 | On Time | 0 | 0 | 36 | Paid | 0 | 2025-11 | Monitor
ORD-0285 | PRJ-011 | Keystone Residence | Hospitality | SUP-10 | Pacific Fixtures | China | CAT-04 | Emergency Lighting | 2025-11-16 17:48 | 2025-11-17 17:48 | 2025-11-18 17:48 | 2026-02-05 17:48 | 2026-02-12 17:48 | 18494 | 12994 | 2026-02-17 17:48 | 2026-03-15 17:48 | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 5500 | 29.74% | 86 | Late | 7 | 18494 | 26 | Paid | 0 | 2025-11 | P2
ORD-0228 | PRJ-008 | Harbor Offices | Retail | SUP-05 | Aegean Systems | Greece | CAT-03 | Lighting Controls | 2025-11-16 21:21 | 2025-11-17 21:21 | 2025-11-19 21:21 | 2026-01-06 21:21 | 2026-01-12 21:21 | 12453 | 9806 | 2026-01-12 21:21 | 2026-03-11 21:21 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 2647 | 21.26% | 54 | Late | 6 | 12453 | 58 | Paid | 0 | 2025-11 | P3
ORD-0128 | PRJ-004 | District Retail | Residential | SUP-07 | Nordic Beam | Germany | CAT-06 | Electrical Accessories | 2025-11-16 21:47 | 2025-11-21 21:47 | 2025-11-23 21:47 | 2026-01-21 21:47 | 2026-01-20 21:47 | 21670 | 14881 | 2026-01-26 21:47 | 2026-03-08 21:47 | 45 | None | Monitor to plan | 6789 | 31.33% | 58 | On Time | 0 | 0 | 41 | Paid | 0 | 2025-11 | Monitor
ORD-0126 | PRJ-013 | Meridian Campus | Retail | SUP-10 | Pacific Fixtures | China | CAT-02 | Outdoor Lighting | 2025-11-15 08:11 | 2025-11-22 08:11 | 2025-11-25 08:11 | 2026-02-05 08:11 | 2026-02-15 08:11 | 35479 | 28366 | 2026-02-17 08:11 | 2026-04-20 08:11 | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 7113 | 20.05% | 82 | Late | 10 | 35479 | 62 | Paid | 0 | 2025-11 | P2
ORD-0273 | PRJ-004 | District Retail | Residential | SUP-12 | Atlas Outdoor | Spain | CAT-01 | Indoor Lighting | 2025-11-22 16:48 | 2025-11-28 16:48 | 2025-11-28 16:48 | 2026-01-18 16:48 | 2026-01-13 16:48 | 32753 | 23656 | 2026-01-19 16:48 | 2026-03-16 16:48 | 45 | None | Monitor to plan | 9097 | 27.77% | 46 | On Time | 0 | 0 | 56 | Paid | 0 | 2025-11 | Monitor
ORD-0349 | PRJ-005 | Elm Hospital | Public Sector | SUP-11 | Orient Emergency Systems | Malaysia | CAT-04 | Emergency Lighting | 2025-11-22 01:42 | 2025-11-28 01:42 | 2025-11-29 01:42 | 2026-02-03 01:42 | 2026-02-02 01:42 | 7148 | 5140 | 2026-02-04 01:42 |  | 30 | Documentation | Complete missing document and revalidate order | 2008 | 28.09% | 65 | On Time | 0 | 0 | 187.9289 | Overdue | 7148 | 2025-11 | P1
ORD-0049 | PRJ-014 | Northgate Complex | Residential | SUP-11 | Orient Emergency Systems | Malaysia | CAT-03 | Lighting Controls | 2025-11-27 18:57 | 2025-12-01 18:57 | 2025-12-01 18:57 | 2026-02-01 18:57 | 2026-01-24 18:57 | 7147 | 5850 | 2026-01-27 18:57 | 2026-03-18 18:57 | 45 | None | Monitor to plan | 1297 | 18.15% | 54 | On Time | 0 | 0 | 50 | Paid | 0 | 2025-12 | Monitor
ORD-0318 | PRJ-005 | Elm Hospital | Public Sector | SUP-03 | Phoenicia Electrical | Lebanon | CAT-06 | Electrical Accessories | 2025-11-23 23:53 | 2025-11-27 23:53 | 2025-12-01 23:53 | 2025-12-26 23:53 | 2025-12-28 23:53 | 2256 | 1702 | 2026-01-01 23:53 | 2026-02-04 23:53 | 30 | Payment blocker | Coordinate payment release with finance | 554 | 24.56% | 27 | Late | 2 | 2256 | 34 | Paid | 0 | 2025-12 | P3
ORD-0163 | PRJ-002 | Beacon Offices | Commercial | SUP-07 | Nordic Beam | Germany | CAT-04 | Emergency Lighting | 2025-11-28 01:50 | 2025-12-04 01:50 | 2025-12-06 01:50 | 2026-02-06 01:50 | 2026-01-29 01:50 | 13733 | 11038 | 2026-02-03 01:50 | 2026-03-19 01:50 | 45 | None | Monitor to plan | 2695 | 19.62% | 54 | On Time | 0 | 0 | 44 | Paid | 0 | 2025-12 | Monitor
ORD-0028 | PRJ-013 | Meridian Campus | Retail | SUP-06 | Alpine Illumination | Italy | CAT-01 | Indoor Lighting | 2025-12-05 00:50 | 2025-12-09 00:50 | 2025-12-11 00:50 | 2026-01-31 00:50 | 2026-01-30 00:50 | 9235 | 6552 | 2026-02-02 00:50 | 2026-03-13 00:50 | 30 | None | Monitor to plan | 2683 | 29.05% | 50 | On Time | 0 | 0 | 39 | Paid | 0 | 2025-12 | Monitor
ORD-0055 | PRJ-003 | Cedar Residence | Retail | SUP-05 | Aegean Systems | Greece | CAT-02 | Outdoor Lighting | 2025-12-04 16:34 | 2025-12-09 16:34 | 2025-12-11 16:34 | 2026-01-25 16:34 | 2026-01-19 16:34 | 36750 | 27925 | 2026-01-22 16:34 | 2026-03-31 16:34 | 60 | None | Monitor to plan | 8825 | 24.01% | 39 | On Time | 0 | 0 | 68 | Paid | 0 | 2025-12 | Monitor
ORD-0068 | PRJ-002 | Beacon Offices | Commercial | SUP-08 | Gulf Smart Controls | UAE | CAT-01 | Indoor Lighting | 2025-12-06 11:44 | 2025-12-11 11:44 | 2025-12-12 11:44 | 2026-01-09 11:44 | 2026-01-11 11:44 | 32091 | 23424 | 2026-01-16 11:44 |  | 30 | Documentation | Complete missing document and revalidate order | 8667 | 27.01% | 30 | Late | 2 | 32091 | 206.5114 | Overdue | 32091 | 2025-12 | P1
ORD-0124 | PRJ-015 | Olive Gardens | Public Sector | SUP-09 | Pearl LED Works | China | CAT-01 | Indoor Lighting | 2025-12-03 17:34 | 2025-12-10 17:34 | 2025-12-13 17:34 | 2026-02-23 17:34 | 2026-02-20 17:34 | 37302 | 25696 | 2026-02-22 17:34 | 2026-03-29 17:34 | 30 | None | Monitor to plan | 11606 | 31.11% | 69 | On Time | 0 | 0 | 35 | Paid | 0 | 2025-12 | Monitor
ORD-0032 | PRJ-005 | Elm Hospital | Public Sector | SUP-12 | Atlas Outdoor | Spain | CAT-06 | Electrical Accessories | 2025-12-13 13:46 | 2025-12-14 13:46 | 2025-12-14 13:46 | 2026-02-05 13:46 | 2026-02-02 13:46 | 21527 | 17199 | 2026-02-03 13:46 | 2026-03-18 13:46 | 30 | None | Monitor to plan | 4328 | 20.1% | 50 | On Time | 0 | 0 | 43 | Paid | 0 | 2025-12 | Monitor
ORD-0164 | PRJ-011 | Keystone Residence | Hospitality | SUP-02 | Levant Controls | Lebanon | CAT-04 | Emergency Lighting | 2025-12-13 10:53 | 2025-12-17 10:53 | 2025-12-17 10:53 | 2026-01-10 10:53 | 2026-01-05 10:53 | 23639 | 18626 | 2026-01-08 10:53 | 2026-02-23 10:53 | 45 | None | Monitor to plan | 5013 | 21.21% | 19 | On Time | 0 | 0 | 46 | Paid | 0 | 2025-12 | Monitor
ORD-0368 | PRJ-002 | Beacon Offices | Commercial | SUP-12 | Atlas Outdoor | Spain | CAT-03 | Lighting Controls | 2025-12-12 07:18 | 2025-12-14 07:18 | 2025-12-18 07:18 | 2026-02-09 07:18 | 2026-02-05 07:18 | 25803 | 17402 | 2026-02-07 07:18 |  | 30 | None | Monitor to plan | 8401 | 32.56% | 49 | On Time | 0 | 0 | 184.6955 | Overdue | 25803 | 2025-12 | P1
ORD-0377 | PRJ-005 | Elm Hospital | Public Sector | SUP-11 | Orient Emergency Systems | Malaysia | CAT-04 | Emergency Lighting | 2025-12-14 09:24 | 2025-12-15 09:24 | 2025-12-18 09:24 | 2026-02-18 09:24 | 2026-02-28 09:24 | 17453 | 14270 | 2026-03-06 09:24 | 2026-04-21 09:24 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 3183 | 18.24% | 72 | Late | 10 | 17453 | 46 | Paid | 0 | 2025-12 | P2
ORD-0370 | PRJ-003 | Cedar Residence | Retail | SUP-08 | Gulf Smart Controls | UAE | CAT-02 | Outdoor Lighting | 2025-12-18 07:46 | 2025-12-19 07:46 | 2025-12-20 07:46 | 2026-01-29 07:46 | 2026-01-31 07:46 | 45421 | 29815 | 2026-02-03 07:46 | 2026-03-31 07:46 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 15606 | 34.36% | 42 | Late | 2 | 45421 | 56 | Paid | 0 | 2025-12 | P1
ORD-0274 | PRJ-013 | Meridian Campus | Retail | SUP-06 | Alpine Illumination | Italy | CAT-06 | Electrical Accessories | 2025-12-14 15:27 | 2025-12-19 15:27 | 2025-12-21 15:27 | 2026-02-11 15:27 | 2026-02-12 15:27 | 21530 | 14603 | 2026-02-18 15:27 | 2026-03-31 15:27 | 45 | Payment blocker | Coordinate payment release with finance | 6927 | 32.17% | 53 | Late | 1 | 21530 | 41 | Paid | 0 | 2025-12 | P2
ORD-0111 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-10 | Pacific Fixtures | China | CAT-04 | Emergency Lighting | 2025-12-17 07:13 | 2025-12-18 07:13 | 2025-12-22 07:13 | 2026-03-16 07:13 | 2026-03-16 07:13 | 23792 | 17703 | 2026-03-22 07:13 | 2026-05-20 07:13 | 45 | None | Monitor to plan | 6089 | 25.59% | 84 | On Time | 0 | 0 | 59 | Paid | 0 | 2025-12 | Monitor
ORD-0136 | PRJ-004 | District Retail | Residential | SUP-11 | Orient Emergency Systems | Malaysia | CAT-04 | Emergency Lighting | 2025-12-11 09:43 | 2025-12-18 09:43 | 2025-12-22 09:43 | 2026-02-21 09:43 | 2026-03-07 09:43 | 12035 | 9674 | 2026-03-09 09:43 | 2026-05-02 09:43 | 45 | None | Monitor to plan | 2361 | 19.62% | 75 | Late | 14 | 12035 | 54 | Paid | 0 | 2025-12 | P2
ORD-0076 | PRJ-007 | Garden Villas | Commercial | SUP-02 | Levant Controls | Lebanon | CAT-06 | Electrical Accessories | 2025-12-13 20:27 | 2025-12-20 20:27 | 2025-12-22 20:27 | 2026-01-21 20:27 | 2026-01-13 20:27 | 6818 | 4487 | 2026-01-18 20:27 | 2026-03-11 20:27 | 45 | None | Monitor to plan | 2331 | 34.19% | 22 | On Time | 0 | 0 | 52 | Paid | 0 | 2025-12 | Monitor
ORD-0237 | PRJ-009 | Iris Resort | Residential | SUP-07 | Nordic Beam | Germany | CAT-06 | Electrical Accessories | 2025-11-29 23:22 | 2025-12-22 23:22 | 2025-12-23 23:22 | 2026-02-16 23:22 | 2026-02-15 23:22 | 4713 | 3342 | 2026-02-15 23:22 | 2026-03-23 23:22 | 45 | Client approval | Confirm decision owner and approval deadline | 1371 | 29.09% | 54 | On Time | 0 | 0 | 36 | Paid | 0 | 2025-12 | Monitor
ORD-0324 | PRJ-003 | Cedar Residence | Retail | SUP-12 | Atlas Outdoor | Spain | CAT-01 | Indoor Lighting | 2025-12-23 03:14 | 2025-12-24 03:14 | 2025-12-24 03:14 | 2026-02-14 03:14 | 2026-02-14 03:14 | 5103 | 3793 | 2026-02-20 03:14 | 2026-03-15 03:14 | 30 | None | Monitor to plan | 1310 | 25.67% | 52 | On Time | 0 | 0 | 23 | Paid | 0 | 2025-12 | Monitor
ORD-0160 | PRJ-008 | Harbor Offices | Retail | SUP-08 | Gulf Smart Controls | UAE | CAT-04 | Emergency Lighting | 2025-12-08 23:02 | 2025-12-20 23:02 | 2025-12-24 23:02 | 2026-01-24 23:02 | 2026-01-19 23:02 | 22904 | 17355 | 2026-01-21 23:02 | 2026-03-01 23:02 | 45 | Client approval | Confirm decision owner and approval deadline | 5549 | 24.23% | 26 | On Time | 0 | 0 | 39 | Paid | 0 | 2025-12 | Monitor
ORD-0402 | PRJ-011 | Keystone Residence | Hospitality | SUP-12 | Atlas Outdoor | Spain | CAT-05 | Architectural Fixtures | 2025-12-07 04:54 | 2025-12-23 04:54 | 2025-12-25 04:54 | 2026-02-23 04:54 | 2026-02-19 04:54 | 59257 | 40588 | 2026-02-19 04:54 | 2026-04-02 04:54 | 30 | Client approval | Confirm decision owner and approval deadline | 18669 | 31.51% | 56 | On Time | 0 | 0 | 42 | Paid | 0 | 2025-12 | Monitor
ORD-0243 | PRJ-004 | District Retail | Residential | SUP-10 | Pacific Fixtures | China | CAT-05 | Architectural Fixtures | 2025-12-23 22:35 | 2025-12-26 22:35 | 2025-12-26 22:35 | 2026-03-11 22:35 | 2026-03-06 22:35 | 48845 | 36242 | 2026-03-08 22:35 | 2026-05-04 22:35 | 45 | None | Monitor to plan | 12603 | 25.8% | 70 | On Time | 0 | 0 | 57 | Paid | 0 | 2025-12 | Monitor
ORD-0291 | PRJ-001 | Atlas Hotel | Hospitality | SUP-01 | Cedar Components | Lebanon | CAT-03 | Lighting Controls | 2025-12-22 04:53 | 2025-12-23 04:53 | 2025-12-27 04:53 | 2026-01-20 04:53 | 2026-01-12 04:53 | 14651 | 10008 | 2026-01-16 04:53 | 2026-02-28 04:53 | 30 | None | Monitor to plan | 4643 | 31.69% | 16 | On Time | 0 | 0 | 43 | Paid | 0 | 2025-12 | Monitor
ORD-0289 | PRJ-006 | Forum Center | Hospitality | SUP-01 | Cedar Components | Lebanon | CAT-04 | Emergency Lighting | 2025-12-18 05:55 | 2025-12-25 05:55 | 2025-12-28 05:55 | 2026-01-12 05:55 | 2026-01-13 05:55 | 17879 | 14281 | 2026-01-16 05:55 | 2026-03-12 05:55 | 60 | Payment blocker | Coordinate payment release with finance | 3598 | 20.12% | 16 | Late | 1 | 17879 | 55 | Paid | 0 | 2025-12 | P3
ORD-0075 | PRJ-003 | Cedar Residence | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-04 | Emergency Lighting | 2025-12-21 22:03 | 2025-12-25 22:03 | 2025-12-28 22:03 | 2026-01-17 22:03 | 2026-01-17 22:03 | 5554 | 4101 | 2026-01-17 22:03 | 2026-03-16 22:03 | 45 | None | Monitor to plan | 1453 | 26.16% | 20 | On Time | 0 | 0 | 58 | Paid | 0 | 2025-12 | Monitor
ORD-0295 | PRJ-006 | Forum Center | Hospitality | SUP-02 | Levant Controls | Lebanon | CAT-06 | Electrical Accessories | 2025-12-22 05:24 | 2025-12-26 05:24 | 2025-12-29 05:24 | 2026-01-20 05:24 | 2026-01-22 05:24 | 7892 | 5536 | 2026-01-26 05:24 |  | 45 | Payment blocker | Coordinate payment release with finance | 2356 | 29.85% | 24 | Late | 2 | 7892 | 196.7747 | Overdue | 7892 | 2025-12 | P1
ORD-0255 | PRJ-001 | Atlas Hotel | Hospitality | SUP-07 | Nordic Beam | Germany | CAT-01 | Indoor Lighting | 2025-12-28 00:13 | 2025-12-29 00:13 | 2026-01-02 00:13 | 2026-02-26 00:13 | 2026-03-05 00:13 | 14167 | 9697 | 2026-03-09 00:13 | 2026-05-02 00:13 | 45 | Payment blocker | Coordinate payment release with finance | 4470 | 31.55% | 62 | Late | 7 | 14167 | 54 | Paid | 0 | 2026-01 | P2
ORD-0409 | PRJ-015 | Olive Gardens | Public Sector | SUP-09 | Pearl LED Works | China | CAT-02 | Outdoor Lighting | 2025-12-30 09:48 | 2026-01-01 09:48 | 2026-01-03 09:48 | 2026-03-11 09:48 | 2026-03-22 09:48 | 21266 | 15456 | 2026-03-27 09:48 | 2026-05-04 09:48 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 5810 | 27.32% | 78 | Late | 11 | 21266 | 38 | Paid | 0 | 2026-01 | P2
ORD-0267 | PRJ-013 | Meridian Campus | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-05 | Architectural Fixtures | 2025-12-30 23:04 | 2025-12-31 23:04 | 2026-01-04 23:04 | 2026-01-27 23:04 | 2026-01-21 23:04 | 33043 | 26603 | 2026-01-26 23:04 | 2026-03-06 23:04 | 45 | None | Monitor to plan | 6440 | 19.49% | 17 | On Time | 0 | 0 | 39 | Paid | 0 | 2026-01 | Monitor
ORD-0230 | PRJ-003 | Cedar Residence | Retail | SUP-01 | Cedar Components | Lebanon | CAT-02 | Outdoor Lighting | 2026-01-01 04:46 | 2026-01-04 04:46 | 2026-01-05 04:46 | 2026-01-21 04:46 | 2026-01-13 04:46 | 13787 | 9866 | 2026-01-14 04:46 | 2026-02-19 04:46 | 45 | None | Monitor to plan | 3921 | 28.44% | 8 | On Time | 0 | 0 | 36 | Paid | 0 | 2026-01 | Monitor
ORD-0310 | PRJ-004 | District Retail | Residential | SUP-09 | Pearl LED Works | China | CAT-05 | Architectural Fixtures | 2025-12-31 17:45 | 2026-01-02 17:45 | 2026-01-05 17:45 | 2026-03-14 17:45 | 2026-03-10 17:45 | 6998 | 4879 | 2026-03-14 17:45 | 2026-04-04 17:45 | 30 | None | Monitor to plan | 2119 | 30.28% | 64 | On Time | 0 | 0 | 21 | Paid | 0 | 2026-01 | Monitor
ORD-0015 | PRJ-014 | Northgate Complex | Residential | SUP-08 | Gulf Smart Controls | UAE | CAT-06 | Electrical Accessories | 2025-12-29 23:37 | 2026-01-01 23:37 | 2026-01-05 23:37 | 2026-02-01 23:37 | 2026-01-29 23:37 | 5607 | 4537 | 2026-01-29 23:37 | 2026-03-19 23:37 | 45 | None | Monitor to plan | 1070 | 19.08% | 24 | On Time | 0 | 0 | 49 | Paid | 0 | 2026-01 | Monitor
ORD-0284 | PRJ-006 | Forum Center | Hospitality | SUP-10 | Pacific Fixtures | China | CAT-02 | Outdoor Lighting | 2025-12-28 10:01 | 2026-01-02 10:01 | 2026-01-06 10:01 | 2026-03-25 10:01 | 2026-03-25 10:01 | 38635 | 26613 | 2026-03-26 10:01 |  | 60 | None | Monitor to plan | 12022 | 31.12% | 78 | On Time | 0 | 0 | 137.5829 | Overdue | 38635 | 2026-01 | P1
ORD-0266 | PRJ-008 | Harbor Offices | Retail | SUP-06 | Alpine Illumination | Italy | CAT-06 | Electrical Accessories | 2025-12-30 14:44 | 2026-01-05 14:44 | 2026-01-06 14:44 | 2026-02-24 14:44 | 2026-03-02 14:44 | 22233 | 17918 | 2026-03-04 14:44 | 2026-04-29 14:44 | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 4315 | 19.41% | 55 | Late | 6 | 22233 | 56 | Paid | 0 | 2026-01 | P2
ORD-0414 | PRJ-008 | Harbor Offices | Retail | SUP-09 | Pearl LED Works | China | CAT-03 | Lighting Controls | 2025-12-20 04:53 | 2026-01-05 04:53 | 2026-01-07 04:53 | 2026-03-26 04:53 | 2026-03-22 04:53 | 4705 | 3440 | 2026-03-22 04:53 | 2026-04-23 04:53 | 30 | Client approval | Confirm decision owner and approval deadline | 1265 | 26.89% | 74 | On Time | 0 | 0 | 32 | Paid | 0 | 2026-01 | Monitor
ORD-0309 | PRJ-004 | District Retail | Residential | SUP-08 | Gulf Smart Controls | UAE | CAT-01 | Indoor Lighting | 2025-12-30 10:24 | 2026-01-05 10:24 | 2026-01-08 10:24 | 2026-02-13 10:24 | 2026-02-13 10:24 | 7144 | 5646 | 2026-02-15 10:24 | 2026-04-06 10:24 | 45 | None | Monitor to plan | 1498 | 20.97% | 36 | On Time | 0 | 0 | 50 | Paid | 0 | 2026-01 | Monitor
ORD-0113 | PRJ-015 | Olive Gardens | Public Sector | SUP-07 | Nordic Beam | Germany | CAT-04 | Emergency Lighting | 2026-01-01 07:27 | 2026-01-05 07:27 | 2026-01-09 07:27 | 2026-03-05 07:27 | 2026-02-28 07:27 | 14041 | 9614 | 2026-03-01 07:27 | 2026-04-29 07:27 | 60 | None | Monitor to plan | 4427 | 31.53% | 50 | On Time | 0 | 0 | 59 | Paid | 0 | 2026-01 | Monitor
ORD-0096 | PRJ-004 | District Retail | Residential | SUP-12 | Atlas Outdoor | Spain | CAT-01 | Indoor Lighting | 2026-01-03 02:52 | 2026-01-09 02:52 | 2026-01-10 02:52 | 2026-02-28 02:52 | 2026-02-25 02:52 | 31690 | 22878 | 2026-02-27 02:52 |  | 45 | None | Monitor to plan | 8812 | 27.81% | 46 | On Time | 0 | 0 | 164.8803 | Overdue | 31690 | 2026-01 | P1
ORD-0354 | PRJ-005 | Elm Hospital | Public Sector | SUP-01 | Cedar Components | Lebanon | CAT-01 | Indoor Lighting | 2026-01-01 22:12 | 2026-01-07 22:12 | 2026-01-10 22:12 | 2026-01-24 22:12 | 2026-02-16 22:12 | 39552 | 25819 | 2026-02-16 22:12 |  | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 13733 | 34.72% | 37 | Late | 23 | 39552 | 175.0749 | Overdue | 39552 | 2026-01 | P1
ORD-0029 | PRJ-015 | Olive Gardens | Public Sector | SUP-12 | Atlas Outdoor | Spain | CAT-03 | Lighting Controls | 2026-01-05 23:03 | 2026-01-06 23:03 | 2026-01-10 23:03 | 2026-03-09 23:03 | 2026-03-02 23:03 | 24259 | 16357 | 2026-03-08 23:03 | 2026-04-13 23:03 | 30 | None | Monitor to plan | 7902 | 32.57% | 51 | On Time | 0 | 0 | 36 | Paid | 0 | 2026-01 | Monitor
ORD-0361 | PRJ-007 | Garden Villas | Commercial | SUP-05 | Aegean Systems | Greece | CAT-04 | Emergency Lighting | 2026-01-08 21:02 | 2026-01-09 21:02 | 2026-01-11 21:02 | 2026-03-03 21:02 | 2026-02-27 21:02 | 16142 | 11972 | 2026-03-01 21:02 | 2026-04-09 21:02 | 30 | None | Monitor to plan | 4170 | 25.83% | 47 | On Time | 0 | 0 | 39 | Paid | 0 | 2026-01 | Monitor
ORD-0184 | PRJ-006 | Forum Center | Hospitality | SUP-06 | Alpine Illumination | Italy | CAT-02 | Outdoor Lighting | 2026-01-04 06:30 | 2026-01-08 06:30 | 2026-01-12 06:30 | 2026-03-07 06:30 | 2026-03-22 06:30 | 8501 | 5700 | 2026-03-27 06:30 | 2026-04-26 06:30 | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 2801 | 32.95% | 69 | Late | 15 | 8501 | 30 | Paid | 0 | 2026-01 | P1
ORD-0395 | PRJ-002 | Beacon Offices | Commercial | SUP-07 | Nordic Beam | Germany | CAT-05 | Architectural Fixtures | 2026-01-11 21:37 | 2026-01-12 21:37 | 2026-01-15 21:37 | 2026-03-11 21:37 | 2026-03-12 21:37 | 35373 | 26424 | 2026-03-15 21:37 | 2026-04-27 21:37 | 45 | Documentation | Complete missing document and revalidate order | 8949 | 25.3% | 56 | Late | 1 | 35373 | 43 | Paid | 0 | 2026-01 | P2
ORD-0219 | PRJ-002 | Beacon Offices | Commercial | SUP-11 | Orient Emergency Systems | Malaysia | CAT-05 | Architectural Fixtures | 2026-01-12 22:23 | 2026-01-14 22:23 | 2026-01-15 22:23 | 2026-03-27 22:23 | 2026-04-10 22:23 | 9587 | 6407 | 2026-04-14 22:23 | 2026-05-27 22:23 | 45 | Shipping / customs | Review freight milestone and customs documents | 3180 | 33.17% | 85 | Late | 14 | 9587 | 43 | Paid | 0 | 2026-01 | P2
ORD-0302 | PRJ-003 | Cedar Residence | Retail | SUP-09 | Pearl LED Works | China | CAT-03 | Lighting Controls | 2026-01-11 10:37 | 2026-01-15 10:37 | 2026-01-17 10:37 | 2026-04-06 10:37 | 2026-04-29 10:37 | 34051 | 24429 | 2026-04-30 10:37 | 2026-06-06 10:37 | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 9622 | 28.26% | 102 | Late | 23 | 34051 | 37 | Paid | 0 | 2026-01 | P1
ORD-0006 | PRJ-001 | Atlas Hotel | Hospitality | SUP-01 | Cedar Components | Lebanon | CAT-04 | Emergency Lighting | 2026-01-12 14:38 | 2026-01-14 14:38 | 2026-01-17 14:38 | 2026-02-13 14:38 | 2026-02-11 14:38 | 4707 | 3331 | 2026-02-14 14:38 | 2026-03-08 14:38 | 30 | None | Monitor to plan | 1376 | 29.23% | 25 | On Time | 0 | 0 | 22 | Paid | 0 | 2026-01 | Monitor
ORD-0419 | PRJ-013 | Meridian Campus | Retail | SUP-01 | Cedar Components | Lebanon | CAT-05 | Architectural Fixtures | 2026-01-17 02:53 | 2026-01-18 02:53 | 2026-01-18 02:53 | 2026-02-07 02:53 | 2026-02-02 02:53 | 46129 | 31813 | 2026-02-02 02:53 |  | 30 | None | Monitor to plan | 14316 | 31.03% | 15 | On Time | 0 | 0 | 189.8799 | Overdue | 46129 | 2026-01 | P1
ORD-0315 | PRJ-005 | Elm Hospital | Public Sector | SUP-04 | Anatolia Lighting | Turkey | CAT-01 | Indoor Lighting | 2026-01-11 15:31 | 2026-01-17 15:31 | 2026-01-18 15:31 | 2026-02-22 15:31 | 2026-02-21 15:31 | 11397 | 7711 | 2026-02-24 15:31 | 2026-04-06 15:31 | 30 | None | Monitor to plan | 3686 | 32.34% | 34 | On Time | 0 | 0 | 41 | Paid | 0 | 2026-01 | Monitor
ORD-0308 | PRJ-003 | Cedar Residence | Retail | SUP-07 | Nordic Beam | Germany | CAT-02 | Outdoor Lighting | 2026-01-04 10:09 | 2026-01-23 10:09 | 2026-01-25 10:09 | 2026-03-24 10:09 | 2026-03-16 10:09 | 36331 | 28449 | 2026-03-16 10:09 | 2026-04-09 10:09 | 30 | Client approval | Confirm decision owner and approval deadline | 7882 | 21.69% | 50 | On Time | 0 | 0 | 24 | Paid | 0 | 2026-01 | Monitor
ORD-0003 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-04 | Anatolia Lighting | Turkey | CAT-03 | Lighting Controls | 2026-01-05 01:15 | 2026-01-25 01:15 | 2026-01-26 01:15 | 2026-03-10 01:15 | 2026-03-23 01:15 | 29091 | 21098 | 2026-03-25 01:15 | 2026-05-16 01:15 | 45 | Client approval | Confirm decision owner and approval deadline | 7993 | 27.48% | 56 | Late | 13 | 29091 | 52 | Paid | 0 | 2026-01 | P2
ORD-0018 | PRJ-011 | Keystone Residence | Hospitality | SUP-09 | Pearl LED Works | China | CAT-06 | Electrical Accessories | 2026-01-17 17:17 | 2026-01-23 17:17 | 2026-01-26 17:17 | 2026-04-08 17:17 | 2026-04-04 17:17 | 18956 | 15206 | 2026-04-09 17:17 | 2026-06-20 17:17 | 60 | Payment blocker | Coordinate payment release with finance | 3750 | 19.78% | 68 | On Time | 0 | 0 | 72 | Paid | 0 | 2026-01 | Monitor
ORD-0157 | PRJ-007 | Garden Villas | Commercial | SUP-05 | Aegean Systems | Greece | CAT-02 | Outdoor Lighting | 2026-01-21 05:57 | 2026-01-23 05:57 | 2026-01-27 05:57 | 2026-03-08 05:57 | 2026-03-02 05:57 | 40736 | 30174 | 2026-03-07 05:57 | 2026-05-10 05:57 | 60 | None | Monitor to plan | 10562 | 25.93% | 34 | On Time | 0 | 0 | 64 | Paid | 0 | 2026-01 | Monitor
ORD-0171 | PRJ-010 | Juniper Mall | Public Sector | SUP-04 | Anatolia Lighting | Turkey | CAT-05 | Architectural Fixtures | 2026-01-11 07:28 | 2026-01-27 07:28 | 2026-01-28 07:28 | 2026-03-02 07:28 | 2026-03-02 07:28 | 19710 | 15173 | 2026-03-05 07:28 | 2026-03-31 07:28 | 30 | Client approval | Confirm decision owner and approval deadline | 4537 | 23.02% | 33 | On Time | 0 | 0 | 26 | Paid | 0 | 2026-01 | Monitor
ORD-0169 | PRJ-003 | Cedar Residence | Retail | SUP-12 | Atlas Outdoor | Spain | CAT-04 | Emergency Lighting | 2026-01-18 10:22 | 2026-01-25 10:22 | 2026-01-28 10:22 | 2026-03-25 10:22 | 2026-04-03 10:22 | 21488 | 14143 | 2026-04-04 10:22 | 2026-05-02 10:22 | 30 | Shipping / customs | Review freight milestone and customs documents | 7345 | 34.18% | 65 | Late | 9 | 21488 | 28 | Paid | 0 | 2026-01 | P2
ORD-0137 | PRJ-009 | Iris Resort | Residential | SUP-08 | Gulf Smart Controls | UAE | CAT-01 | Indoor Lighting | 2026-01-23 01:53 | 2026-01-27 01:53 | 2026-01-30 01:53 | 2026-02-25 01:53 | 2026-02-20 01:53 | 38292 | 30438 | 2026-02-21 01:53 | 2026-04-10 01:53 | 45 | None | Monitor to plan | 7854 | 20.51% | 21 | On Time | 0 | 0 | 48 | Paid | 0 | 2026-01 | Monitor
ORD-0014 | PRJ-013 | Meridian Campus | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-02 | Outdoor Lighting | 2026-01-27 20:52 | 2026-01-31 20:52 | 2026-02-01 20:52 | 2026-02-23 20:52 | 2026-03-09 20:52 | 9142 | 6272 | 2026-03-14 20:52 | 2026-04-23 20:52 | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 2870 | 31.39% | 36 | Late | 14 | 9142 | 40 | Paid | 0 | 2026-02 | P2
ORD-0224 | PRJ-001 | Atlas Hotel | Hospitality | SUP-12 | Atlas Outdoor | Spain | CAT-03 | Lighting Controls | 2026-01-27 17:01 | 2026-01-29 17:01 | 2026-02-02 17:01 | 2026-03-27 17:01 | 2026-04-07 17:01 | 18041 | 12977 | 2026-04-09 17:01 | 2026-05-16 17:01 | 45 | None | Monitor to plan | 5064 | 28.07% | 64 | Late | 11 | 18041 | 37 | Paid | 0 | 2026-02 | P2
ORD-0362 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-05 | Aegean Systems | Greece | CAT-04 | Emergency Lighting | 2026-01-24 03:12 | 2026-01-30 03:12 | 2026-02-03 03:12 | 2026-03-22 03:12 | 2026-03-28 03:12 | 20204 | 14399 | 2026-03-30 03:12 | 2026-05-25 03:12 | 60 | None | Monitor to plan | 5805 | 28.73% | 53 | Late | 6 | 20204 | 56 | Paid | 0 | 2026-02 | P2
ORD-0333 | PRJ-013 | Meridian Campus | Retail | SUP-10 | Pacific Fixtures | China | CAT-03 | Lighting Controls | 2026-01-27 07:27 | 2026-02-01 07:27 | 2026-02-03 07:27 | 2026-04-26 07:27 | 2026-04-26 07:27 | 29317 | 21835 | 2026-04-30 07:27 | 2026-06-06 07:27 | 30 | None | Monitor to plan | 7482 | 25.52% | 82 | On Time | 0 | 0 | 37 | Paid | 0 | 2026-02 | Monitor
ORD-0367 | PRJ-006 | Forum Center | Hospitality | SUP-01 | Cedar Components | Lebanon | CAT-05 | Architectural Fixtures | 2026-01-30 03:55 | 2026-02-03 03:55 | 2026-02-04 03:55 | 2026-02-21 03:55 | 2026-02-19 03:55 | 40826 | 26739 | 2026-02-24 03:55 | 2026-04-13 03:55 | 45 | Documentation | Complete missing document and revalidate order | 14087 | 34.5% | 15 | On Time | 0 | 0 | 48 | Paid | 0 | 2026-02 | Monitor
ORD-0194 | PRJ-014 | Northgate Complex | Residential | SUP-12 | Atlas Outdoor | Spain | CAT-04 | Emergency Lighting | 2026-01-28 12:17 | 2026-02-01 12:17 | 2026-02-04 12:17 | 2026-04-06 12:17 | 2026-04-11 12:17 | 17753 | 13809 | 2026-04-16 12:17 |  | 30 | Payment blocker | Coordinate payment release with finance | 3944 | 22.22% | 66 | Late | 5 | 17753 | 116.488 | Overdue | 17753 | 2026-02 | P1
ORD-0279 | PRJ-010 | Juniper Mall | Public Sector | SUP-06 | Alpine Illumination | Italy | CAT-02 | Outdoor Lighting | 2026-02-02 20:33 | 2026-02-04 20:33 | 2026-02-04 20:33 | 2026-03-28 20:33 | 2026-04-01 20:33 | 45614 | 30668 | 2026-04-04 20:33 | 2026-05-12 20:33 | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 14946 | 32.77% | 56 | Late | 4 | 45614 | 38 | Paid | 0 | 2026-02 | P1
ORD-0348 | PRJ-007 | Garden Villas | Commercial | SUP-04 | Anatolia Lighting | Turkey | CAT-03 | Lighting Controls | 2026-01-31 21:37 | 2026-02-04 21:37 | 2026-02-04 21:37 | 2026-03-16 21:37 | 2026-03-27 21:37 | 24365 | 16327 | 2026-04-01 21:37 | 2026-05-26 21:37 | 45 | Shipping / customs | Review freight milestone and customs documents | 8038 | 32.99% | 51 | Late | 11 | 24365 | 55 | Paid | 0 | 2026-02 | P2
ORD-0016 | PRJ-008 | Harbor Offices | Retail | SUP-10 | Pacific Fixtures | China | CAT-05 | Architectural Fixtures | 2026-01-25 13:57 | 2026-02-01 13:57 | 2026-02-05 13:57 | 2026-04-21 13:57 | 2026-04-15 13:57 | 26851 | 18541 | 2026-04-20 13:57 | 2026-05-15 13:57 | 30 | None | Monitor to plan | 8310 | 30.95% | 69 | On Time | 0 | 0 | 25 | Paid | 0 | 2026-02 | Monitor
ORD-0296 | PRJ-011 | Keystone Residence | Hospitality | SUP-06 | Alpine Illumination | Italy | CAT-05 | Architectural Fixtures | 2026-01-28 19:57 | 2026-02-04 19:57 | 2026-02-05 19:57 | 2026-03-25 19:57 | 2026-04-12 19:57 | 14430 | 11437 | 2026-04-17 19:57 | 2026-06-11 19:57 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 2993 | 20.74% | 66 | Late | 18 | 14430 | 55 | Paid | 0 | 2026-02 | P1
ORD-0087 | PRJ-002 | Beacon Offices | Commercial | SUP-02 | Levant Controls | Lebanon | CAT-05 | Architectural Fixtures | 2026-01-29 15:04 | 2026-02-02 15:04 | 2026-02-06 15:04 | 2026-03-04 15:04 | 2026-02-25 15:04 | 57108 | 40153 | 2026-02-26 15:04 | 2026-03-25 15:04 | 30 | None | Monitor to plan | 16955 | 29.69% | 19 | On Time | 0 | 0 | 27 | Paid | 0 | 2026-02 | Monitor
ORD-0060 | PRJ-004 | District Retail | Residential | SUP-08 | Gulf Smart Controls | UAE | CAT-05 | Architectural Fixtures | 2026-02-04 16:49 | 2026-02-07 16:49 | 2026-02-08 16:49 | 2026-03-11 16:49 | 2026-03-04 16:49 | 58915 | 42770 | 2026-03-10 16:49 | 2026-04-20 16:49 | 45 | None | Monitor to plan | 16145 | 27.4% | 24 | On Time | 0 | 0 | 41 | Paid | 0 | 2026-02 | Monitor
ORD-0403 | PRJ-003 | Cedar Residence | Retail | SUP-02 | Levant Controls | Lebanon | CAT-05 | Architectural Fixtures | 2026-02-06 03:45 | 2026-02-11 03:45 | 2026-02-12 03:45 | 2026-03-07 03:45 | 2026-03-04 03:45 | 17413 | 12765 | 2026-03-08 03:45 | 2026-04-24 03:45 | 45 | None | Monitor to plan | 4648 | 26.69% | 20 | On Time | 0 | 0 | 47 | Paid | 0 | 2026-02 | Monitor
ORD-0115 | PRJ-003 | Cedar Residence | Retail | SUP-10 | Pacific Fixtures | China | CAT-03 | Lighting Controls | 2026-02-07 04:03 | 2026-02-12 04:03 | 2026-02-12 04:03 | 2026-04-28 04:03 | 2026-04-20 04:03 | 7587 | 6117 | 2026-04-25 04:03 | 2026-05-25 04:03 | 30 | None | Monitor to plan | 1470 | 19.38% | 67 | On Time | 0 | 0 | 30 | Paid | 0 | 2026-02 | Monitor
ORD-0192 | PRJ-003 | Cedar Residence | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-03 | Lighting Controls | 2026-02-03 00:07 | 2026-02-09 00:07 | 2026-02-13 00:07 | 2026-03-08 00:07 | 2026-03-16 00:07 | 14194 | 10011 | 2026-03-22 00:07 | 2026-05-31 00:07 | 60 | Shipping / customs | Review freight milestone and customs documents | 4183 | 29.47% | 31 | Late | 8 | 14194 | 70 | Paid | 0 | 2026-02 | P2
ORD-0415 | PRJ-015 | Olive Gardens | Public Sector | SUP-05 | Aegean Systems | Greece | CAT-04 | Emergency Lighting | 2026-02-11 13:56 | 2026-02-13 13:56 | 2026-02-14 13:56 | 2026-03-30 13:56 | 2026-03-29 13:56 | 21562 | 14095 | 2026-03-31 13:56 | 2026-04-28 13:56 | 30 | None | Monitor to plan | 7467 | 34.63% | 43 | On Time | 0 | 0 | 28 | Paid | 0 | 2026-02 | Monitor
ORD-0033 | PRJ-005 | Elm Hospital | Public Sector | SUP-01 | Cedar Components | Lebanon | CAT-04 | Emergency Lighting | 2026-02-09 19:30 | 2026-02-13 19:30 | 2026-02-16 19:30 | 2026-03-11 19:30 | 2026-03-04 19:30 | 24314 | 16082 | 2026-03-08 19:30 | 2026-04-10 19:30 | 30 | None | Monitor to plan | 8232 | 33.86% | 16 | On Time | 0 | 0 | 33 | Paid | 0 | 2026-02 | Monitor
ORD-0070 | PRJ-004 | District Retail | Residential | SUP-10 | Pacific Fixtures | China | CAT-04 | Emergency Lighting | 2026-02-18 11:56 | 2026-02-19 11:56 | 2026-02-20 11:56 | 2026-05-13 11:56 | 2026-06-05 11:56 | 22630 | 17494 | 2026-06-08 11:56 | 2026-08-05 11:56 | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 5136 | 22.7% | 105 | Late | 23 | 22630 | 58 | Paid | 0 | 2026-02 | P1
ORD-0299 | PRJ-008 | Harbor Offices | Retail | SUP-02 | Levant Controls | Lebanon | CAT-04 | Emergency Lighting | 2026-02-13 10:39 | 2026-02-17 10:39 | 2026-02-21 10:39 | 2026-03-15 10:39 | 2026-03-14 10:39 | 9964 | 7847 | 2026-03-17 10:39 | 2026-04-29 10:39 | 45 | None | Monitor to plan | 2117 | 21.25% | 21 | On Time | 0 | 0 | 43 | Paid | 0 | 2026-02 | Monitor
ORD-0107 | PRJ-009 | Iris Resort | Residential | SUP-12 | Atlas Outdoor | Spain | CAT-01 | Indoor Lighting | 2026-02-21 08:29 | 2026-02-23 08:29 | 2026-02-25 08:29 | 2026-04-24 08:29 | 2026-04-21 08:29 | 26421 | 20877 | 2026-04-25 08:29 | 2026-06-25 08:29 | 60 | None | Monitor to plan | 5544 | 20.98% | 55 | On Time | 0 | 0 | 61 | Paid | 0 | 2026-02 | Monitor
ORD-0241 | PRJ-008 | Harbor Offices | Retail | SUP-12 | Atlas Outdoor | Spain | CAT-01 | Indoor Lighting | 2026-02-28 14:20 | 2026-03-01 14:20 | 2026-03-03 14:20 | 2026-04-29 14:20 | 2026-04-23 14:20 | 31955 | 25776 | 2026-04-29 14:20 | 2026-06-22 14:20 | 45 | None | Monitor to plan | 6179 | 19.34% | 51 | On Time | 0 | 0 | 54 | Paid | 0 | 2026-03 | Monitor
ORD-0360 | PRJ-001 | Atlas Hotel | Hospitality | SUP-05 | Aegean Systems | Greece | CAT-01 | Indoor Lighting | 2026-02-26 22:15 | 2026-03-03 22:15 | 2026-03-03 22:15 | 2026-04-11 22:15 | 2026-04-13 22:15 | 35400 | 27120 | 2026-04-16 22:15 | 2026-05-17 22:15 | 30 | Payment blocker | Coordinate payment release with finance | 8280 | 23.39% | 41 | Late | 2 | 35400 | 31 | Paid | 0 | 2026-03 | P2
ORD-0358 | PRJ-009 | Iris Resort | Residential | SUP-10 | Pacific Fixtures | China | CAT-02 | Outdoor Lighting | 2026-02-13 14:02 | 2026-03-04 14:02 | 2026-03-04 14:02 | 2026-05-19 14:02 | 2026-05-24 14:02 | 46921 | 33230 | 2026-05-30 14:02 |  | 60 | Client approval | Confirm decision owner and approval deadline | 13691 | 29.18% | 81 | Late | 5 | 46921 | 72.4153 | Overdue | 46921 | 2026-03 | P1
ORD-0178 | PRJ-014 | Northgate Complex | Residential | SUP-11 | Orient Emergency Systems | Malaysia | CAT-01 | Indoor Lighting | 2026-02-25 05:55 | 2026-03-01 05:55 | 2026-03-05 05:55 | 2026-05-08 05:55 | 2026-05-05 05:55 | 19963 | 14488 | 2026-05-09 05:55 | 2026-07-05 05:55 | 45 | None | Monitor to plan | 5475 | 27.43% | 61 | On Time | 0 | 0 | 57 | Paid | 0 | 2026-03 | Monitor
ORD-0050 | PRJ-014 | Northgate Complex | Residential | SUP-11 | Orient Emergency Systems | Malaysia | CAT-02 | Outdoor Lighting | 2026-02-24 02:48 | 2026-03-02 02:48 | 2026-03-06 02:48 | 2026-05-16 02:48 | 2026-06-10 02:48 | 13261 | 8839 | 2026-06-10 02:48 | 2026-07-26 02:48 | 45 | Supplier lead time | Escalate supplier and confirm recovery date | 4422 | 33.35% | 96 | Late | 25 | 13261 | 46 | Paid | 0 | 2026-03 | P1
ORD-0339 | PRJ-009 | Iris Resort | Residential | SUP-08 | Gulf Smart Controls | UAE | CAT-04 | Emergency Lighting | 2026-02-27 23:37 | 2026-03-02 23:37 | 2026-03-06 23:37 | 2026-04-01 23:37 | 2026-04-01 23:37 | 19165 | 12895 | 2026-04-03 23:37 | 2026-05-03 23:37 | 30 | None | Monitor to plan | 6270 | 32.72% | 26 | On Time | 0 | 0 | 30 | Paid | 0 | 2026-03 | Monitor
ORD-0130 | PRJ-006 | Forum Center | Hospitality | SUP-08 | Gulf Smart Controls | UAE | CAT-06 | Electrical Accessories | 2026-03-03 10:30 | 2026-03-08 10:30 | 2026-03-09 10:30 | 2026-04-13 10:30 | 2026-04-26 10:30 | 10394 | 7017 | 2026-04-28 10:30 | 2026-06-11 10:30 | 30 | Shipping / customs | Review freight milestone and customs documents | 3377 | 32.49% | 48 | Late | 13 | 10394 | 44 | Paid | 0 | 2026-03 | P2
ORD-0086 | PRJ-009 | Iris Resort | Residential | SUP-03 | Phoenicia Electrical | Lebanon | CAT-05 | Architectural Fixtures | 2026-03-02 17:45 | 2026-03-08 17:45 | 2026-03-10 17:45 | 2026-04-07 17:45 | 2026-04-12 17:45 | 31685 | 23521 | 2026-04-15 17:45 | 2026-05-22 17:45 | 30 | None | Monitor to plan | 8164 | 25.77% | 33 | Late | 5 | 31685 | 37 | Paid | 0 | 2026-03 | P2
ORD-0221 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-02 | Levant Controls | Lebanon | CAT-03 | Lighting Controls | 2026-03-11 01:54 | 2026-03-12 01:54 | 2026-03-14 01:54 | 2026-04-05 01:54 | 2026-04-03 01:54 | 17899 | 12587 | 2026-04-08 01:54 | 2026-05-16 01:54 | 30 | None | Monitor to plan | 5312 | 29.68% | 20 | On Time | 0 | 0 | 38 | Paid | 0 | 2026-03 | Monitor
ORD-0376 | PRJ-001 | Atlas Hotel | Hospitality | SUP-10 | Pacific Fixtures | China | CAT-04 | Emergency Lighting | 2026-03-10 04:39 | 2026-03-17 04:39 | 2026-03-19 04:39 | 2026-06-10 04:39 | 2026-06-02 04:39 | 19295 | 14215 | 2026-06-02 04:39 | 2026-07-15 04:39 | 45 | None | Monitor to plan | 5080 | 26.33% | 75 | On Time | 0 | 0 | 43 | Paid | 0 | 2026-03 | Monitor
ORD-0030 | PRJ-011 | Keystone Residence | Hospitality | SUP-10 | Pacific Fixtures | China | CAT-02 | Outdoor Lighting | 2026-03-07 05:32 | 2026-03-15 05:32 | 2026-03-19 05:32 | 2026-06-11 05:32 | 2026-06-09 05:32 | 23798 | 16650 | 2026-06-10 05:32 | 2026-08-01 05:32 | 60 | Client approval | Confirm decision owner and approval deadline | 7148 | 30.04% | 82 | On Time | 0 | 0 | 52 | Paid | 0 | 2026-03 | Monitor
ORD-0262 | PRJ-009 | Iris Resort | Residential | SUP-04 | Anatolia Lighting | Turkey | CAT-03 | Lighting Controls | 2026-03-14 23:32 | 2026-03-18 23:32 | 2026-03-19 23:32 | 2026-04-21 23:32 | 2026-04-17 23:32 | 31968 | 26119 | 2026-04-23 23:32 |  | 60 | None | Monitor to plan | 5849 | 18.3% | 29 | On Time | 0 | 0 | 109.0191 | Overdue | 31968 | 2026-03 | P1
ORD-0072 | PRJ-004 | District Retail | Residential | SUP-08 | Gulf Smart Controls | UAE | CAT-01 | Indoor Lighting | 2026-03-17 11:05 | 2026-03-20 11:05 | 2026-03-20 11:05 | 2026-04-15 11:05 | 2026-04-15 11:05 | 11574 | 8685 | 2026-04-21 11:05 |  | 60 | None | Monitor to plan | 2889 | 24.96% | 26 | On Time | 0 | 0 | 111.538 | Overdue | 11574 | 2026-03 | P1
ORD-0054 | PRJ-015 | Olive Gardens | Public Sector | SUP-11 | Orient Emergency Systems | Malaysia | CAT-01 | Indoor Lighting | 2026-03-21 00:23 | 2026-03-23 00:23 | 2026-03-23 00:23 | 2026-05-25 00:23 | 2026-05-24 00:23 | 36084 | 29314 | 2026-05-29 00:23 | 2026-07-25 00:23 | 45 | None | Monitor to plan | 6770 | 18.76% | 62 | On Time | 0 | 0 | 57 | Paid | 0 | 2026-03 | Monitor
ORD-0210 | PRJ-009 | Iris Resort | Residential | SUP-06 | Alpine Illumination | Italy | CAT-05 | Architectural Fixtures | 2026-03-19 16:41 | 2026-03-23 16:41 | 2026-03-27 16:41 | 2026-05-22 16:41 | 2026-05-22 16:41 | 5951 | 4839 | 2026-05-28 16:41 | 2026-07-30 16:41 | 60 | None | Monitor to plan | 1112 | 18.69% | 56 | On Time | 0 | 0 | 63 | Paid | 0 | 2026-03 | Monitor
ORD-0382 | PRJ-004 | District Retail | Residential | SUP-01 | Cedar Components | Lebanon | CAT-04 | Emergency Lighting | 2026-03-18 05:46 | 2026-03-25 05:46 | 2026-03-29 05:46 | 2026-04-24 05:46 | 2026-04-27 05:46 | 17573 | 13623 | 2026-05-02 05:46 | 2026-06-03 05:46 | 30 | None | Monitor to plan | 3950 | 22.48% | 29 | Late | 3 | 17573 | 32 | Paid | 0 | 2026-03 | P3
ORD-0027 | PRJ-013 | Meridian Campus | Retail | SUP-09 | Pearl LED Works | China | CAT-02 | Outdoor Lighting | 2026-03-31 03:38 | 2026-04-02 03:38 | 2026-04-02 03:38 | 2026-06-09 03:38 | 2026-06-03 03:38 | 24853 | 19100 | 2026-06-09 03:38 |  | 60 | None | Monitor to plan | 5753 | 23.15% | 62 | On Time | 0 | 0 | 62.8489 | Overdue | 24853 | 2026-04 | P1
ORD-0082 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-10 | Pacific Fixtures | China | CAT-02 | Outdoor Lighting | 2026-03-28 10:44 | 2026-03-30 10:44 | 2026-04-03 10:44 | 2026-06-28 10:44 | 2026-07-03 10:44 | 18102 | 14256 | 2026-07-08 10:44 |  | 45 | Shipping / customs | Review freight milestone and customs documents | 3846 | 21.25% | 91 | Late | 5 | 18102 | 33.5526 | Open | 18102 | 2026-04 | P3
ORD-0051 | PRJ-007 | Garden Villas | Commercial | SUP-02 | Levant Controls | Lebanon | CAT-05 | Architectural Fixtures | 2026-03-25 15:59 | 2026-03-30 15:59 | 2026-04-03 15:59 | 2026-05-04 15:59 | 2026-05-03 15:59 | 15882 | 11034 | 2026-05-03 15:59 | 2026-05-23 15:59 | 30 | None | Monitor to plan | 4848 | 30.53% | 30 | On Time | 0 | 0 | 20 | Paid | 0 | 2026-04 | Monitor
ORD-0061 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-10 | Pacific Fixtures | China | CAT-01 | Indoor Lighting | 2026-03-29 23:29 | 2026-03-31 23:29 | 2026-04-04 23:29 | 2026-06-25 23:29 | 2026-06-20 23:29 | 28575 | 19677 | 2026-06-26 23:29 |  | 60 | None | Monitor to plan | 8898 | 31.14% | 77 | On Time | 0 | 0 | 45.0213 | Open | 28575 | 2026-04 | Monitor
ORD-0172 | PRJ-002 | Beacon Offices | Commercial | SUP-02 | Levant Controls | Lebanon | CAT-01 | Indoor Lighting | 2026-03-29 14:02 | 2026-04-04 14:02 | 2026-04-06 14:02 | 2026-04-24 14:02 | 2026-04-17 14:02 | 38223 | 30506 | 2026-04-21 14:02 |  | 60 | None | Monitor to plan | 7717 | 20.19% | 11 | On Time | 0 | 0 | 111.4153 | Overdue | 38223 | 2026-04 | P1
ORD-0363 | PRJ-004 | District Retail | Residential | SUP-09 | Pearl LED Works | China | CAT-01 | Indoor Lighting | 2026-03-31 00:34 | 2026-04-05 00:34 | 2026-04-09 00:34 | 2026-06-16 00:34 | 2026-06-10 00:34 | 8351 | 5812 | 2026-06-12 00:34 | 2026-07-05 00:34 | 30 | None | Monitor to plan | 2539 | 30.4% | 62 | On Time | 0 | 0 | 23 | Paid | 0 | 2026-04 | Monitor
ORD-0085 | PRJ-015 | Olive Gardens | Public Sector | SUP-07 | Nordic Beam | Germany | CAT-06 | Electrical Accessories | 2026-04-04 15:21 | 2026-04-07 15:21 | 2026-04-10 15:21 | 2026-06-09 15:21 | 2026-06-01 15:21 | 5537 | 4389 | 2026-06-06 15:21 | 2026-08-04 15:21 | 45 | None | Monitor to plan | 1148 | 20.73% | 52 | On Time | 0 | 0 | 59 | Paid | 0 | 2026-04 | Monitor
ORD-0387 | PRJ-008 | Harbor Offices | Retail | SUP-01 | Cedar Components | Lebanon | CAT-02 | Outdoor Lighting | 2026-04-04 21:44 | 2026-04-10 21:44 | 2026-04-11 21:44 | 2026-05-06 21:44 | 2026-05-05 21:44 | 34266 | 26837 | 2026-05-11 21:44 | 2026-06-01 21:44 | 30 | None | Monitor to plan | 7429 | 21.68% | 24 | On Time | 0 | 0 | 21 | Paid | 0 | 2026-04 | Monitor
ORD-0031 | PRJ-015 | Olive Gardens | Public Sector | SUP-12 | Atlas Outdoor | Spain | CAT-05 | Architectural Fixtures | 2026-04-06 22:58 | 2026-04-07 22:58 | 2026-04-11 22:58 | 2026-06-06 22:58 | 2026-05-30 22:58 | 23805 | 17087 | 2026-06-02 22:58 |  | 45 | None | Monitor to plan | 6718 | 28.22% | 49 | On Time | 0 | 0 | 69.043 | Overdue | 23805 | 2026-04 | P1
ORD-0242 | PRJ-015 | Olive Gardens | Public Sector | SUP-11 | Orient Emergency Systems | Malaysia | CAT-04 | Emergency Lighting | 2026-04-07 01:12 | 2026-04-13 01:12 | 2026-04-15 01:12 | 2026-06-27 01:12 | 2026-06-23 01:12 | 9287 | 7603 | 2026-06-23 01:12 | 2026-07-28 01:12 | 30 | None | Monitor to plan | 1684 | 18.13% | 69 | On Time | 0 | 0 | 35 | Paid | 0 | 2026-04 | Monitor
ORD-0154 | PRJ-015 | Olive Gardens | Public Sector | SUP-12 | Atlas Outdoor | Spain | CAT-02 | Outdoor Lighting | 2026-03-31 06:07 | 2026-04-15 06:07 | 2026-04-15 06:07 | 2026-06-07 06:07 | 2026-06-07 06:07 | 42701 | 33253 | 2026-06-08 06:07 |  | 30 | Client approval | Confirm decision owner and approval deadline | 9448 | 22.13% | 53 | On Time | 0 | 0 | 63.7448 | Overdue | 42701 | 2026-04 | P1
ORD-0369 | PRJ-011 | Keystone Residence | Hospitality | SUP-12 | Atlas Outdoor | Spain | CAT-03 | Lighting Controls | 2026-03-25 06:43 | 2026-04-15 06:43 | 2026-04-16 06:43 | 2026-06-16 06:43 | 2026-06-22 06:43 | 8647 | 6726 | 2026-06-26 06:43 |  | 45 | Client approval | Confirm decision owner and approval deadline | 1921 | 22.22% | 67 | Late | 6 | 8647 | 45.7202 | Overdue | 8647 | 2026-04 | P1
ORD-0021 | PRJ-002 | Beacon Offices | Commercial | SUP-03 | Phoenicia Electrical | Lebanon | CAT-05 | Architectural Fixtures | 2026-04-12 10:50 | 2026-04-13 10:50 | 2026-04-16 10:50 | 2026-05-12 10:50 | 2026-05-09 10:50 | 43832 | 30259 | 2026-05-14 10:50 | 2026-06-21 10:50 | 45 | None | Monitor to plan | 13573 | 30.97% | 23 | On Time | 0 | 0 | 38 | Paid | 0 | 2026-04 | Monitor
ORD-0261 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-03 | Phoenicia Electrical | Lebanon | CAT-02 | Outdoor Lighting | 2026-04-12 11:33 | 2026-04-14 11:33 | 2026-04-16 11:33 | 2026-05-12 11:33 | 2026-05-08 11:33 | 15463 | 10608 | 2026-05-13 11:33 | 2026-07-03 11:33 | 45 | None | Monitor to plan | 4855 | 31.4% | 22 | On Time | 0 | 0 | 51 | Paid | 0 | 2026-04 | Monitor
ORD-0011 | PRJ-004 | District Retail | Residential | SUP-05 | Aegean Systems | Greece | CAT-02 | Outdoor Lighting | 2026-04-12 19:41 | 2026-04-13 19:41 | 2026-04-17 19:41 | 2026-06-01 19:41 | 2026-06-06 19:41 | 18995 | 14857 | 2026-06-11 19:41 | 2026-08-02 19:41 | 60 | Documentation | Complete missing document and revalidate order | 4138 | 21.78% | 50 | Late | 5 | 18995 | 52 | Paid | 0 | 2026-04 | P3
ORD-0182 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-11 | Orient Emergency Systems | Malaysia | CAT-03 | Lighting Controls | 2026-04-11 00:28 | 2026-04-16 00:28 | 2026-04-20 00:28 | 2026-07-01 00:28 | 2026-06-28 00:28 | 23257 | 18471 | 2026-06-29 00:28 |  | 30 | None | Monitor to plan | 4786 | 20.58% | 69 | On Time | 0 | 0 | 42.9809 | Overdue | 23257 | 2026-04 | P1
ORD-0388 | PRJ-010 | Juniper Mall | Public Sector | SUP-08 | Gulf Smart Controls | UAE | CAT-03 | Lighting Controls | 2026-04-01 03:15 | 2026-04-19 03:15 | 2026-04-20 03:15 | 2026-05-27 03:15 | 2026-05-19 03:15 | 25528 | 20119 | 2026-05-19 03:15 | 2026-07-09 03:15 | 45 | Client approval | Confirm decision owner and approval deadline | 5409 | 21.19% | 29 | On Time | 0 | 0 | 51 | Paid | 0 | 2026-04 | Monitor
ORD-0300 | PRJ-015 | Olive Gardens | Public Sector | SUP-08 | Gulf Smart Controls | UAE | CAT-04 | Emergency Lighting | 2026-04-12 20:10 | 2026-04-18 20:10 | 2026-04-21 20:10 | 2026-05-18 20:10 | 2026-05-15 20:10 | 30689 | 23909 | 2026-05-20 20:10 | 2026-06-24 20:10 | 30 | None | Monitor to plan | 6780 | 22.09% | 24 | On Time | 0 | 0 | 35 | Paid | 0 | 2026-04 | Monitor
ORD-0410 | PRJ-005 | Elm Hospital | Public Sector | SUP-11 | Orient Emergency Systems | Malaysia | CAT-04 | Emergency Lighting | 2026-04-14 21:47 | 2026-04-21 21:47 | 2026-04-21 21:47 | 2026-06-28 21:47 | 2026-06-27 21:47 | 4423 | 3427 | 2026-06-28 21:47 | 2026-08-06 21:47 | 45 | None | Monitor to plan | 996 | 22.52% | 67 | On Time | 0 | 0 | 39 | Paid | 0 | 2026-04 | Monitor
ORD-0142 | PRJ-008 | Harbor Offices | Retail | SUP-12 | Atlas Outdoor | Spain | CAT-04 | Emergency Lighting | 2026-04-14 07:41 | 2026-04-21 07:41 | 2026-04-22 07:41 | 2026-06-21 07:41 | 2026-06-14 07:41 | 25872 | 19456 | 2026-06-14 07:41 | 2026-07-24 07:41 | 45 | None | Monitor to plan | 6416 | 24.8% | 53 | On Time | 0 | 0 | 40 | Paid | 0 | 2026-04 | Monitor
ORD-0103 | PRJ-013 | Meridian Campus | Retail | SUP-11 | Orient Emergency Systems | Malaysia | CAT-04 | Emergency Lighting | 2026-04-20 07:22 | 2026-04-24 07:22 | 2026-04-24 07:22 | 2026-07-08 07:22 | 2026-07-04 07:22 | 13454 | 9823 | 2026-07-07 07:22 |  | 60 | None | Monitor to plan | 3631 | 26.99% | 71 | On Time | 0 | 0 | 34.6931 | Open | 13454 | 2026-04 | Monitor
ORD-0081 | PRJ-007 | Garden Villas | Commercial | SUP-10 | Pacific Fixtures | China | CAT-06 | Electrical Accessories | 2026-04-20 12:55 | 2026-04-23 12:55 | 2026-04-25 12:55 | 2026-07-17 12:55 | 2026-07-12 12:55 | 24566 | 16987 | 2026-07-18 12:55 | 2026-08-09 12:55 | 45 | None | Monitor to plan | 7579 | 30.85% | 78 | On Time | 0 | 0 | 22 | Paid | 0 | 2026-04 | Monitor
ORD-0216 | PRJ-001 | Atlas Hotel | Hospitality | SUP-05 | Aegean Systems | Greece | CAT-06 | Electrical Accessories | 2026-04-19 21:03 | 2026-04-24 21:03 | 2026-04-25 21:03 | 2026-06-12 21:03 | 2026-06-08 21:03 | 20000 | 15262 | 2026-06-12 21:03 | 2026-07-11 21:03 | 30 | None | Monitor to plan | 4738 | 23.69% | 44 | On Time | 0 | 0 | 29 | Paid | 0 | 2026-04 | Monitor
ORD-0170 | PRJ-015 | Olive Gardens | Public Sector | SUP-06 | Alpine Illumination | Italy | CAT-06 | Electrical Accessories | 2026-04-26 09:13 | 2026-05-02 09:13 | 2026-05-02 09:13 | 2026-06-15 09:13 | 2026-06-23 09:13 | 16517 | 13518 | 2026-06-29 09:13 |  | 30 | None | Monitor to plan | 2999 | 18.16% | 52 | Late | 8 | 16517 | 42.6161 | Overdue | 16517 | 2026-05 | P1
ORD-0332 | PRJ-005 | Elm Hospital | Public Sector | SUP-11 | Orient Emergency Systems | Malaysia | CAT-06 | Electrical Accessories | 2026-04-26 16:32 | 2026-05-02 16:32 | 2026-05-04 16:32 | 2026-07-18 16:32 | 2026-07-27 16:32 | 5824 | 4142 | 2026-07-28 16:32 |  | 60 | None | Monitor to plan | 1682 | 28.88% | 84 | Late | 9 | 5824 | 13.3113 | Open | 5824 | 2026-05 | P2
ORD-0276 | PRJ-008 | Harbor Offices | Retail | SUP-05 | Aegean Systems | Greece | CAT-04 | Emergency Lighting | 2026-04-28 20:39 | 2026-05-01 20:39 | 2026-05-05 20:39 | 2026-06-24 20:39 | 2026-07-08 20:39 | 11515 | 7794 | 2026-07-08 20:39 |  | 60 | Shipping / customs | Review freight milestone and customs documents | 3721 | 32.31% | 64 | Late | 14 | 11515 | 33.1396 | Open | 11515 | 2026-05 | P2
ORD-0272 | PRJ-001 | Atlas Hotel | Hospitality | SUP-12 | Atlas Outdoor | Spain | CAT-01 | Indoor Lighting | 2026-04-09 05:46 | 2026-05-04 05:46 | 2026-05-06 05:46 | 2026-06-28 05:46 | 2026-06-28 05:46 | 7946 | 6054 | 2026-07-01 05:46 |  | 30 | Client approval | Confirm decision owner and approval deadline | 1892 | 23.81% | 53 | On Time | 0 | 0 | 40.7595 | Overdue | 7946 | 2026-05 | P1
ORD-0019 | PRJ-009 | Iris Resort | Residential | SUP-03 | Phoenicia Electrical | Lebanon | CAT-04 | Emergency Lighting | 2026-05-02 19:57 | 2026-05-04 19:57 | 2026-05-06 19:57 | 2026-06-02 19:57 | 2026-05-26 19:57 | 31436 | 24808 | 2026-05-30 19:57 | 2026-08-09 19:57 | 60 | None | Monitor to plan | 6628 | 21.08% | 20 | On Time | 0 | 0 | 71 | Paid | 0 | 2026-05 | Monitor
ORD-0167 | PRJ-004 | District Retail | Residential | SUP-02 | Levant Controls | Lebanon | CAT-01 | Indoor Lighting | 2026-04-30 07:19 | 2026-05-06 07:19 | 2026-05-08 07:19 | 2026-05-28 07:19 | 2026-05-20 07:19 | 29993 | 23047 | 2026-05-21 07:19 | 2026-07-13 07:19 | 45 | None | Monitor to plan | 6946 | 23.16% | 12 | On Time | 0 | 0 | 53 | Paid | 0 | 2026-05 | Monitor
ORD-0022 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-08 | Gulf Smart Controls | UAE | CAT-03 | Lighting Controls | 2026-05-06 02:10 | 2026-05-09 02:10 | 2026-05-10 02:10 | 2026-06-06 02:10 | 2026-06-04 02:10 | 35204 | 23436 | 2026-06-05 02:10 |  | 30 | None | Monitor to plan | 11768 | 33.43% | 25 | On Time | 0 | 0 | 66.9097 | Overdue | 35204 | 2026-05 | P1
ORD-0207 | PRJ-010 | Juniper Mall | Public Sector | SUP-01 | Cedar Components | Lebanon | CAT-03 | Lighting Controls | 2026-05-07 06:45 | 2026-05-10 06:45 | 2026-05-10 06:45 | 2026-05-26 06:45 | 2026-05-19 06:45 | 7635 | 6172 | 2026-05-20 06:45 | 2026-06-27 06:45 | 30 | None | Monitor to plan | 1463 | 19.16% | 9 | On Time | 0 | 0 | 38 | Paid | 0 | 2026-05 | Monitor
ORD-0131 | PRJ-011 | Keystone Residence | Hospitality | SUP-01 | Cedar Components | Lebanon | CAT-04 | Emergency Lighting | 2026-04-30 13:15 | 2026-05-07 13:15 | 2026-05-10 13:15 | 2026-05-28 13:15 | 2026-05-26 13:15 | 5249 | 3564 | 2026-05-27 13:15 | 2026-07-17 13:15 | 45 | None | Monitor to plan | 1685 | 32.1% | 16 | On Time | 0 | 0 | 51 | Paid | 0 | 2026-05 | Monitor
ORD-0254 | PRJ-005 | Elm Hospital | Public Sector | SUP-10 | Pacific Fixtures | China | CAT-06 | Electrical Accessories | 2026-05-08 17:14 | 2026-05-09 17:14 | 2026-05-11 17:14 | 2026-08-04 17:14 | 2026-07-31 17:14 | 21589 | 16433 | 2026-08-05 17:14 |  | 45 | None | Monitor to plan | 5156 | 23.88% | 81 | On Time | 0 | 0 | 5.2819 | Open | 21589 | 2026-05 | Monitor
ORD-0045 | PRJ-004 | District Retail | Residential | SUP-05 | Aegean Systems | Greece | CAT-04 | Emergency Lighting | 2026-05-09 16:29 | 2026-05-10 16:29 | 2026-05-12 16:29 | 2026-06-30 16:29 | 2026-07-15 16:29 | 22737 | 16803 | 2026-07-20 16:29 |  | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 5934 | 26.1% | 64 | Late | 15 | 22737 | 21.313 | Open | 22737 | 2026-05 | P1
ORD-0174 | PRJ-010 | Juniper Mall | Public Sector | SUP-08 | Gulf Smart Controls | UAE | CAT-04 | Emergency Lighting | 2026-05-07 11:42 | 2026-05-13 11:42 | 2026-05-13 11:42 | 2026-06-20 11:42 | 2026-06-24 11:42 | 23122 | 15667 | 2026-06-25 11:42 |  | 45 | Documentation | Complete missing document and revalidate order | 7455 | 32.24% | 42 | Late | 4 | 23122 | 46.5125 | Overdue | 23122 | 2026-05 | P1
ORD-0084 | PRJ-002 | Beacon Offices | Commercial | SUP-02 | Levant Controls | Lebanon | CAT-04 | Emergency Lighting | 2026-05-07 15:22 | 2026-05-09 15:22 | 2026-05-13 15:22 | 2026-06-13 15:22 | 2026-06-26 15:22 | 10388 | 7215 | 2026-06-30 15:22 |  | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 3173 | 30.54% | 44 | Late | 13 | 10388 | 41.3598 | Overdue | 10388 | 2026-05 | P1
ORD-0205 | PRJ-010 | Juniper Mall | Public Sector | SUP-08 | Gulf Smart Controls | UAE | CAT-02 | Outdoor Lighting | 2026-05-08 10:11 | 2026-05-15 10:11 | 2026-05-15 10:11 | 2026-06-12 10:11 | 2026-06-10 10:11 | 36427 | 27155 | 2026-06-12 10:11 |  | 60 | None | Monitor to plan | 9272 | 25.45% | 26 | On Time | 0 | 0 | 59.5754 | Open | 36427 | 2026-05 | Monitor
ORD-0238 | PRJ-008 | Harbor Offices | Retail | SUP-07 | Nordic Beam | Germany | CAT-04 | Emergency Lighting | 2026-04-27 02:28 | 2026-05-13 02:28 | 2026-05-16 02:28 | 2026-07-10 02:28 | 2026-07-13 02:28 | 13887 | 9796 | 2026-07-14 02:28 |  | 60 | Client approval | Confirm decision owner and approval deadline | 4091 | 29.46% | 58 | Late | 3 | 13887 | 27.897 | Open | 13887 | 2026-05 | P3
ORD-0389 | PRJ-014 | Northgate Complex | Residential | SUP-02 | Levant Controls | Lebanon | CAT-04 | Emergency Lighting | 2026-05-12 22:11 | 2026-05-15 22:11 | 2026-05-16 22:11 | 2026-06-15 22:11 | 2026-06-11 22:11 | 18791 | 12348 | 2026-06-16 22:11 |  | 60 | None | Monitor to plan | 6443 | 34.29% | 26 | On Time | 0 | 0 | 55.076 | Open | 18791 | 2026-05 | Monitor
ORD-0252 | PRJ-014 | Northgate Complex | Residential | SUP-02 | Levant Controls | Lebanon | CAT-04 | Emergency Lighting | 2026-05-22 11:22 | 2026-05-23 11:22 | 2026-05-23 11:22 | 2026-06-16 11:22 | 2026-06-15 11:22 | 29070 | 20188 | 2026-06-18 11:22 | 2026-08-03 11:22 | 45 | None | Monitor to plan | 8882 | 30.55% | 23 | On Time | 0 | 0 | 46 | Paid | 0 | 2026-05 | Monitor
ORD-0100 | PRJ-009 | Iris Resort | Residential | SUP-03 | Phoenicia Electrical | Lebanon | CAT-06 | Electrical Accessories | 2026-05-17 13:39 | 2026-05-22 13:39 | 2026-05-23 13:39 | 2026-06-21 13:39 | 2026-06-18 13:39 | 24007 | 18778 | 2026-06-18 13:39 | 2026-07-12 13:39 | 30 | None | Monitor to plan | 5229 | 21.78% | 26 | On Time | 0 | 0 | 24 | Paid | 0 | 2026-05 | Monitor
ORD-0232 | PRJ-006 | Forum Center | Hospitality | SUP-08 | Gulf Smart Controls | UAE | CAT-05 | Architectural Fixtures | 2026-05-17 03:40 | 2026-05-21 03:40 | 2026-05-24 03:40 | 2026-07-01 03:40 | 2026-07-20 03:40 | 43809 | 34330 | 2026-07-24 03:40 |  | 60 | Supplier lead time | Escalate supplier and confirm recovery date | 9479 | 21.64% | 57 | Late | 19 | 43809 | 17.8473 | Open | 43809 | 2026-05 | P1
ORD-0346 | PRJ-005 | Elm Hospital | Public Sector | SUP-04 | Anatolia Lighting | Turkey | CAT-02 | Outdoor Lighting | 2026-05-21 08:14 | 2026-05-23 08:14 | 2026-05-25 08:14 | 2026-07-04 08:14 | 2026-07-04 08:14 | 21983 | 14369 | 2026-07-05 08:14 | 2026-07-30 08:14 | 30 | None | Monitor to plan | 7614 | 34.64% | 40 | On Time | 0 | 0 | 25 | Paid | 0 | 2026-05 | Monitor
ORD-0350 | PRJ-013 | Meridian Campus | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-06 | Electrical Accessories | 2026-05-23 03:05 | 2026-05-25 03:05 | 2026-05-26 03:05 | 2026-06-24 03:05 | 2026-06-30 03:05 | 10134 | 7184 | 2026-07-03 03:05 |  | 45 | None | Monitor to plan | 2950 | 29.11% | 35 | Late | 6 | 10134 | 38.8715 | Open | 10134 | 2026-05 | P3
ORD-0317 | PRJ-001 | Atlas Hotel | Hospitality | SUP-09 | Pearl LED Works | China | CAT-05 | Architectural Fixtures | 2026-05-21 06:48 | 2026-05-24 06:48 | 2026-05-26 06:48 | 2026-08-11 06:48 |  | 10598 | 8647 |  |  | 45 | Payment blocker | Coordinate payment release with finance | 1951 | 18.41% | 76.717 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-05 | Monitor
ORD-0135 | PRJ-006 | Forum Center | Hospitality | SUP-03 | Phoenicia Electrical | Lebanon | CAT-05 | Architectural Fixtures | 2026-05-18 10:10 | 2026-05-25 10:10 | 2026-05-29 10:10 | 2026-06-26 10:10 | 2026-06-22 10:10 | 7309 | 5633 | 2026-06-24 10:10 | 2026-08-03 10:10 | 45 | None | Monitor to plan | 1676 | 22.93% | 24 | On Time | 0 | 0 | 40 | Paid | 0 | 2026-05 | Monitor
ORD-0063 | PRJ-015 | Olive Gardens | Public Sector | SUP-03 | Phoenicia Electrical | Lebanon | CAT-06 | Electrical Accessories | 2026-05-24 06:38 | 2026-05-28 06:38 | 2026-05-30 06:38 | 2026-06-29 06:38 | 2026-06-25 06:38 | 11477 | 8810 | 2026-06-30 06:38 |  | 60 | None | Monitor to plan | 2667 | 23.24% | 26 | On Time | 0 | 0 | 41.7236 | Open | 11477 | 2026-05 | Monitor
ORD-0322 | PRJ-011 | Keystone Residence | Hospitality | SUP-03 | Phoenicia Electrical | Lebanon | CAT-02 | Outdoor Lighting | 2026-05-24 21:12 | 2026-05-30 21:12 | 2026-06-01 21:12 | 2026-06-17 21:12 | 2026-06-12 21:12 | 16080 | 11288 | 2026-06-17 21:12 | 2026-06-27 21:12 | 60 | None | Monitor to plan | 4792 | 29.8% | 11 | On Time | 0 | 0 | 10 | Paid | 0 | 2026-06 | Monitor
ORD-0340 | PRJ-001 | Atlas Hotel | Hospitality | SUP-12 | Atlas Outdoor | Spain | CAT-03 | Lighting Controls | 2026-05-17 21:36 | 2026-05-30 21:36 | 2026-06-01 21:36 | 2026-07-26 21:36 | 2026-07-25 21:36 | 22301 | 17215 | 2026-07-27 21:36 |  | 30 | Client approval | Confirm decision owner and approval deadline | 5086 | 22.81% | 54 | On Time | 0 | 0 | 14.0999 | Open | 22301 | 2026-06 | Monitor
ORD-0059 | PRJ-014 | Northgate Complex | Residential | SUP-04 | Anatolia Lighting | Turkey | CAT-02 | Outdoor Lighting | 2026-05-27 15:47 | 2026-06-02 15:47 | 2026-06-03 15:47 | 2026-07-12 15:47 | 2026-07-11 15:47 | 21844 | 14792 | 2026-07-13 15:47 | 2026-08-07 15:47 | 45 | Documentation | Complete missing document and revalidate order | 7052 | 32.28% | 38 | On Time | 0 | 0 | 25 | Paid | 0 | 2026-06 | Monitor
ORD-0335 | PRJ-004 | District Retail | Residential | SUP-04 | Anatolia Lighting | Turkey | CAT-05 | Architectural Fixtures | 2026-05-30 04:57 | 2026-05-31 04:57 | 2026-06-04 04:57 | 2026-07-10 04:57 | 2026-07-06 04:57 | 43065 | 31223 | 2026-07-11 04:57 |  | 30 | None | Monitor to plan | 11842 | 27.5% | 32 | On Time | 0 | 0 | 30.7936 | Overdue | 43065 | 2026-06 | P1
ORD-0110 | PRJ-005 | Elm Hospital | Public Sector | SUP-07 | Nordic Beam | Germany | CAT-06 | Electrical Accessories | 2026-05-28 19:35 | 2026-05-31 19:35 | 2026-06-04 19:35 | 2026-07-28 19:35 | 2026-07-31 19:35 | 18613 | 14262 | 2026-08-02 19:35 |  | 60 | Payment blocker | Coordinate payment release with finance | 4351 | 23.38% | 57 | Late | 3 | 18613 | 8.1839 | Open | 18613 | 2026-06 | P3
ORD-0404 | PRJ-003 | Cedar Residence | Retail | SUP-12 | Atlas Outdoor | Spain | CAT-05 | Architectural Fixtures | 2026-06-05 09:47 | 2026-06-06 09:47 | 2026-06-06 09:47 | 2026-07-31 09:47 | 2026-07-27 09:47 | 57681 | 41851 | 2026-07-29 09:47 |  | 30 | None | Monitor to plan | 15830 | 27.44% | 51 | On Time | 0 | 0 | 12.5921 | Open | 57681 | 2026-06 | Monitor
ORD-0198 | PRJ-009 | Iris Resort | Residential | SUP-06 | Alpine Illumination | Italy | CAT-02 | Outdoor Lighting | 2026-05-30 13:25 | 2026-06-02 13:25 | 2026-06-06 13:25 | 2026-07-28 13:25 | 2026-08-07 13:25 | 36310 | 29146 | 2026-08-11 13:25 |  | 30 | None | Monitor to plan | 7164 | 19.73% | 62 | Late | 10 | 36310 | -0.55911 | Open | 36310 | 2026-06 | P2
ORD-0077 | PRJ-008 | Harbor Offices | Retail | SUP-05 | Aegean Systems | Greece | CAT-06 | Electrical Accessories | 2026-06-04 14:06 | 2026-06-07 14:06 | 2026-06-07 14:06 | 2026-07-16 14:06 | 2026-07-10 14:06 | 11210 | 7691 | 2026-07-11 14:06 |  | 45 | None | Monitor to plan | 3519 | 31.39% | 33 | On Time | 0 | 0 | 30.4125 | Open | 11210 | 2026-06 | Monitor
ORD-0233 | PRJ-006 | Forum Center | Hospitality | SUP-06 | Alpine Illumination | Italy | CAT-02 | Outdoor Lighting | 2026-06-04 21:52 | 2026-06-09 21:52 | 2026-06-11 21:52 | 2026-07-25 21:52 | 2026-07-19 21:52 | 29021 | 19698 | 2026-07-24 21:52 |  | 30 | None | Monitor to plan | 9323 | 32.13% | 38 | On Time | 0 | 0 | 17.0892 | Open | 29021 | 2026-06 | Monitor
ORD-0301 | PRJ-007 | Garden Villas | Commercial | SUP-07 | Nordic Beam | Germany | CAT-03 | Lighting Controls | 2026-06-10 10:56 | 2026-06-13 10:56 | 2026-06-13 10:56 | 2026-08-15 10:56 |  | 25577 | 20141 |  |  | 45 | None | Monitor to plan | 5436 | 21.25% | 58.5443 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-06 | Monitor
ORD-0109 | PRJ-009 | Iris Resort | Residential | SUP-01 | Cedar Components | Lebanon | CAT-04 | Emergency Lighting | 2026-06-10 07:12 | 2026-06-15 07:12 | 2026-06-15 07:12 | 2026-07-04 07:12 | 2026-07-03 07:12 | 16504 | 12333 | 2026-07-08 07:12 |  | 30 | Documentation | Complete missing document and revalidate order | 4171 | 25.27% | 18 | On Time | 0 | 0 | 33.6999 | Overdue | 16504 | 2026-06 | P1
ORD-0162 | PRJ-001 | Atlas Hotel | Hospitality | SUP-11 | Orient Emergency Systems | Malaysia | CAT-03 | Lighting Controls | 2026-05-26 23:27 | 2026-06-15 23:27 | 2026-06-18 23:27 | 2026-08-28 23:27 |  | 14171 | 11407 |  |  | 30 | Client approval | Confirm decision owner and approval deadline | 2764 | 19.5% | 53.0227 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-06 | Monitor
ORD-0328 | PRJ-015 | Olive Gardens | Public Sector | SUP-02 | Levant Controls | Lebanon | CAT-05 | Architectural Fixtures | 2026-06-16 14:39 | 2026-06-19 14:39 | 2026-06-19 14:39 | 2026-07-17 14:39 |  | 33386 | 22989 |  |  | 45 | None | Monitor to plan | 10397 | 31.14% | 52.3895 | Open | 24.3895 | 33386 |  | Not Invoiced | 0 | 2026-06 | P1
ORD-0253 | PRJ-001 | Atlas Hotel | Hospitality | SUP-11 | Orient Emergency Systems | Malaysia | CAT-01 | Indoor Lighting | 2026-06-04 04:33 | 2026-06-19 04:33 | 2026-06-20 04:33 | 2026-09-01 04:33 |  | 24245 | 16480 |  |  | 30 | Client approval | Confirm decision owner and approval deadline | 7765 | 32.03% | 51.8105 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-06 | Monitor
ORD-0144 | PRJ-004 | District Retail | Residential | SUP-11 | Orient Emergency Systems | Malaysia | CAT-04 | Emergency Lighting | 2026-06-15 23:18 | 2026-06-18 23:18 | 2026-06-20 23:18 | 2026-08-20 23:18 |  | 8142 | 5646 |  |  | 45 | Documentation | Complete missing document and revalidate order | 2496 | 30.66% | 51.029 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-06 | Monitor
ORD-0197 | PRJ-007 | Garden Villas | Commercial | SUP-11 | Orient Emergency Systems | Malaysia | CAT-02 | Outdoor Lighting | 2026-06-17 05:15 | 2026-06-22 05:15 | 2026-06-22 05:15 | 2026-08-25 05:15 |  | 6010 | 4869 |  |  | 60 | None | Monitor to plan | 1141 | 18.99% | 49.7811 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-06 | Monitor
ORD-0288 | PRJ-004 | District Retail | Residential | SUP-04 | Anatolia Lighting | Turkey | CAT-04 | Emergency Lighting | 2026-06-15 06:42 | 2026-06-22 06:42 | 2026-06-23 06:42 | 2026-08-02 06:42 | 2026-08-04 06:42 | 29249 | 21375 | 2026-08-04 06:42 |  | 60 | Payment blocker | Coordinate payment release with finance | 7874 | 26.92% | 42 | Late | 2 | 29249 | 6.7206 | Open | 29249 | 2026-06 | P2
ORD-0277 | PRJ-002 | Beacon Offices | Commercial | SUP-12 | Atlas Outdoor | Spain | CAT-03 | Lighting Controls | 2026-06-22 14:37 | 2026-06-23 14:37 | 2026-06-25 14:37 | 2026-08-22 14:37 |  | 4385 | 2860 |  |  | 30 | None | Monitor to plan | 1525 | 34.78% | 46.391 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-06 | Monitor
ORD-0385 | PRJ-009 | Iris Resort | Residential | SUP-08 | Gulf Smart Controls | UAE | CAT-05 | Architectural Fixtures | 2026-06-06 17:07 | 2026-06-23 17:07 | 2026-06-25 17:07 | 2026-07-23 17:07 | 2026-07-23 17:07 | 44498 | 35020 | 2026-07-24 17:07 | 2026-08-03 17:07 | 45 | Client approval | Confirm decision owner and approval deadline | 9478 | 21.3% | 28 | On Time | 0 | 0 | 10 | Paid | 0 | 2026-06 | Monitor
ORD-0165 | PRJ-007 | Garden Villas | Commercial | SUP-03 | Phoenicia Electrical | Lebanon | CAT-05 | Architectural Fixtures | 2026-06-21 03:20 | 2026-06-24 03:20 | 2026-06-26 03:20 | 2026-07-23 03:20 |  | 51650 | 41411 |  |  | 30 | None | Monitor to plan | 10239 | 19.82% | 45.8612 | Open | 18.8612 | 51650 |  | Not Invoiced | 0 | 2026-06 | P1
ORD-0278 | PRJ-003 | Cedar Residence | Retail | SUP-09 | Pearl LED Works | China | CAT-04 | Emergency Lighting | 2026-06-17 00:07 | 2026-06-23 00:07 | 2026-06-27 00:07 | 2026-09-06 00:07 |  | 7782 | 5679 |  |  | 30 | Payment blocker | Coordinate payment release with finance | 2103 | 27.02% | 44.9953 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-06 | Monitor
ORD-0149 | PRJ-011 | Keystone Residence | Hospitality | SUP-12 | Atlas Outdoor | Spain | CAT-06 | Electrical Accessories | 2026-06-18 16:10 | 2026-06-25 16:10 | 2026-06-27 16:10 | 2026-08-16 16:10 |  | 18961 | 13746 |  |  | 45 | None | Monitor to plan | 5215 | 27.5% | 44.3265 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-06 | Monitor
ORD-0215 | PRJ-011 | Keystone Residence | Hospitality | SUP-11 | Orient Emergency Systems | Malaysia | CAT-01 | Indoor Lighting | 2026-06-22 06:19 | 2026-06-28 06:19 | 2026-06-29 06:19 | 2026-08-29 06:19 |  | 10283 | 7617 |  |  | 30 | None | Monitor to plan | 2666 | 25.93% | 42.7368 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-06 | Monitor
ORD-0391 | PRJ-010 | Juniper Mall | Public Sector | SUP-07 | Nordic Beam | Germany | CAT-06 | Electrical Accessories | 2026-06-27 04:21 | 2026-06-30 04:21 | 2026-06-30 04:21 | 2026-08-29 04:21 |  | 6757 | 4606 |  |  | 45 | None | Monitor to plan | 2151 | 31.83% | 41.8189 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-06 | Monitor
ORD-0101 | PRJ-011 | Keystone Residence | Hospitality | SUP-03 | Phoenicia Electrical | Lebanon | CAT-04 | Emergency Lighting | 2026-06-23 04:39 | 2026-06-30 04:39 | 2026-06-30 04:39 | 2026-07-23 04:39 | 2026-07-23 04:39 | 29357 | 20493 | 2026-07-27 04:39 |  | 60 | Documentation | Complete missing document and revalidate order | 8864 | 30.19% | 23 | On Time | 0 | 0 | 14.8065 | Open | 29357 | 2026-06 | Monitor
ORD-0145 | PRJ-003 | Cedar Residence | Retail | SUP-03 | Phoenicia Electrical | Lebanon | CAT-02 | Outdoor Lighting | 2026-06-29 07:12 | 2026-06-30 07:12 | 2026-06-30 07:12 | 2026-07-21 07:12 | 2026-07-25 07:12 | 11774 | 9203 | 2026-07-31 07:12 |  | 45 | Documentation | Complete missing document and revalidate order | 2571 | 21.84% | 25 | Late | 4 | 11774 | 10.6998 | Open | 11774 | 2026-06 | P3
ORD-0104 | PRJ-011 | Keystone Residence | Hospitality | SUP-11 | Orient Emergency Systems | Malaysia | CAT-04 | Emergency Lighting | 2026-06-22 14:46 | 2026-06-29 14:46 | 2026-06-30 14:46 | 2026-09-02 14:46 |  | 26185 | 20350 |  |  | 45 | Payment blocker | Coordinate payment release with finance | 5835 | 22.28% | 41.3844 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-06 | Monitor
ORD-0323 | PRJ-011 | Keystone Residence | Hospitality | SUP-08 | Gulf Smart Controls | UAE | CAT-03 | Lighting Controls | 2026-06-25 17:21 | 2026-06-30 17:21 | 2026-07-01 17:21 | 2026-08-10 17:21 |  | 17930 | 12465 |  |  | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 5465 | 30.48% | 40.2774 | Open | 0.27738 | 17930 |  | Not Invoiced | 0 | 2026-07 | P3
ORD-0153 | PRJ-015 | Olive Gardens | Public Sector | SUP-03 | Phoenicia Electrical | Lebanon | CAT-05 | Architectural Fixtures | 2026-06-24 01:46 | 2026-06-29 01:46 | 2026-07-02 01:46 | 2026-07-28 01:46 | 2026-07-25 01:46 | 20555 | 13800 | 2026-07-26 01:46 |  | 45 | None | Monitor to plan | 6755 | 32.86% | 23 | On Time | 0 | 0 | 15.9266 | Open | 20555 | 2026-07 | Monitor
ORD-0108 | PRJ-015 | Olive Gardens | Public Sector | SUP-02 | Levant Controls | Lebanon | CAT-05 | Architectural Fixtures | 2026-06-23 11:14 | 2026-06-30 11:14 | 2026-07-02 11:14 | 2026-07-22 11:14 |  | 29995 | 20670 |  |  | 30 | None | Monitor to plan | 9325 | 31.09% | 39.5317 | Open | 19.5317 | 29995 |  | Not Invoiced | 0 | 2026-07 | P1
ORD-0251 | PRJ-013 | Meridian Campus | Retail | SUP-01 | Cedar Components | Lebanon | CAT-05 | Architectural Fixtures | 2026-07-01 22:41 | 2026-07-05 22:41 | 2026-07-06 22:41 | 2026-07-31 22:41 |  | 56669 | 42683 |  |  | 45 | None | Monitor to plan | 13986 | 24.68% | 35.0549 | Open | 10.0549 | 56669 |  | Not Invoiced | 0 | 2026-07 | P1
ORD-0244 | PRJ-001 | Atlas Hotel | Hospitality | SUP-05 | Aegean Systems | Greece | CAT-03 | Lighting Controls | 2026-07-05 10:00 | 2026-07-08 10:00 | 2026-07-09 10:00 | 2026-08-19 10:00 |  | 12743 | 8991 |  |  | 30 | None | Monitor to plan | 3752 | 29.44% | 32.5834 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0041 | PRJ-001 | Atlas Hotel | Hospitality | SUP-06 | Alpine Illumination | Italy | CAT-01 | Indoor Lighting | 2026-07-05 21:09 | 2026-07-06 21:09 | 2026-07-10 21:09 | 2026-09-03 21:09 |  | 37130 | 29200 |  |  | 60 | None | Monitor to plan | 7930 | 21.36% | 31.1187 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0260 | PRJ-002 | Beacon Offices | Commercial | SUP-07 | Nordic Beam | Germany | CAT-06 | Electrical Accessories | 2026-07-05 07:57 | 2026-07-10 07:57 | 2026-07-14 07:57 | 2026-09-05 07:57 |  | 6452 | 5001 |  |  | 45 | None | Monitor to plan | 1451 | 22.49% | 27.6688 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0353 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-05 | Aegean Systems | Greece | CAT-05 | Architectural Fixtures | 2026-07-13 08:06 | 2026-07-14 08:06 | 2026-07-17 08:06 | 2026-08-29 08:06 |  | 58367 | 47118 |  |  | 45 | None | Monitor to plan | 11249 | 19.27% | 24.6622 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0214 | PRJ-014 | Northgate Complex | Residential | SUP-06 | Alpine Illumination | Italy | CAT-04 | Emergency Lighting | 2026-06-28 18:25 | 2026-07-17 18:25 | 2026-07-18 18:25 | 2026-09-04 18:25 |  | 13352 | 8948 |  |  | 30 | Client approval | Confirm decision owner and approval deadline | 4404 | 32.98% | 23.2328 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0220 | PRJ-009 | Iris Resort | Residential | SUP-05 | Aegean Systems | Greece | CAT-04 | Emergency Lighting | 2026-07-16 01:32 | 2026-07-19 01:32 | 2026-07-19 01:32 | 2026-09-04 01:32 |  | 18237 | 13456 |  |  | 45 | None | Monitor to plan | 4781 | 26.22% | 22.9359 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0114 | PRJ-010 | Juniper Mall | Public Sector | SUP-02 | Levant Controls | Lebanon | CAT-06 | Electrical Accessories | 2026-07-13 02:20 | 2026-07-16 02:20 | 2026-07-20 02:20 | 2026-08-16 02:20 | 2026-08-10 02:20 | 18945 | 13067 | 2026-08-10 02:20 |  | 30 | None | Monitor to plan | 5878 | 31.03% | 21 | On Time | 0 | 0 | 0.90258 | Open | 18945 | 2026-07 | Monitor
ORD-0275 | PRJ-004 | District Retail | Residential | SUP-10 | Pacific Fixtures | China | CAT-02 | Outdoor Lighting | 2026-07-13 04:33 | 2026-07-17 04:33 | 2026-07-20 04:33 | 2026-10-11 04:33 |  | 33526 | 24651 |  |  | 30 | None | Monitor to plan | 8875 | 26.47% | 21.8105 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0023 | PRJ-009 | Iris Resort | Residential | SUP-06 | Alpine Illumination | Italy | CAT-02 | Outdoor Lighting | 2026-07-16 22:46 | 2026-07-19 22:46 | 2026-07-22 22:46 | 2026-09-13 22:46 |  | 43694 | 33366 |  |  | 60 | None | Monitor to plan | 10328 | 23.64% | 19.0515 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0106 | PRJ-005 | Elm Hospital | Public Sector | SUP-06 | Alpine Illumination | Italy | CAT-02 | Outdoor Lighting | 2026-07-16 00:24 | 2026-07-20 00:24 | 2026-07-23 00:24 | 2026-09-19 00:24 |  | 15475 | 12019 |  |  | 45 | None | Monitor to plan | 3456 | 22.33% | 18.9833 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0120 | PRJ-003 | Cedar Residence | Retail | SUP-07 | Nordic Beam | Germany | CAT-04 | Emergency Lighting | 2026-07-18 02:14 | 2026-07-25 02:14 | 2026-07-25 02:14 | 2026-09-19 02:14 |  | 14506 | 11581 |  |  | 30 | Supplier lead time | Escalate supplier and confirm recovery date | 2925 | 20.16% | 16.9072 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0256 | PRJ-012 | Lighthouse Hotel | Commercial | SUP-09 | Pearl LED Works | China | CAT-01 | Indoor Lighting | 2026-07-21 17:32 | 2026-07-23 17:32 | 2026-07-25 17:32 | 2026-10-11 17:32 |  | 34203 | 25090 |  |  | 30 | None | Monitor to plan | 9113 | 26.64% | 16.2695 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0217 | PRJ-004 | District Retail | Residential | SUP-12 | Atlas Outdoor | Spain | CAT-06 | Electrical Accessories | 2026-07-20 22:12 | 2026-07-24 22:12 | 2026-07-25 22:12 | 2026-09-16 22:12 |  | 20708 | 16395 |  |  | 30 | None | Monitor to plan | 4313 | 20.83% | 16.0753 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0191 | PRJ-004 | District Retail | Residential | SUP-09 | Pearl LED Works | China | CAT-02 | Outdoor Lighting | 2026-07-22 23:06 | 2026-07-25 23:06 | 2026-07-25 23:06 | 2026-10-13 23:06 |  | 44029 | 34929 |  |  | 30 | None | Monitor to plan | 9100 | 20.67% | 16.0372 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0038 | PRJ-007 | Garden Villas | Commercial | SUP-11 | Orient Emergency Systems | Malaysia | CAT-05 | Architectural Fixtures | 2026-07-23 08:53 | 2026-07-26 08:53 | 2026-07-26 08:53 | 2026-09-25 08:53 |  | 20574 | 14295 |  |  | 30 | None | Monitor to plan | 6279 | 30.52% | 15.6299 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0374 | PRJ-006 | Forum Center | Hospitality | SUP-07 | Nordic Beam | Germany | CAT-05 | Architectural Fixtures | 2026-07-24 17:30 | 2026-07-30 17:30 | 2026-07-30 17:30 | 2026-09-20 17:30 |  | 35922 | 28475 |  |  | 30 | Payment blocker | Coordinate payment release with finance | 7447 | 20.73% | 11.2712 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-07 | Monitor
ORD-0334 | PRJ-014 | Northgate Complex | Residential | SUP-01 | Cedar Components | Lebanon | CAT-01 | Indoor Lighting | 2026-07-28 17:52 | 2026-07-30 17:52 | 2026-07-31 17:52 | 2026-08-13 17:52 | 2026-08-09 17:52 | 23451 | 15611 | 2026-08-09 17:52 |  | 30 | Documentation | Complete missing document and revalidate order | 7840 | 33.43% | 9 | On Time | 0 | 0 | 1.2559 | Open | 23451 | 2026-07 | Monitor
ORD-0259 | PRJ-009 | Iris Resort | Residential | SUP-03 | Phoenicia Electrical | Lebanon | CAT-05 | Architectural Fixtures | 2026-07-23 22:26 | 2026-07-30 22:26 | 2026-08-01 22:26 | 2026-08-22 22:26 |  | 20468 | 15929 |  |  | 30 | None | Monitor to plan | 4539 | 22.18% | 9.065 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-08 | Monitor
ORD-0257 | PRJ-008 | Harbor Offices | Retail | SUP-10 | Pacific Fixtures | China | CAT-04 | Emergency Lighting | 2026-07-27 07:51 | 2026-08-01 07:51 | 2026-08-02 07:51 | 2026-10-26 07:51 |  | 10237 | 7901 |  |  | 30 | None | Monitor to plan | 2336 | 22.82% | 8.6728 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-08 | Monitor
ORD-0132 | PRJ-003 | Cedar Residence | Retail | SUP-04 | Anatolia Lighting | Turkey | CAT-02 | Outdoor Lighting | 2026-07-30 15:00 | 2026-08-02 15:00 | 2026-08-02 15:00 | 2026-09-15 15:00 |  | 33487 | 24716 |  |  | 45 | None | Monitor to plan | 8771 | 26.19% | 8.3747 | Open | 0 | 0 |  | Not Invoiced | 0 | 2026-08 | Monitor

## Monthly Trend
PO Month | Order Value | Gross Profit | Gross Margin | On-Time Delivery | Delayed Value
2025-01 | 541493 | 140325 | 25.91% | 57.14% | 174546
2025-02 | 301940 | 81353 | 26.94% | 68.75% | 102096
2025-03 | 430631 | 109483 | 25.42% | 65.22% | 153023
2025-04 | 463749 | 122065 | 26.32% | 63.64% | 156570
2025-05 | 495798 | 127143 | 25.64% | 92% | 35278
2025-06 | 340545 | 88611 | 26.02% | 76.47% | 73281
2025-07 | 598913 | 155487 | 25.96% | 73.91% | 132481
2025-08 | 605389 | 152977 | 25.27% | 61.54% | 239374
2025-09 | 433343 | 111075 | 25.63% | 84.21% | 78267
2025-10 | 421859 | 115642 | 27.41% | 61.9% | 174937
2025-11 | 417391 | 109314 | 26.19% | 68.42% | 164132
2025-12 | 523330 | 142118 | 27.16% | 68% | 156557
2026-01 | 647618 | 175827 | 27.15% | 65.52% | 235309
2026-02 | 506651 | 145436 | 28.71% | 55% | 186373
2026-03 | 372886 | 93968 | 25.2% | 62.5% | 155234
2026-04 | 504308 | 124850 | 24.76% | 86.96% | 45744
2026-05 | 456647 | 120756 | 26.44% | 60.87% | 157933
2026-06 | 625041 | 161650 | 25.86% | 71.43% | 180982

## Project Performance
Project | Segment | Orders | Order Value | Open Orders | On-Time Delivery | Delayed Value | Outstanding | Health Score | Risk
Atlas Hotel | Hospitality | 23 | 463961 | 5 | 72.22% | 117127 | 80265 | 75.2043 | Low
Beacon Offices | Commercial | 30 | 603168 | 2 | 71.43% | 137710 | 146950 | 74.2794 | Medium
Cedar Residence | Retail | 31 | 673684 | 3 | 60.71% | 226877 | 150200 | 66.0754 | Medium
District Retail | Residential | 35 | 773365 | 4 | 67.74% | 169639 | 174093 | 73.3043 | Medium
Elm Hospital | Public Sector | 31 | 642094 | 1 | 66.67% | 208680 | 133696 | 69.4607 | Medium
Forum Center | Hospitality | 32 | 744766 | 1 | 74.19% | 149338 | 147814 | 77.3996 | Low
Garden Villas | Commercial | 23 | 595065 | 4 | 78.95% | 161583 | 0 | 81.0225 | Low
Harbor Offices | Retail | 29 | 592789 | 1 | 67.86% | 146380 | 106947 | 73.2847 | Medium
Iris Resort | Residential | 31 | 747470 | 3 | 75% | 199013 | 140642 | 75.6681 | Low
Juniper Mall | Public Sector | 25 | 502961 | 1 | 70.83% | 157149 | 113519 | 71.4253 | Medium
Keystone Residence | Hospitality | 24 | 505595 | 4 | 75% | 78253 | 72872 | 80.4503 | Low
Lighthouse Hotel | Commercial | 27 | 621262 | 2 | 56% | 232637 | 134349 | 62.7689 | Medium
Meridian Campus | Retail | 27 | 646684 | 1 | 65.38% | 276025 | 181795 | 63.8616 | Medium
Northgate Complex | Residential | 24 | 487003 | 1 | 73.91% | 131404 | 98077 | 74.7893 | Medium
Olive Gardens | Public Sector | 28 | 728320 | 2 | 69.23% | 314896 | 172039 | 66.297 | Medium

## Supplier Performance
Supplier | Country | Orders | Order Value | On-Time Delivery | Average Delay Days | Gross Margin
Cedar Components | Lebanon | 31 | 744386 | 73.33% | 2.4211 | 27.01%
Levant Controls | Lebanon | 37 | 752398 | 71.43% | 3.8627 | 27.99%
Phoenicia Electrical | Lebanon | 42 | 922892 | 72.5% | 2.5919 | 25.63%
Anatolia Lighting | Turkey | 34 | 820119 | 60.61% | 3.4118 | 26.76%
Aegean Systems | Greece | 39 | 968927 | 69.44% | 2.2308 | 25.09%
Alpine Illumination | Italy | 31 | 661195 | 59.26% | 3.9032 | 26.95%
Nordic Beam | Germany | 28 | 527180 | 69.57% | 0.89286 | 24.72%
Gulf Smart Controls | UAE | 36 | 864830 | 77.14% | 1.5633 | 26.88%
Pearl LED Works | China | 26 | 580013 | 72.73% | 2.2692 | 25.33%
Pacific Fixtures | China | 40 | 881977 | 65.79% | 3.55 | 26.02%
Orient Emergency Systems | Malaysia | 36 | 634552 | 62.07% | 4.5833 | 24.55%
Atlas Outdoor | Spain | 40 | 969718 | 75.68% | 2.2 | 26.24%

## Root Cause Analysis
Primary Blocker | Orders | Delayed Value | Average Delay Days | Share of Delayed Value
Supplier lead time | 52 | 1236134 | 13.1538 | 45.67%
Unclassified | 25 | 540530 | 9.8 | 19.97%
Payment blocker | 17 | 345305 | 2.9412 | 12.76%
Shipping / customs | 14 | 243095 | 10 | 8.981%
Client approval | 7 | 172155 | 5.8571 | 6.36%
Documentation | 8 | 169492 | 3.625 | 6.262%
Data-quality note: 'Unclassified' means a delayed order has no usable blocker. It is surfaced for correction, not hidden.

## KPI Dictionary
KPI DICTIONARY
KPI | Definition | Unit | Management use | Formula / source | Owner | Grain / denominator | Time basis | Quality rule
Total Order Value | Sum of order value | USD | Commercial scale | SUM(Order_Value_USD) | Commercial Manager | All orders | PO date; as-of 11 Aug 2026 | Value >= 0
Gross Profit | Order value less cost | USD | Value generated before overhead | SUM(Order_Value_USD - Cost_USD) | Finance | All orders | PO date | Value and cost >= 0
Gross Margin | Gross profit / order value | % | Pricing quality | Gross Profit / Total Order Value | Finance | All orders | PO date | Order value cannot be zero
On-Time Delivery | Delivered on/before promise / delivered | % | Delivery reliability | On Time / (On Time + Late) | Operations | Delivered orders only | Actual vs promised date | Open orders excluded
Delayed Order Value | Value of orders with delay days > 0 | USD | Commercial exposure | SUM(Delayed_Value_USD) | Operations | Delayed orders | As-of 11 Aug 2026 | Delay cannot be negative
Outstanding Receivables | Invoiced value not paid | USD | Cash exposure | SUM(Outstanding_USD) | Finance | Open + overdue invoices | As-of 11 Aug 2026 | Invoice required
Overdue Receivables | Outstanding value past due date | USD | Collection urgency | SUMIF(Payment_Status, Overdue) | Finance | Overdue invoices | Invoice + terms vs as-of | Invoice required
Average Lead Time | PO to actual delivery or as-of | Days | Cycle-time monitoring | AVERAGE(Lead_Time_Days) | Operations | All orders | As-of 11 Aug 2026 | End date >= PO date
Average Collection Days | Invoice to payment or as-of | Days | Collection performance | AVERAGE(Collection_Days) | Finance | Invoiced orders | As-of 11 Aug 2026 | Payment requires invoice
At-Risk Orders | Orders with delay days > 0 | Count | Exception workload | COUNTIF(Delay_Days, >0) | Operations | Delayed orders | As-of 11 Aug 2026 | Priority rule documented
At-Risk Order Value | Order value where delay days > 0 | USD | Prioritise exposure | SUM(Delayed_Value_USD) | Operations | Delayed orders | As-of 11 Aug 2026 | Tie to order ID
Unclassified Delayed Value | Delayed value with blocker = None | USD / % | Data-quality follow-up | SUMIFS(Delayed_Value, Blocker=None) | Data Owner | Delayed orders | As-of 11 Aug 2026 | Target = 0
Risk Priority | P1 overdue/high value/15+ days; P2 7+ days/$20k+; P3 other delays | Band | Daily action order | Orders.Risk_Priority | Operations | One label per order | As-of 11 Aug 2026 | Transparent thresholds

## BA Pack
BUSINESS ANALYSIS PACK
PROBLEM STATEMENT | Order information is spread across follow-ups, approvals, supplier updates, delivery milestones, invoices, and payments. Management needs one reliable view of status, risk, value, and action ownership.
BUSINESS OBJECTIVE | Create a controlled order-to-delivery view that reduces manual status consolidation, surfaces exceptions early, and supports weekly management decisions.
STAKEHOLDERS | Operations ¦ Sales ¦ Procurement ¦ Finance ¦ Project coordination ¦ Management ¦ Suppliers
SCOPE | From approved quotation and purchase order through delivery, invoicing, and payment follow-up. The case study does not include ERP configuration or software development.
BUSINESS REQUIREMENTS
ID | Requirement | Priority | Owner | Acceptance criteria
BR-01 | Management must see current order value, stage, delivery risk, and action owner in one view. | High | Operations | Every active order shows stage, value, risk, blocker, and action.
BR-02 | Late and at-risk deliveries must be visible before the weekly review. | High | Operations | All open past-due and late delivered orders are classified without manual flags.
BR-03 | Supplier performance must use consistent lead-time and on-time definitions. | High | Procurement | Supplier view shows orders, value, on-time rate, delay days, and margin.
BR-04 | Operations and finance must share one invoicing and payment-status definition. | High | Finance | Status is derived from invoice date, terms, payment date, and as-of date.
BR-05 | Every KPI must be traceable to a source field and documented calculation. | Medium | Reporting | KPI Dictionary identifies definition, unit, management use, and source field.
BR-06 | Portfolio reporting must not expose confidential production records. | High | Project Owner | Workbook, SQL, and case study contain synthetic records only.
USER STORIES & ACCEPTANCE CRITERIA
ID | User story | Acceptance criteria
US-01 | As a manager, I want a KPI summary so that I can understand order value, margin, delay, and collection exposure before the weekly review. | Dashboard shows current values from the Orders table and contains no manual KPI inputs.
US-02 | As an operations coordinator, I want delayed orders highlighted so that I can focus follow-up on the highest-value exceptions. | Every late or overdue order is visibly classified and includes a recommended management action.
US-03 | As a procurement user, I want supplier reliability compared consistently so that I can support sourcing and escalation decisions. | Supplier page shows order count, value, on-time rate, average delay, and margin using one KPI definition.
US-04 | As a finance user, I want unpaid invoices separated into open and overdue so that I can prioritize collection follow-up. | Payment status uses invoice date, terms, payment date, and the documented as-of date.
RECOMMENDED OPERATING ACTIONS
Priority | Action | Owner | Cadence
1 | Create an exception-first weekly review focused on late value, overdue receivables, and blockers. | Operations Lead | Weekly
2 | Agree recovery dates with suppliers whose on-time rate falls below the target. | Procurement | Monthly
3 | Assign a named decision owner and deadline to every client-approval blocker. | Sales / Project | Per exception
4 | Reconcile delivery, invoice, and payment milestones before reporting collection performance. | Operations / Finance | Weekly

## Process & RACI
PROCESS DESIGN & RACI
CURRENT STATE — WHERE CONTROL BREAKS
Step | Activity | Owner | Current tool | Control gap | Business impact | Required control
1 | Approved quotation | Sales | Email / file | Requirements may be incomplete | Rework after PO | Completeness check before handoff
2 | Purchase order | Operations | Spreadsheet | Approval timing unclear | Late supplier commitment | Approval timestamp and owner
3 | Supplier follow-up | Procurement | Email / messaging | Updates not centralized | Risk discovered late | Weekly exception log
4 | Delivery coordination | Operations | Manual tracker | Promise date changes not governed | Customer escalation | Baseline and recovery dates
5 | Invoice handoff | Operations / Finance | Email | Delivery and invoice status differ | Delayed billing | Delivery-to-invoice reconciliation
6 | Payment follow-up | Finance | Separate file | Actions disconnected from order status | Overdue exposure | Shared payment status and owner
FUTURE STATE — EXCEPTION-FIRST CONTROL
Step | Activity | Control | Owner | Cadence | Output
1 | Validate handoff | Required fields complete | Sales | Before PO | Approved handoff
2 | Create PO baseline | Promise date and value recorded | Operations | At PO | Controlled baseline
3 | Monitor exceptions | Past-due and high-value risks flagged | Operations | Daily | Exception queue
4 | Escalate supplier risk | Recovery date and owner assigned | Procurement | Weekly | Recovery plan
5 | Reconcile milestones | Delivery, invoice, and payment aligned | Operations / Finance | Weekly | Reliable status
6 | Review performance | KPI trend and root cause reviewed | Management | Monthly | Decision log
RACI — WHO OWNS EACH CONTROL
Control | Sales | Operations | Procurement | Finance | Management
Order handoff quality | R | C | I | I | A
Supplier recovery plan | I | C | R | I | A
Delivery exception action | C | R | C | I | A
Invoice reconciliation | I | R | I | R | A
Payment collection action | I | C | I | R | A
Monthly performance review | C | R | C | C | A
IMPLEMENTATION ROADMAP
Phase | Timing | Work | Deliverable
1. Define | Week 1 | Confirm fields, KPI definitions, owners, and review cadence | Approved KPI dictionary
2. Build | Weeks 2–3 | Create data model, validation rules, exception logic, and dashboard | Testable prototype
3. Validate | Week 4 | Reconcile sample orders and complete user acceptance testing | Signed UAT log
4. Adopt | Weeks 5–6 | Train users, start weekly review, and track issue resolution | Operating control

## Project Guide
ORDER-TO-DELIVERY OPERATIONS CONTROL TOWER
Project field | Value
Candidate | Youssef Khoury
Target roles | Data Analyst ¦ Operations Analyst ¦ Business Analyst ¦ ERP Support
As-of date | 2026-08-11
Dataset | 420 synthetic orders ¦ PO dates Jan 2025-Aug 2026 ¦ deliveries through 10 Aug 2026
Purpose | Show how operational data, KPI reporting, and requirements analysis support management decisions
Tools represented | Excel, SQL Server, SQL, Power Query, Power BI-ready star schema, DAX, data-quality validation
Confidentiality | All project, supplier, value, date, and performance information is synthetic
HOW TO PRESENT THIS PROJECT
1. Start with the business problem: delayed deliveries, scattered follow-up, and limited visibility.
2. Explain the model: orders connect projects, suppliers, products, delivery milestones, invoices, and payments.
3. Show the executive KPIs, then open Action Center to explain how risk is prioritised.
4. Use supplier, project, root-cause, and Data Quality pages to explain drivers and caveats.
5. Finish with requirements, UAT, process controls, RACI, and the implementation roadmap.
6. State that all data is synthetic and position the work as analysis and decision support, not ERP configuration.
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This documented as-of date drives open-order lead time, delay days, collection days, and overdue classification.
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This documented as-of date drives open-order lead time, delay days, collection days, and overdue classification.

## Action Center
ACTION CENTER
Prioritised exception queue ¦ Formula-derived rules ¦ Synthetic data ¦ As of 11 Aug 2026
AT-RISK ORDERS |  |  | AT-RISK ORDER VALUE |  |  | OVERDUE RECEIVABLES |  |  | UNCLASSIFIED DELAYED VALUE
123 |  |  | 2706711 |  |  | 1288470 |  |  | 540530
TOP 20 P1 EXCEPTIONS — sorted by priority, delayed value, then delay days
Priority | Order ID | Project | Supplier | Delivery | Payment | Order Value | Delay Days | Delayed Value | Outstanding | Blocker | Manager Action
P1 | ORD-0251 | Meridian Campus | Cedar Components | Open | Not Invoiced | 56669 | 11 | 56669 | 0 | Unclassified | Assign owner and capture blocker before review
P1 | ORD-0412 | Meridian Campus | Cedar Components | Late | Paid | 54053 | 7 | 54053 | 0 | Supplier lead time | Escalate supplier and confirm recovery date
P1 | ORD-0165 | Garden Villas | Phoenicia Electrical | Open | Not Invoiced | 51650 | 19 | 51650 | 0 | Unclassified | Assign owner and capture blocker before review
P1 | ORD-0358 | Iris Resort | Pacific Fixtures | Late | Overdue | 46921 | 5 | 46921 | 46921 | Client approval | Confirm decision owner and approval deadline
P1 | ORD-0279 | Juniper Mall | Alpine Illumination | Late | Paid | 45614 | 4 | 45614 | 0 | Supplier lead time | Escalate supplier and confirm recovery date
P1 | ORD-0370 | Cedar Residence | Gulf Smart Controls | Late | Paid | 45421 | 2 | 45421 | 0 | Supplier lead time | Escalate supplier and confirm recovery date
P1 | ORD-0090 | Garden Villas | Atlas Outdoor | Late | Paid | 44725 | 20 | 44725 | 0 | Supplier lead time | Escalate supplier and confirm recovery date
P1 | ORD-0287 | Olive Gardens | Aegean Systems | Late | Paid | 44466 | 18 | 44466 | 0 | Supplier lead time | Escalate supplier and confirm recovery date
P1 | ORD-0089 | Meridian Campus | Pearl LED Works | Late | Overdue | 44095 | 1 | 44095 | 44095 | Payment blocker | Coordinate payment release with finance
P1 | ORD-0232 | Forum Center | Gulf Smart Controls | Late | Open | 43809 | 19 | 43809 | 43809 | Supplier lead time | Escalate supplier and confirm recovery date
P1 | ORD-0199 | Elm Hospital | Aegean Systems | Late | Paid | 41366 | 3 | 41366 | 0 | Payment blocker | Coordinate payment release with finance
P1 | ORD-0294 | Elm Hospital | Aegean Systems | Late | Overdue | 40970 | 6 | 40970 | 40970 | Unclassified | Assign owner and capture blocker before review
P1 | ORD-0270 | Olive Gardens | Phoenicia Electrical | Late | Paid | 40940 | 16 | 40940 | 0 | Supplier lead time | Escalate supplier and confirm recovery date
P1 | ORD-0354 | Elm Hospital | Cedar Components | Late | Overdue | 39552 | 23 | 39552 | 39552 | Supplier lead time | Escalate supplier and confirm recovery date
P1 | ORD-0406 | Northgate Complex | Cedar Components | Late | Paid | 37867 | 17 | 37867 | 0 | Supplier lead time | Escalate supplier and confirm recovery date
P1 | ORD-0218 | Olive Gardens | Pacific Fixtures | Late | Paid | 35209 | 16 | 35209 | 0 | Unclassified | Assign owner and capture blocker before review
P1 | ORD-0366 | Olive Gardens | Alpine Illumination | Late | Paid | 34504 | 21 | 34504 | 0 | Supplier lead time | Escalate supplier and confirm recovery date
P1 | ORD-0302 | Cedar Residence | Pearl LED Works | Late | Paid | 34051 | 23 | 34051 | 0 | Supplier lead time | Escalate supplier and confirm recovery date
P1 | ORD-0328 | Olive Gardens | Levant Controls | Open | Not Invoiced | 33386 | 25 | 33386 | 0 | Unclassified | Assign owner and capture blocker before review
P1 | ORD-0068 | Beacon Offices | Gulf Smart Controls | Late | Overdue | 32091 | 2 | 32091 | 32091 | Documentation | Complete missing document and revalidate order
PRIORITY LOGIC
P1 = overdue receivable OR delayed value >= $40k OR delay >= 15 days. P2 = delay >= 7 days OR delayed value >= $20k. P3 = any other delayed order. Monitor = no delay. The queue is a management aid, not an automated decision; owners validate each exception before action.

## Data Quality
DATA QUALITY & CONTROL EVIDENCE
Automated validation summary ¦ 420 synthetic orders ¦ Validator + SQL checks
ORDERS TESTED |  | DUPLICATE IDS |  | INVALID DATE ROWS |  | ORPHAN DIMENSIONS
420 |  | 0 |  | 0 |  | 0
UNCLASSIFIED DELAYED ORDERS |  |  |  | UNCLASSIFIED DELAYED VALUE
25 |  |  |  | 540530
Control | Status | Rows | Value | Rule | Evidence
Unique Order ID | PASS | 0 | — | No duplicate Order_ID | validate_portfolio.py / SQL check 1
Date chronology | PASS | 0 | — | Quote <= approval <= PO <= promised; later dates valid | Validator / SQL check 2
Financial validity | PASS | 0 | $0 invalid | Value, cost, and terms are non-negative | Validator / SQL check 3
Dimension integrity | PASS | 0 | — | Every project, supplier, category key resolves | Validator / SQL check 4
Payment dependency | PASS | 0 | — | Payment date cannot exist without invoice | Validator / SQL check 5
Core field completeness | PASS | 0 | 100% | Required IDs and dates populated | Validator / data dictionary
Delayed blocker coverage | REVIEW | 25 | $540,530 | Delayed orders should have a usable blocker | SQL check 7 / Action Center
KPI reconciliation | PASS | 0 | $9,328,187 | Excel totals tie to source extract | Dashboard / SQL reconciliation
WHAT THIS MEANS
The dataset is structurally clean and reconciles to the executive KPIs. The only material issue is blocker completeness: 25 delayed orders, representing 20.0% of delayed value, are unclassified. A professional analyst should not guess those causes; the Action Center assigns them for owner follow-up and the quality target is zero unclassified delayed exposure.